## 2025
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2024-12-30 |  | 1 |  |  |  |  | 2025-01-06 |  | 2 |  |  |  |  | 2025-01-13 |  | 3
Franck |  | Congé |  |  | 5 |  |  | 1 | CMS |  | Chassis demontage tete pompe LEWA | 1 | 1 | Cédric
[8 empty] | 1 | CMS |  | Inheritance | 0.5 | 0.5 | Cédric | 1 | Atlas - CMS |  | Surface Storage | 3 | 2 | Jerome
[8 empty] | 1 | CMS |  | HGTD L Manifold | 4 | 3.2 | Jér - Karol | 1 | CMS |  | HGTD L Manifold | 2 | 2 | Jér - Karol
[8 empty] | 1 | CMS |  | Dog leg | 0.3 | 0.3 | Cédric |  | CMS |  | Dog leg |  | 1
Loic |  | Congé |  |  | 5 |  |  | 1 | CMS |  | Installation Dog Leg / interconnection | 1.5 | 1.5 | Cédric | 1 | ATLAS |  | IBL - B Maintenance lundi am - mardi … | 2 | 1.5 | Cédric - Alexandros
[8 empty] | 1 | CMS | Inheritance | Inheritance CMS Piping / Exhaust | 2.5 | 2.5 | Cédric | 1 | CMS |  | CMS Piping / Inheritance Exhaust | 2 | 3.5 | Cédric
[8 empty] | 1 | CMS |  | Chassis demontage tete pompe LEWA | 1 | 1 | Cédric
[16 empty] | ATLAS |  | installation armoire elec | 1 | 0 | Cédric
Abdel |  | Congé |  |  | 5 |  |  | 2 | LHCB |  | RICH 1 recuperation new | 4.5 | 4.5 | Patrick | 2 | LHCB |  | RICH 1 recuperation new | 3.5 | 4 | Patrick
[9 empty] | congé |  | vendredi AM | 0.5 | 0.5 |  |  | congé |  | jeudi AM | 0.5 | 0.5
[15 empty] | 1 | ATLAS |  | SR1 flex line | 1 | 0.5 | jerome
Laurent |  | Congé | [12 empty] | 1 | ALICE |  | DUMPER | 2.5 | 3 | Louis-Philippe
[15 empty] | 1 | Atlas - CMS |  | Surface Storage | 2 | 0 | Jerome
[8 empty] | 1 | ATLAS |  | pp2 supply manifold | 3 | 4 | Jerome / Martin |  | SCE |  | réservoir inox |  | 2 | Fred
[9 empty] | Congé |  | Mardi | 1
[8 empty] | 2 | ALICE |  | DUMPER | 1 | 0 | Louis-Philippe
Hervé |  | Congé |  |  | 5 |  |  | 2 | CMS |  | Flushing UX - Modification Racks | 2 | 2 | Andréa | 1 | CMS | usinage | platine inox Accu | 0.5 | 0.3 | Cédric
[8 empty] | 2 | LHCB |  | RICH 1 recuperation new | 3 | 2 | Patrick | 2 | CMS |  | Flushing UX - Modification Racks | 1.5 | 1.5 | Andréa
[9 empty] | CMS |  | HGTD L Manifold | 1 | 1 | Jerome | 2 | LHCB |  | RICH support | 0.2 | 1 | Patrick
[15 empty] | 2 | CMS |  | RPC Frame à usiner | 2 | 1 | Stéphania. Andrea
[15 empty] | 2 | R&D |  | Box 256 | 1 | 1.2 | Mattia
Fabio |  | Congé |  |  | 5 |  |  |  | Congé |  | mardi | 0.5 |  |  | 2 | ATLAS |  | MDT (Flow increase) | 1.5 |  | Mattia
[8 empty] | 2 | ATLAS |  | MDT (Flow increase) | 1.5 |  | Mattia | 2 | ATLAS |  | RPC Flow cell calibration | 1 |  | Pieter / Gianluca
[8 empty] | 2 | ATLAS |  | RPC Flow cell calibration | 3 |  | Pieter / Gianluca | 2 | ATLAS |  | RPC purif 1 démontage colone | 1 | 0 | Mattia
2
[16 empty] | B256 |  | Vendredi matin 17 demontage banc bonkhorst | 0.5 |  | Patrick
[16 empty] | Congé |  | Vendredi AM | 0.5 | 0.5
[8 empty] | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 | 0.5 | Roberto
Jonathan |  | Congé |  |  | 5 |  |  | 2 | ATLAS |  | Purifier | 2 |  | Gianluca | 2 | ATLAS |  | Profibus - Canbus / cable swap | 3 |  | Gianluca
[8 empty] | 2 | LHCB |  | Rich 1 Récupération new | 3 |  | Patrick | 2 | ATLAS |  | RPC Purif 3 test | 0.5 |  | Mattia
[15 empty] | 2 | CMS |  | RPC Purifier 3 test | 0.5 |  | Patrick
[15 empty] | 2 | Congé |  | Vendredi AM | 0.5 | 0.5
[15 empty] | 1 | CMS |  | CO2 maintenance | 0.5 | 0.5 | Loic
Julien |  | Congé |  |  | 5 |  |  | 1 | CMS |  | Cablages Armoires | 5 | 5 | Marcin | 1 | CMS |  | Cablages Armoires | 5 | 5 | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-01-20 |  | 4 |  |  |  |  | 2025-01-27 |  | 5 |  |  |  |  | 2025-02-03 |  | 6
Franck | 1 | CMS |  | DOG LEG Plant / Accu | 3 | 4.5 | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 3 | 4 | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 0.5 | 1.5 | Cédric
[8 empty] | 1 | Atlas - CMS |  | Surface Storage | 1 | 1 | Jerome
| 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | ATLAS |  | CO2 Manifold / B180 clean room | 0.5 |  | Joao / Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
|  | Atlas |  | RPC purif 1 colonne |  | 0.25 | Patrick | 1 | CMS Inheritance |  | soudure tuyaux pompe | 0.5 |  | Cédric | 1 | ATLAS |  | CO2 Manifold / B180 clean room | 3.5 | 3.3 | Joao / Jerome
|  | Réfectoire |  | Déménagement réfection sol | 0.15 | 0.25 | [9 empty] | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2
Loic | 1 | CMS |  | Installation Dog Leg / interconnection | 4 | 3.5 | Cédric | 1 | CMS |  | Installation Dog Leg / interconnection | 2 |  | Cédric
| 1 | CMS Inheritance | Inheritance | CMS Piping / Exhaust | 1 | 0 | Cédric | 1 | CMS Inheritance | Inheritance | CMS Piping / Exhaust | 1 |  | Cédric |  | Maladie |  |  | 5 | 5
| 1 | CMS |  | Aide cablage armoire Julien |  | 1 |  | 1 | Maladie |  | jeudi et vendredi |  | 2
|  | LHCB |  | Maintenance CO2 | 0.5 | 0.25 |  | 1 | LHCB |  | Junction box Maintenance | 1 |  | Cédric
|  | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2
Abdel | [14 empty] | 2 | ATLAS |  | TGC new chanel - rack 63 | 1 |  | Mattia
| 2 | CMS |  | Flushing SX/5 pipe connection D22 | 1 | 1 | Andréa | 2 | LHCB |  | Rich 1 Récupération new | 3 | 1 | Patrick
| 1 | ATLAS |  | SR1 flex line | 0.5 | 0.5 | jerome | 2 | AMBER |  | Rack vert Amber | 1 | 1 | Gianluca / Andréa | 2 | AMBER |  | TPC | 4 | 4.5 | Gianluca
| 2 | ATLAS |  | RPC Purif 1 démontage colone | 3 | 3.3 | Mattia |  | Atlas |  | remontage purif 1 | 1 | 3 | Patrick |  | Réfectoire |  | Déménagement réfection sol | 0.2 | 0
|  | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2 | [9 empty] | Congé |  | Mardi et vendredi AM départ 15h00 | 0.5
Laurent | 1 | Atlas - CMS |  | Surface Storage | 4 | 2.8 | Jerome | [8 empty] | Maladie |  | lundi et mardi |  | 2
|  | CMS |  | Dog leg 1'' | 1 | 2 | Cédric | 1 | ATLAS |  | CO2 Manifold / B180 clean room | 2 | 0 | Joao / Jerome | 1 | ATLAS |  | CO2 Manifold / B180 clean room | 2 |  | Joao / Jerome
[8 empty] | 1 | Atlas - CMS |  | Surface Storage | 2 | 3 | Jerome
|  | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2 |  | 1 | CMS |  | DOG LEG Plant / Accu | 1 | 2 | Cédric |  | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2
Hervé | 2 | R&D |  | Box 256 | 1 | 2 | Mattia.V | 2 | CMS |  | Maintenance pompe RPC | 1 |  | Andréa | 2
| 2 | CMS |  | RPC Frame à usiner | 1 |  | Stéphania. Andrea | 2 | LHCB |  | Rich 1 Récupération new | 3 |  | Patrick | 2 | AMBER |  | TPC | 3.5 | 3.3 | Gianluca
| 2 | CMS |  | HGTD L manifold | 0.5 | 0.5 |  |  | R&D |  | Box 256 | 1 |  | Mattia.V | 1 | CMS |  | HGTD L Manifold et Surface Storage | 1 | 1 | jerome
| 2 | ATLAS |  | RPC Purif 1 démontage colone | 2.3 | 2.5 | Mattia.B |  | congé |  | lundi | 1 |  |  | 2 | CMS |  | SGX/5 support tubes | 0.5 | 0.5 | Andréa
|  | Réfectoire |  | Déménagement réfection sol | 0.2 | [10 empty] | Réfectoire |  | Déménagement réfection sol | 0.2 | 0.2
Fabio | 2 | ATLAS |  | TGC Flow calibration | 1 |  | Mattia | 2 | ATLAS |  | TGC RPC - MMG - Bublers | 2 | 3 | Mattia | 2 | ATLAS |  | RPC - connect new bis line | 1 |  | Mattia
| 2 | CMS |  | Flushing | 1 | 1 | Andréa | 2 | AMBER |  | 2 x Nettoyage Rack vert Amber | 1 | 0.5 | Gianluca / Andréa | 2 | CMS |  | recovery cf4 | 0.5 | 0.5
| 2 | ATLAS |  | RPC Flow cell calibration | 1 |  | Mattia / Pieter | 2 | CMS |  | soupape 904 | 1 | 1 | Andréa | 2 | AMBER |  | 2 x Nettoyage Rack vert Amber | 0.5 |  | Gianluca / Andréa
| 2 | ATLAS |  | Purif 1 démontage colone | 1.2 |  | Mattia |  | ALICE |  | Vendredi Matin capteur sur ALICE MID | 0.5 | 0 | Louis-Philippe |  | CMS |  | Flushing test | 2 |  | Andréa
|  | Réfectoire |  | Déménagement réfection sol | 0.2 | [10 empty] | Réfectoire |  | Déménagement réfection sol | 0.2
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 | 0.5 | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | 2 | ATLAS |  | Profibus - Canbus / cable swap | 3.5 |  | Gianluca | 2 | ALICE |  | TOF Flow meter (backup) | 1 |  | Louis Philippe | 2 | LHCB |  | Rich 1 Récupération new | 4 |  | Patrick
| 2 | ATLAS |  | RPC Purif 1 démontage colone | 1 |  | Mattia | 2 | LHCB |  | Rich 1 Récupération new | 3 |  | Patrick | 2 | R&D |  | Box absorbeur R&D | 1 |  | Maria Christina
| 2 | ATLAS |  | Flow cell replacement | 0.5 |  | Pieter | 2 | ALICE |  | Vendredi Matin capteur sur ALICE MID | 0.5 |  | Louis-Philippe
[9 empty] | CMS |  | Vendredi après-midi CF4 et 134a | 0.5 |  | Patrick |  | Réfectoire |  | Déménagement réfection sol | 0.2
|  | Réfectoire |  | Déménagement réfection sol | 0.2
Julien | 1 | ATLAS - CMS |  | Cablages Armoires | 3 | 3 | Marcin | 1 | ATLAS - CMS |  | Cablages Armoires | 5 |  | Marcin | 1 | ATLAS - CMS |  | Cablages Armoires | 5 |  | Marcin
| 1 | CMS Inheritance |  | Cablages Armoires | 2 | 2 | Marcin
|  | Réfectoire |  | Déménagement réfection sol | 0.2
|  | congé |  | Mardi matin | 0.5 | 0.5
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-02-10 |  | 7 |  |  |  |  | 2025-02-17 |  | 8 |  |  |  |  | 2025-02-24 |  | 9
Franck | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 0.5 | 0 | Cédric | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 3 |  | Cédric | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 3 |  | Cédric
| 1 | ATLAS | J2120142 | HGTD b180 manifold box | 4 | 4.5 | Jerome | [7 empty] | 1 | Atlas - CMS | J2119683 | Surface Storage heaters Assy | 1 |  | Jerome
| 1 | CMS Inheritance | J2119684 | CMS Piping | 0.5 | 0 | Cédric | 1 | ATLAS | J2120142 | HGTD b180 manifold box | 2 |  | Jerome | 1 | ATLAS | J2120142 | HGTD b180 manifold box | 1 |  | Jerome
| 1 | Atlas - CMS | J2119683 | Surface Storage | 0.5 | 0.5 | Jerome
Loic | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 5 |  | Cédric | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 5 |  | Cédric | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 5 |  | Cédric
[8 empty] | 1 | [6 empty] | 1
| 1 | Atlas - CMS | J2119683 | Surface Storage | 0.5 | 0 | Jerome | 1 | Atlas - CMS | J2119683 | Surface Storage | 0.5 | 0 | Jerome | 1 | Atlas - CMS | J2119683 | Surface Storage | 0.5 | 0 | Jerome
Abdel | 2 | AMBER |  | TPC | 5 | 5 | Gianluca | 2 | AMBER | J2119951 | TPC | 4 |  | Gianluca | 2 | AMBER | J2119951 | TPC | 3 |  | Gianluca
[8 empty] | 2 | CMS |  | Flushing USC PH2 | 1 |  | Andréa | 2 | LHCB |  | Rich 1 Récupération new | 1 |  | Patrick
[15 empty] | 1 | ATLAS | J2119690 | SR1 flex line / flex dans étagère livraison | 1 |  | jerome
Laurent | 1 | ATLAS | J2120142 | HGTD b180 manifold box | 4 | 3.5 | Joao | 1 | ATLAS | J2120142 | HGTD b180 manifold box | 3.5 |  | Joao | 1 | ATLAS | J2120142 | HGTD b180 manifold box | 1 | 3 | Joao
| 1 | R&D | J2120141 | Echangeur Krypton | 0.5 | 1 | Bart - Jerome | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 0.5 |  | Cédric | 1 | Atlas - CMS | J2119683 | Surface Storage heaters assy | 3 |  | Jerome
| 1 | CMS | J2119688 | DOG LEG Plant / Accu | 0.5 | 0.5 | Cédric |  | Congé |  | Mardi 18 | 1 | 1
[15 empty] | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 1 |  | Cédric
Hervé | 2 | AMBER | J2119951 | TPC | 2 | 1 | Gianluca | 2 | AMBER | J2119951 | TPC | 2 |  | Gianluca | 2 | AMBER | J2119951 | TPC | 2 |  | Gianluca
[9 empty] | LHCB |  | MWPC Rich pompe purif / MARDI | 1 | 1 | Patrick | 2 | CMS | J2119625 | RPC Frame à usiner | 1.5 |  | Stéphania. Andrea
| 2 | LHCB | J2119619 | Rich 1 Récupération new | 2 | 3 | Patrick | 1 | CMS |  | Usinage réduction cooling | 1.5 |  |  | 2 | GAS |  | Maintenance pompe Atex purif | 0.5 |  | Louis-Philippe
| 2 | LHCB | J2119617 | Muons _ lundi | 1 | 1 | Patrick | 2 | CMS |  | SGX/5 support tubes sur site | 0.5 |  | Andréa | 2 | CMS |  | Flushing USC PH2 | 1 |  | Andréa
Fabio | 2 | AMBER | J2119951 | TPC | 2 | 1.5 | Gianluca
| 2 | LHCB | J2119619 | RICH 1 |  | 0.5 | Patrick | 2 | LHCB |  | rich1 | 1.5 | 1.5 | Damiano / Patrick
| 2 | CMS | J2119615 | Pompe à vide Alcatel | 0.5 | 0.5 | Andréa | 2 | CMS |  | RPC endoscope | 1 |  | Roberto | 2 | CMS |  | Distilation 134a | 2 |  | Andréa
| 2 | CMS | J2119615 | recovery compresseur | 0.5 | 0.5 | Andréa | 2 | CMS | JEUDI 20 | Demontage et Montage flow cell 48X | 0.5 |  | Pieter /Andréa | 2 | CMS |  | Recovery 134a / bac de rétention | 0.5 |  | Andréa
| 2 | CMS | J2119618 | Flushing USC PH2 |  | 0.5 | Andréa | [7 empty] | 2 | R&D |  | Mixeur absorbeur 256 | 2 |  | Amin / Damiano
|  | Congé |  | vendredi | 1 | 1 |  |  | Congé |  | lundi matin et vendredi | 1.5 | 1.5
| 2 | Non LHC | J2119621 | Check of the gas systems | 0.5 | 0.5 | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 | 0.5 | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | [14 empty] | 2 | LHCB |  | RICH 1 | 2 |  | Patrick
[15 empty] | 2 | AMBER |  | TPC | 1.5 |  | Gianluca
| 2 | LHCB | J2119619 | RICH 1 | 5 | 5 | Patrick | 2 | LHCB |  | RICH 1 | 3 |  | Patrick | 2 | Alice |  | Capteur débit Oron | 1 |  | Patrick
[8 empty] | 2 | CMS | J2119618 | Flushing USC PH2 | 2 |  | Patrick | 2 | CMS |  | MFC 2 - récupération 134a | 0.5 |  | Patrick
Julien | 1 | CMS | J2119686 | Cablages Armoires | 4.5 |  | Marcin | 1 | CMS | J2119686 | Cablages Armoires | 4 |  | Marcin | 1 | CMS | J2119686 | Cablages Armoires | 5 |  | Marcin
|  | Congé |  | Jeudi AM | 0.5
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-03-03 |  | 10 |  |  |  |  | 2025-03-10 |  | 11 |  |  |  |  | 2025-03-17 |  | 12
Franck | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 4 |  | Cédric | 1 | CMS | J2119688 | DOG LEG Plant / Accu | 1 | 0 | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 0 |  | Jerome | 1 | CMS |  | Tuyauterie B155 | 0.25 |  | Jerome
[15 empty] | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
| 1 | ATLAS |  | Dummy load connection CO2 + exhaust | 1 |  |  | 1 | ATLAS |  | Dummy load connection CO2 + exhaust | 4 |  | Jerome | 1 | ATLAS |  | Dummy load connection CO2 + exhaust | 4
Loic | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 5 |  | Cédric | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 3 |  | Cédric | 1 | CMS | J2119688 | Installation Dog Leg / interconnection | 3 |  | Cédric
[8 empty] | 1 | ATLAS |  | Dummy load connection CO2 + exhaust | 2 |  | Martin | 1 | ATLAS |  | Dummy load connection CO2 + exhaust | 2 |  | Martin
[8 empty] | 1 | ATLAS |  | Accu plant Installation Dog Leg / interconnection | 0 |  | Cédric
Abdel | 2 | AMBER |  | TPC | 5 |  | Andréa / Gianluca | 2 | AMBER |  | TPC | 2 |  | Andréa / Gianluca | 2 | LHCB |  | Recovery rich 1 | 2 |  | Damiano
| 2 | CMS |  | Recovery 134a / bac de rétention | 0.5 |  | Andréa | 2 | LHCB |  | Recovery rich 1 | 1 |  | Damiano | 2 | AMBER |  | TPC | 3 |  | Andréa / Gianluca
[8 empty] | 1 | Atlas |  | SR1 transfert lines 4 flex | 1 |  | Jerome / George
[8 empty] | 2 | toutes |  | Test capteur pression aging | 1 |  | Mattia.B
Laurent | [7 empty] | 1 | Atlas - CMS |  | Surface Storage heaters assy | 4.5 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage heaters assy | 2 |  | Jerome
| 1 | ATLAS | J2120142 | HGTD b180 manifold box | 2.5 |  | Joao | [7 empty] | 1 | CMS |  | HGTD L Manifold | 3 |  | Jér - Karol
| 1 | ATLAS |  | tuyauterie detecteur SR1. | 1.5 |  | Martin | 1 | CMS |  | Tuyauterie B155 | 0.5 |  | Jerome
|  | Congé |  | Vendredi | 1 | 1
Hervé | 2 | AMBER |  | TPC | 1 |  | Gianluca | [7 empty] | 2 | AMBER |  | TPC | 2 |  | Gianluca
|  | Congé |  | Mardi | 1 |  |  | 2 | CMS | Mardi / Mercredi | USC Flushing démontage pour transport | 1.5 |  | Andréa / Patrick | 2 | CMS |  | SGX5 intervention | 1 |  | Andréa
| 2 | CMS |  | Maintenance pompe GEM + csc | 1 |  | Andréa | 2 | CMS |  | Support tuyau SGX5 | 1 |  | Andréa | 2 | toutes |  | test capteur pression aging | 1
| 2 |  |  | Maintenance pompe atex | 1 |  | Louis-Philippe | 2 | toutes |  | Test capteur pression aging | 1 |  | Mattia.B | 2 |  |  | Chambre avec panneau recup | 1 |  | Stéfania
| 2 | CMS |  | RPC 134a récupération / optique | 1 |  | Andréa | 2 |  |  | Chambre avec panneau recup | 1 |  | Stéfania
[8 empty] | 1 | Atlas CMS |  | Usinage raccords CO2 surface storage | 0.5
Fabio | [7 empty] | 2 | CMS |  | lundi matin cms recupération 134 | 0.5 | 0.5 | Andréa | 2 | ATLAS |  | Massflow control - calibration | 1 |  | Mattia
[8 empty] | 2 | 904 |  | rpc lundi AM Mardi matin | 1 | 1 | Andréa
| 2 | R&D |  | Mixeur absorbeur 256 | 3.5 |  | Amin / Damiano | 2 | R&D |  | Mixeur absorbeur 256 | 1 |  | Amin / Damiano | 2 | R&D |  | Mixeur absorbeur 256 / 134a | 3.5 |  | Amin / Damiano
| 2 | CMS |  | Distilation 134a | 1 |  | Damiano / Andréa |  | Congé |  | Jeudi et Vendredi | 2 | 2
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | [14 empty] | 2 | CMS |  | récupération 134a | 2 |  | Patrick / Andréa
[8 empty] | 2 | CMS | Lundi | USC Flushing décablage et prépa transport | 1 |  | Andréa / Patrick | 2 | Alice |  | Tof or run | 1 |  | LP
| 2 | CMS |  | RPC 134a récupération / optique | 2 |  | Andréa | 2 | CMS | Mardi | RPC ELMB | 1 |  | Pieter | 2 | LHCB |  | Rich1 recovery balance et bande | 0.5 |  | Patrick
[8 empty] | 2 | CMS |  | Fabriquation boite fibre optique 134a | 2 |  | Andréa / Patrick | 2 | ATLAS |  | préparation Chauffage | 0.5 |  | Patrick
[8 empty] | 2 | AGS |  | Chariot stockage mercredi AM | 0.5
[8 empty] | 2 | LHCB |  | Rich1 recovery balance et bande | 0.5
Julien | [15 empty] | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin
| 1 | ATLAS |  | Cablage plant Accu | 5 |  | Cédric | 1 | ATLAS |  | Cablage plant Accu | 5 |  | Cédric
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-03-24 |  | 13 |  |  |  |  | 2025-03-31 |  | 14 |  |  |  |  | 2025-04-07 |  | 15
Franck | 1 | CMS |  | DOG LEG Plant / Accu | 3 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 3 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome
[8 empty] | 1 | ATLAS |  | SR1 transfert line piping on site | 2
Loic | 1 | CMS |  | DOG LEG Plant / Accu | 3 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 3 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 3 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome
Abdel | [7 empty] | 1 | ATLAS |  | SR1 transfert line piping on site | 2 |  |  | 1 | CMS |  | HGTD L Manifold | 1 |  | Jér - Karol
[8 empty] | 2 | CMS |  | Distilation 134a | 1 |  | Andréa | 2 | CMS |  | Distilation 134a | 2 |  | Andréa
| 2 | AMBER |  | TPC Installation | 5 |  | Gianluca | 2 | AMBER |  | TPC Installation | 2 |  | Gianluca | 2 | AMBER |  | TPC Installation | 2 |  | Gianluca
[8 empty] | 2 | CMS |  | USC Flushing | 2 |  | Andréa / Patrick | 2 | CMS |  | SX5 Flushing | 1 |  | Andréa / Patrick
Laurent | 1 | ATLAS |  | PRV Manifolds (2x 50 vannes) | 5 |  |  | 1 | ATLAS |  | PRV Manifolds (2x 50 vannes) | 5 |  |  | 1 | ATLAS |  | PRV Manifolds (2x 50 vannes) | 5
Hervé | [7 empty] | 1 | CMS |  | sgx5 support tuyauterie | 1 |  | Andréa
| 1 | CMS |  | HGTD L Manifold x11 usinage tube / bouchon | 1 |  | Jér - Karol | 1 | CMS |  | HGTD L Manifold x11 usinage tube / bouchon | 1 |  | Jér - Karol | 1 | CMS |  | HGTD L Manifold x11 usinage tube / bouchon | 1 |  | Jér - Karol
| 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
Fabio
| 2 | CMS |  | Distilation 134a | 3.5 |  | Andréa / Daniano | 2 | CMS |  | Distilation 134a | 4 |  | Andréa / Damiano | 2 | CMS |  | Distilation 134a | 2 |  | Andréa
| 2 | B256 |  | Remontage banc Bonkhorst B256 | 1 |  | Patrick
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | 2 | CMS |  | USC Flushing | 4.5 |  | Andréa / Patrick
| 2 | CMS |  | Distilation 134a | 0.5 |  | Andréa | 2 | CMS |  | Distilation 134a | 1 |  | Andréa | 2 | CMS |  | Distilation 134a | 1 |  | Andréa
[8 empty] | 2 | AMBER |  | TPC Installation | 2 |  | Gianluca | 2 | AMBER |  | TPC Installation | 2 |  | Gianluca
[8 empty] | 1 | ATLAS |  | CO2 - Cablages Armoires | 2 |  |  | 1 | ATLAS |  | CO2 - Cablages Armoires | 2
Julien
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-04-14 |  | 16 |  |  |  |  | 2025-04-21 |  | 17 |  |  |  |  | 2025-04-28 |  | 18
Franck
[8 empty] | 1 | CMS |  | HGTD L Manifold x11 | 5 |  | Jér - Karol
| 1 | Atlas - CMS |  | Surface Storage | 5 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 5 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 5 |  | Jerome
Loic | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Abdel | 1 | CMS |  | HGTD L Manifold x11 | 2 |  | Jér - Karol | 1 | CMS |  | HGTD L Manifold x11 | 2 |  | Jér - Karol | 1 | CMS |  | HGTD L Manifold x11 | 1 |  | Jér - Karol
| 2 | CMS |  | Distilation 134a | 2 |  | Andréa | 2 | CMS |  | Distilation 134a | 2 |  | Andréa | 2 | CMS |  | Distilation 134a | 2 |  | Andréa
| 2 | CMS |  | USC Flushing | 1 |  | Andréa / Patrick | 2 | Cloud |  |  | 1 |  | LP / Mattia | 2 | Cloud |  |  | 2 |  | LP / Mattia
Laurent | 1 | CMS |  | HGTD L Manifold x11 | 5 |  | Jér - Karol | 1 | ATLAS |  | SR1 ITK detector splitter boxes | 4 |  |  | 1 | Atlas |  | PP2 Manifold | 5 |  | Jér - Karol Romec
| 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome
Hervé
| 2 | CMS |  | Distilation 134a | 2 |  | Andréa | 2 | CMS |  | Distilation 134a | 1 |  | Andréa | 2 | CMS |  | Distilation 134a | 1 |  | Andréa
| 2 | CMS |  | USC Flushing | 1 |  | Andréa / Patrick
Fabio
[8 empty] | 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | 2 | CMS |  | USC Flushing | 4 |  | Andréa / Patrick | 2 | CMS |  | USC Flushing | 3 |  | Andréa / Patrick
[8 empty] | 2 | 904 |  | Mixeur | 3 |  |  | 2 | 904 |  | Mixeur | 3
| 1 | ATLAS |  | CO2 - Cablages Armoires | 1 |  |  | 1 | ATLAS |  | CO2 - Cablages Armoires | 1 |  |  | 1 | ATLAS |  | CO2 - Cablages Armoires | 1
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-05-05 |  | 19 |  |  |  |  | 2025-05-12 |  | 20 |  |  |  |  | 2025-05-19 |  | 21
Franck | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 4 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
Loic | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 4 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
Abdel | 1 | ATLAS |  | SR1 flex lines (last 4) | 2 |  | Jerome | 1 | ATLAS |  | SR1 flex lines (last 4) | 2 |  | Jerome | 2 | CHARM |  |  | 2
| 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia
Laurent
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Hervé
Fabio
| 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan | [14 empty] | 2 | CHARM |  |  | 2
| 2 | Cloud |  |  | 3 |  | LP / Mattia | [7 empty] | 2 | Cloud |  |  | 2 |  | LP / Mattia
| 1 | ATLAS |  | CO2 - Cablages Armoires | 2 |  |  | 2 | Cloud |  |  | 2 |  | LP / Mattia
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-05-26 |  | 22 |  |  |  |  | 2025-06-02 |  | 23 |  |  |  |  | 2025-06-09 |  | 24
Franck | 1 | CMS |  | DOG LEG Plant / Accu | 4 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Loic | 1 | CMS |  | DOG LEG Plant / Accu | 4 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Abdel
| 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia | 2 | Cloud |  |  | 3 |  | LP / Mattia
Laurent
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-06-16 |  | 25 |  |  |  |  | 2025-06-23 |  | 26 |  |  |  |  | 2025-06-30 |  | 27
Franck | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 1 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Loic | 1 | CMS |  | DOG LEG Plant / Accu | 2 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 2 |  | Cédric | 1 | CMS |  | DOG LEG Plant / Accu | 2 |  | Cédric
| 1 | CMS Inheritance |  | CMS Piping / Exhaust | 1 |  | Cédric | 1 | CMS Inheritance |  | CMS Piping / Exhaust | 1 |  | Cédric | 1 | CMS Inheritance |  | CMS Piping / Exhaust | 1 |  | Cédric
| 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 1 |  | Jerome
Abdel
| 2 | 904 |  | Mixeur | 1 |  | Andréa | 2 | 904 |  | Mixeur | 1 |  | Andréa
| 2 | Cloud |  |  | 4 |  | LP / Mattia | 2 | Cloud |  |  | 4 |  | LP / Mattia
Laurent
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
| 2 | 904 |  | Mixeur | 1 |  | Andréa | 2 | 904 |  | Mixeur | 1 |  | Andréa
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-07-07 |  | 28 |  |  |  |  | 2025-07-14 |  | 29 |  |  |  |  | 2025-07-21 |  | 30
Franck
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Loic
| 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 2 |  | Jerome
Abdel
Laurent
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-07-28 |  | 31 |  |  |  |  | 2025-08-04 |  | 32 |  |  |  |  | 2025-08-11 |  | 33
Franck
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome
Loic
| 1 | Atlas - CMS |  | Surface Storage | 4 |  |  | 1 | Atlas - CMS |  | Surface Storage | 4
Abdel
Laurent
| 1 | Atlas - CMS |  | Surface Storage | 4 |  | Jerome | 1 | Atlas - CMS |  | Surface Storage | 4
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-08-18 |  | 34 |  |  |  |  | 2025-08-25 |  | 35 |  |  |  |  | 2025-09-01 |  | 36
Franck
Loic
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-09-08 |  | 37 |  |  |  |  | 2025-09-15 |  | 38 |  |  |  |  | 2025-09-22 |  | 39
Franck
Loic
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-09-29 |  | 40 |  |  |  |  | 2025-10-06 |  | 41 |  |  |  |  | 2025-10-13 |  | 42
Franck
Loic
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien | 1 | CMS -ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin | 1 | CMS - ATLAS |  | Cablages Armoires | 5 |  | Marcin
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-10-20 |  | 43 |  |  |  |  | 2025-10-27 |  | 44 |  |  |  |  | 2025-11-03 |  | 45
Franck
Loic
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-11-10 |  | 46 |  |  |  |  | 2025-11-17 |  | 47 |  |  |  |  | 2025-11-24 |  | 48
Franck
Loic
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien
2025 |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week |  |  |  |  | Lundi |  | Week
|  | 2025-12-01 |  | 49 |  |  |  |  | 2025-12-08 |  | 50 |  |  |  |  | 2025-12-15 |  | 51
Franck
Loic
Laurent
Abdel
Laurent
Hervé
Fabio
| 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto | 2 | Non LHC |  | Check of the gas systems | 0.5 |  | Roberto
Jonathan
Julien
Formulas:
Lundi = [Lundi]+7

## Welders_Electricians
|  | Now |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun | [6 empty] | July
WELDERS | W | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Franck | 1 | CMS Dog legs | Atlas dummy load | Atlas dummy load | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | … | … | … | … | … | … | …
| 1 | Now 13: CMS Dog legs plant 5; Apr 15: DT/FS valves test stand; Apr 17: CMS Manifolds connection Pablo; Apr 18: CMS Manifolds connection Pablo; May 19: CMS Manifolds connection Pablo
Loic | 1
1
Abdel | 2 | AMBER TPC | AMBER TPC | AMBER TPC | AMBER TPC Installation | AMBER TPC installation | AMBER TPC |  | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD | CLOUD
| 2 | Now 10: Recovery 134a BAC; Now 13: CMS USC Flushing; Now 14: CMS Distilation 134a; Apr 15: CMS Distilation 134a; Apr 16: CMS Distilation 134a; Apr 17: CMS Distilation 134a; Apr 18: CMS Distilation 134a; May 19: CMS Distilation 134a
| 2 | Now 11: Banc aging capteur P; Now 12: CMS Sx5 Flushing; Jun 29: 904 Mixeur Gem
| 1 | Now 12: Atlas SR1 Flex lines; Now 14: Atlas SR1 transfert line on site; Apr 15: CMS HGCAL manifold; Apr 16: CMS HGCAL manifold; Apr 17: CMS HGCAL manifold; Apr 18: CMS HGCAL manifold; May 19: CMS HGCAL manifold; May 20: CMS HGCAL manifold; May 21: CMS HGCAL manifold; May 22: CMS HGCAL manifold
Laurent | 1 | Atlas B180 Manifold | Both SS heaters assy | Both SS heaters assy | Atlas PRV Manifolds (2x 50 vannes) | Atlas PRV Manifolds (2x 50 vannes) | Atlas PRV Manifolds (2x 50 vannes) | Atlas ITK distri rack | Atlas SR1 Splitter boxes | Atlas PP2 Manifold Karol | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | Both Surface Storage | … | … | … | … | … | … | …
| 1 | Now 10: Atlas CO2 lines SR1; Now 12: Atlas B180 Manifold; Now 13: CMS Dog legs plant 5; Apr 15: DT/FS valves test stand; May 19: Atlas SR1 ITK Manifold; Jun 28: Atlas Cable cooling Manifolds
Négociations en cours avec EGTIM
| 1 | [5 empty] | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | CMS dog legs | … | … | … | … | … | … | …
1
Recherche en parallèle :
_ recherche d'un soudeur FSU
_ disponibilité dans autre atelier CERN
…
Jonathan | 2
2
Julien
|  | Now |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun | [6 empty] | July
ELECTRICIANS | W | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Julien | 1 | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | ATLAS cabling / wiring | ATLAS cabling / wiring | ATLAS cabling / wiring | ATLAS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | … | …. | ….
Marc | 1 | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | CMS cabling / wiring | ? | ? | ? | ? | ? | ?
| Xavier | [6 empty] | DSS ? | DSS | DSS | DSS | DSS | DSS | DSS | …. | …. | …. | …. | …. | …. | …. | ….
Murat | 1 | Now 13: ATLAS cabling / wiring; Now 14: ATLAS cabling / wiring; Apr 15: ATLAS cabling / wiring; Apr 16: ATLAS cabling / wiring
| Xavier | [6 empty] | DSS ? | DSS | DSS | DSS | DSS | DSS | DSS | … | … | … | … | … | … | … | …
Jerome | 1 | Now 11: CMS cabling / wiring; Now 12: CMS cabling / wiring; Now 13: CMS cabling / wiring; Now 14: CMS cabling / wiring; Apr 15: CMS cabling / wiring; Apr 16: CMS cabling / wiring; Apr 17: ?; Apr 18: ?; May 19: ?; May 20: ?; May 21: ?; May 22: ?
Jonathan | 2 | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | Gas | … | … | … | … | … | … | … | …
| 1 | Now 13: ATLAS cabling / wiring; Now 14: ATLAS cabling / wiring; Apr 15: ATLAS cabling / wiring; Apr 16: ATLAS cabling / wiring
2
2