## Slide 1: CERN part procurement status on series HL MBRD (D2)
A. Foussat (TE MSC)
on behalf of CERN-INFN WP3 collaboration for D2 construction
CERN-INFN ASG Collaboration meeting 18th March 2025

## Slide 2: Parts procurement status
Parts | comments | Delivered | CERN stock status
Insulated Cable | U.L of 655 m | All 24 Uls series | 1 UL
Bare Wedges : | one set for one coil is formed of 3 x 9 different types =27 pieces 2.6 m in length | All 28 units delivered | none
G1 End Spacers | one set for one coil, either A or B type, is formed of 18 pieces | All 28 sets (A&B) delivered | none
Quench Heaters | one set for one aperture is formed of two QHs | 12 sets + 3 extra delivered | 10 sets qualified
Aluminum Sleeves | On set composed of 85 pieces | All 6 sets | 75 pces

## Slide 3: Parts procurement status
Parts | comments | Delivered | CERN stock status
Magnetic steel for laminations ARMCO | 5.80 mmx750 mm x 4000mm | done | -
Austenitic sandvik Stainless Steel for collars | one set for one aperture weights 3.7 t | done | -
Poly-imide Tape | 68.6µmx9mmx6.5mm, roll of minimum length 430 m | done | -
Conductor Copper stabiliser strips | OFE Cu profile strip with drawing LHCMB_A0199 | done | 10 sets qualified
VT wires | No. 34 HV wires HH2619 -LH for a total of about 220 m | done | 75 pces
QH wires | No. 16 HV wires HH1819-LH for a total of about 105 m (about 6.5 m each wire) | done | -

## Slide 4: Parts production lead time ( based on D2 series experience)
  G11 end spacer set : outsourced, 4 - 5 months
  Alu sleeves outsourced, 4-5 months for a first batch
  Quench heaters: 6 months, series recommended
  Insulated cable UL :outsourced 3-4 months, could be internalised with preparation work, 2-3 months
  Cu wedges: procured by large batches at luvata 6-7 months.
  Collar SS steel: available in stock, lead time of collars production ( see ASG last contract)

## Slide 5
Need by Date | Qt. (units) | Eq. Name | Delivered on | Eq references
February 2021 | 4 U.L. | Insulated Cable | 2021-01-07 #3 SHIP 8584672 | HCMBRDC007-3T50892A HCMBRDC007-3T50869A HCMBRDC007-3T50894A
June 2021 | 4 U.L. | Insulated Cable | 2022-04-13 #12 SHIP 9205830 | HCMBRDC007-3T50889B HCMBRDC007-3T50875D HCMBRDC007-3T50875A HCMBRDC007-3T50881D HCMBRDC007-3T50881B HCMBRDC007-3T50857A HCMBRDC007-3T50883E HCMBRDC007-3T50881A HCMBRDC007-3T50859A HCMBRDC007-3T50881F HCMBRDC007-3T50858A HCMBRDC007-3T50881E
Sept 2021 | 4 U.L. | Insulated Cable |  | 
Dec 2021 | 4 U.L. | Insulated Cable |  | 
March 2022 | 4 U.L. | Insulated Cable |  | 
June 2022 | 4 U.L. | Insulated Cable |  |