## Slide 1: BWS LHC CONS Status and planning update
BWS LHC CONS #26 J. Emery 23.03.2025

## Slide 3: February 2025
10.02.2025 - February BWS LHC CONS meeting #25 https://indico.cern.ch/event/1514016/
18.02.2025 - 96th Impedance Working Group meeting Studies on BWSs for HL-LHC (Hikmet Bursali) https://indico.cern.ch/event/1486663/

## Slide 4
Waiting final OK
04.03.2025 (Chiara) : Transverse simulations are done and impact on the transverse impedance is low ( 0.2%). Still, I asked for an official confirmation [from the IWG]

## Slide 5: 2025 Milestones
End of April 2025: Mechanical design of the tank and scanner ready without driving system
?--May 2025-- Documentations for the installation, ECR?
Mid 2025: - Laboratory scanner ready for dynamic testing (motion, calibration, etc..) with the aim to design optimal motion and validate it with the laser calibration bench (Bld. 867) - Update detailed budget based on R&D advances
September 2025: Tank and scanner (external driving system optional if time) ready for laboratory tests (Vacuum, RF, --?Motion, --?Calibration) -equipped with inner part identical to the final system to measure RF coupling and carbon wire heating in the LHC during the run2026.
End of 2025: Ready to install wire-scanner prototype in the LHC.

## Slide 6: BWS LHC CONS – MS Project reporting (as good as what we file in it…)

## Slide 9: January 2025 recorded activities
09.01.2025 - Kick off detailed linear design SY-BI / EN-MME => status update today (Harry)
14.01.2025 - January BWS LHC CONS meeting https://indico.cern.ch/event/1503356/
21.01.2025 - Magnet system for LHC BWS - final design https://indico.cern.ch/event/1504619/ => Magnet team waiting for simulation inputs (Jonathan/Harry)
23.01.2025 - BI consolidation activities review https://indico.cern.ch/event/1478672/
28.01.2025 - Optical ruler design discussion => missing info on the markings (Jonathan)

## Slide 10: Proposed project structure (presented BI cons day 23.01.2025)
Milestones and Deliverables
WU 1 | Next activities/ milestones/deliverables | Date Expected
WU 1 | Design/production/test of a prototype in the LHC | By 09.2026
WU 1.1 | Detailed design with MME | By 05.2025
WU 1.2 | Production of the protype LHC (mechanical, electrical) | By 10.2025
WU 1.3 | Laboratory test of the prototype (vacuum, RF, motion?) | By 12.2025
WU 1.4 | LHC Beam test and analysis | By 07.2026
WU 2 | Next activities/ milestones/deliverables | Date Expected
WU 2 | Design/production/test of dynamic proto in the Laboratory | By 05.2026
WU 2.1 | Detailed design with MME | By 05.2025
WU 2.2 | Production (mechanical, electrical, c-wire technology) | By 10.2025
WU 2.3 | Laboratory test of the prototype (motion, calibration with laser) | By 05.2026
WU 3 | Next activities/ milestones/deliverables | Date Expected
WU 3 | Design/production/validation of the series for the LHC | By 2029
WU 3.1 | Final detailed design with MME (after results machine & lab tests) | By 04.2027
WU 3.2 | Production of the series (mechanical, electrical, PMT, etc…) | By 06.2028
WU 3.3 | Calibration of the instruments in the Laboratory | By 12.2028
WU 4 | Next activities/ milestones/deliverables | Date Expected
WU 4 | Installation 4 new linear scanners + validation with beam | By end 2031
WU 4.1 | Installation of the 4 scanners in the LHC | By 12.2029
WU 4.2 | Validation with beam, comparison against OP systems | By end 2031
WU 5 | Next activities/ milestones/deliverables | Date Expected
WU 5 | Installation and validation 4 spares linear scanners in LHC | By end 2032
WU 5.1 | Decommissioning Hybrid+ and installation 4 last scanners | By end 2031
WU 5.2 | Validation with beam, comparison against OP scanners | By end 2032

## Slide 11: Planning
Start 01/06/24
Finish 27/08/27
Jul '24
Oct '24
Jan '25
Apr '25
Jul '25
Oct '25
Jan '26
Apr '26
Jul '26
Oct '26
Jan '27
Apr '27
Jul '27
Test instrument manufacturing 01/04/25 - 11/07/25
✔Mechanical pre-design ready for detailed design 09/01/25
LHC instument manufacturing 09/04/25 - 18/09/25
Mechanical design 02/09/24 - 09/04/25
LHC instrument tests and validation (Laboratory) 18/09/25 - 24/12/25
LHC instrument installation in the LHC 24/12/25 - 23/01/26
Test instrument tests and validaiton (Laboratory) 11/07/25 - 03/12/25
Beam in the LHC - run2026 - prototype test with beam 23/01/26 - 26/05/26
Wire-scanner series installation in the LHC 29/07/27 - 27/08/27
Mechanical series design and production 28/07/26 - 28/07/27
Today

## Slide 12: Laboratory test instruments

## Slide 13: LHC test instrument

## Slide 14: New entries: LHC test instrument validation and series production