## Slide 1: HI-ECN3 WP4 coordination meeting #11
Jean-Louis GRENARD
16-4-2025

## Slide 2: Agenda
Target station and target area updates
Target station and vacuum vessel updates → Gemma
Target cooling station and target complex ventilation → Nikola & Francesco
FMEA process (target complex including target) → Alvaro, Gemma, Mike
BDF-SHiP Layout → Pablo
3D model organization → Béa
Handling studies update → Cristina
AOB

## Slide 3: Service cell – design study
Spec for design study allmost ready to go out
Interfaces with CE have been clearly defined
Timeline to have preliminary feedback especially for CE are including the delivery schedule
RP, fire safety, seismic requirement have been included
We will involve key stakeholder once we will start the contract

## Slide 4: Integration
We need continue our progress with service building integration
Please fill the shared table: Service building design parameters.xlsx
One major concern cooling room size:
Need space for a second compressor to be adressed:
How long will take to replace the compressor in case of failure?
RP constrains, time to prepare the area, replacement, recomissioning, area ‘’cleaning’’
→ What downtime shall we expect out this procedure

## Slide 5: Coherance between models
Revision foreseen of the Fluka and 3d models to make them coherent
Length of hadron stopper
Implementation of irradiation stations
Proximity shielding configuration
Beam instrumentation package
Proton beam window?
Model back from FLUKA will be integrated for cross checks

## Slide 6: AOB