## Weekly Action List
46
Assigned to | Detector | Action | Deadline | Solved | FSU | Need help/info from | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 (cavern closing) | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 47 | 48 | 49 | 50
ALICE
AUG tests
LPh | ELOG | [5 empty] | yes | yes | yes | yes | no | no | yes | no | no | yes | yes | no | yes (M) | yes (M) | - | - | no | no | - | no | no | late | late | late | no | no | no | no | no | no | no | no | Mattia | Mattia
LPh | Check-list | [5 empty] | yes | yes | no | yes | no | no | no | yes | no | 11: yes; 13: no; 14: yes (M); 15: yes (M); 16: -; 17: -; 18: no; 19: no; 20: -; 21: no; 22: no; 23: late
LPh | Warning check | [5 empty] | - | no | no | no | no | no | no | no | no | bar: 11 to 23
LPh | ALL | Safety valve and filters: to prearae a list of what is missing | 7 | NOT DONE | bar: 11 to 14
LPh | CPV/TRD | spikes in vaisala + contact company (problem also in other Vaisala) | 28 (2022)
LPh | TPC | To understand back-up in order to intervene in EYETS | 45-46 | w3
Patrick/Michal | FGD | Ar/H2 and CH4 cables swapped | 12 | need further investigation | bar: 12 to 23
LPh | MCH | Buy material for new humidifier module | 36 | bar: 18 to 23
LPh | MCH | build new humidifier | 50 | bar: 18 to 23
Gianluca | MID | New system for analysis rack | 9 | on-going
Gianluca/Patrick | MID | Detection head + pneumatic valves + omron flowmeter | 9 | on-going
LPh | MID | Monday-Thursday system OFF maintence and mixer zimmerli | 10 |  | 0
LPh | MID | Fix leak in He line for analysis rack | 9 | 15 | bar: 11 to 14
LPh | MID | Pump filter to change | 10 | 10
LPh | MID | Add zimmerli in mixer | 10
LPh | MID | N2 and exhaust lines for new analysis rack (contact MID to agree on short stop during TS) | 22 | Mattia | bar: 22 to 23
LPh | MID | Leak search in the line from surface to CR5 | 12 | bar: 11 to 12
LPh | MID | To install pump | 11 | 12 | bar: 11
Mattia V | MID | To check recirculation fraction | 15 | 15 | bar: 15
LPh | MID | Clean up of racks: safety | 21 | on-going | bar: 15; 21 to 23
LPh/Kacper | MID | Pump difference to be solved: new pump or repair or … | 35 | bar: 15; 21 to 23
MCA | MID | Purif can skip phase 2 after a short stop? How much short? | 40 | bar: 15; 21 to 23
LPh/Mattia | MID | increase time of phase 2 to avoid buffer LL alarm | 36 | bar: 15; 21 to 23
LPh | Pump | To check H limit for temperature (now in piquet) | 44-45 (2022?) | Gianluca
LPh | TOF | To think how to implement with Patrick flowmeter in back-up line
Mattia V | TOF | O2 and H2O analysis before and after purifier | 14 | bar: 14
LPh | TOF | Valve of purifier to change | 5 | NOT DONE, postponed TS
LPh | TOF | to check purifier status for H2O contamination | 7 | Gianluca
LPh | TOF | to buy 500 ppm calibration bottle | 7 | 11
Michal | HMP | Regeneration of code for gas loss alarm | 9 | 9
LPh | MID | Zimmerli distribution to change | 2 | 5
LPh | MID | reparation of pump (screws) | 3 | 5 | 0.5
LPh | MCH | Prepare list of material for new humidifier module | April | 25 | bar: 18 to 23
LPh | AUX | O2 cell to change | 3 | 4
Patrick | PGS | Ar dewar cables to connect |  | 13
LPh | PGS | To check with MID and TOF for stop of SF6 for 0.5+0.5 hour | 11 | bar: 11 to 23
LPh/Mattia | TOF | Khrone problem or valve problem in purif? Flow was restricted after swap. | 34
LPh | TOF | Buy two new khrone with dumper for purif | 36
LPh | TOF | high O2 concentration. Purif to be modified? | 44 | postponed to YETS
LPh | TOF | 500 ppm O2 calibration bottle in CR5 | 36 | Mattia
LPh | TPC | To find leak in back-up | 4
LPh | TPC | backup pressostat not working or not clear how it works
LPh | TPC | Installation of zimmerli for back-up | April | TS
LPh | TPC | To buy new zimmerli for back-up | 6 | 8
Gianluca | TPC | Is it possible to add alarm on current of the pump? | 5
LPh | TPC | To fix fluctuation in pressure sensor of pump -> replace sensor | 11 | to change p sensor | bar: 11 to 23
LPh/Patrick | TPC | Pump current problem to check | 11 | 12
Gianluca | TPC | To test pump repaired: waiting greenlight from Chilo | 18 | 18
Patrick | TRD | pump temperature sensor to fix | 9 | 10 | 2 E
LPh/Michal | TPC | To add pressure sensor filter in purifier | 13 | 33 | Elec | bar: 13
Mattia/Patrick | TPC | pressure sensor filter in purifier read-out: cable to be installed | 45 | 34->45 not possible during run | Elec | bar: 13
LPh | TPC | Installation of second filter in pump module | 11 | 12 | bar: 11
LPh | TPC | Change of the envelopp humidifier H2O analyser | 11 | 12 | bar: 11
LPh | TPC | Leak in one pump: to search for leak | 26
LPh | TRD | Install pump when back from manufacturer | 20 | 24 | bar: 24 to 25
LPh | TOF | To investigate O2 and H2O increase | 45-46 | Gianluca
LPh | TOF | To add volume on pump filter pressure sensor for dump oscilaltions | 4 | 6 | 1 or 2
Gianluca/Mattia | TPC | MFC1109 with profibus error. Profibus check? | 34
LPh | TPC | put "fake" MFC to check if probibus problem is from MFC or gas system | 33 | Mattia
Kacper | TPC | check MFC giving profibus errors | 36 | Kacper/Mattia
LPh | TRD | Change material purifier: CU R11 | 3 | postponed | 1
LPh | TRD | To change pump and to send to manufacturer | 4 | 9
LPh | TPC | Investigation of Air intake (Chilo) | 19 | MD-TS
LPh | TRD | To add pressure sensor for filter of pump | 10 | postponed to end of LHC?
Patrick | TRD | Heating tape to replace | 9 | 9
LPh | TRD | Safety valve purifier, volume low pressure | 13 | to open volume
LPh | TOF | To check for installation of flowmeter in back-up line | 4
LPh | TOF | Valve of purifier maybe leak: to investigate | 2 | Gianluca
LPh | TOF | Pump membrane | 32 | 33
LPh | MID | Pump membrane | 32 | 33
LPh/Mattia | HMPID | Flow problem in R61Chn5 loss -30% - check with bypass | 33 | 33
Lph/Mattia | All | Check for Nicolas Broca tests | 39
ATLAS
AUG tests | 14 November 2023
Kacper | ELOG | [5 empty] | no | no | no | yes | late | late | late | late | no |  | no | no | late | - | - | - | - | late | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes | yes |  | yes | yes | yes
Kacper | Check-list | [5 empty] | no | no | no | no | no | no | yes | no | no |  | no | no | no | - | - | - | - | no | no | no | no | late
Kacper | Warning check | [5 empty] | no | no | no | no | no | no | yes | yes | no |  | no | no | late | - | - | - | - | late | yes | yes | yes | yes
Kacper | General | To check for pipes from surface to USA15 analysis and RPC | 9
Gianluca | MDT | To understand problem of spikes in flowcells | on-going | bar: -
Kacper | MDT | Rack64ch5 Pressure sensor to be reseted during next access. | 23 | 25 | bar: yes
Gianluca | ITK | understand requirements | 22 | done | bar: -; yes
Bianca | MDT | Check for spikes in VAISALA | 13 | bar: no
Bianca | MDT | New cable for VAISALA ordered when test possible? | 38 | final report? | bar: no
Kacper | MMG | To prepare table of pressure, flow, flowcell valve for MMG team | 15 | bar: - to yes
Kacper | MMG | HF line and analyzer updated P&ID | 39 | bar: - to yes
Kacper/Gianluca | RPC | To adjust monitor gas loss alarms | 25 | on-going | bar: late to -
Kacper | RPC | To check pressure of dummy chamber | February | March
Kacper | RPC | To check pressure sensors in rack 61,62,63 | 10 | 10
Kacper | RPC | To add in series repaired IR | 14 | 15 | bar: late
Kacper | RPC | To prepare list of chamber pressure for each rack and how to change: to present in next RPC meeting | 23 | 23 | bar: late
Kacper | RPC | summary of lesk change wrt std mixture | 40 | bar: late
Kacper | RPC | Follow up of old IR | 17 | on-going | bar: late
Kacper | RPC | To check and calibrate IR for the CO2 gas mixture | 21 | 21 | bar: yes
Kacper | RPC | To increase lifetime of purifier 2 | 14 | on-going | bar: late
Kacper | RPC | To add VAISALA in series with dewmaster - mech | Feb/March | May
Kacper | RPC | To add VAISALA in series with dewmaster - elec | Feb/March | 23
Michal | MMG | Calibration of all flowcells | 5 | 5
Kacper/Fabio | MMG | Check and calibration of MFCs | 5 | 6
Kacper | RPC | Discrepancy between Vaisala (-5 C) and dewmaster (5 C) to understand | 31
Kacper | RPC | test Vaisala and dewmaster at 256 with RPC mixture | 33 | Gianluca
Kacper | RPC | Humidifier MFC blocked when was last in the past? | 32
Kacper | MMG | Input line manometer replacement/modification | 5 | 5
Kacper | MMG | O2 measurements of all channels | 6 | 7 |  | LPh
Kacper | MMG | Rack 62: to order spring for safety zimmerli | 6 | 7
Gianluca | MMG | To check when flowcells started to have problems | 5 | 5
Kacper | MMG | To check flowcell with by-pass | 4 | 4
Kacper | MMG | To replace spring for safety zimmerli | 10 | 10
Kacper | ALL | Safety valve and filters: RPC exhaust, MDT, TGC | 7 | 7
Kacper | MMG | To order O2 sensor (new MFC ok) | 11 | 22 | bar: no to late
Kacper | MMG | Installation of O2 sensor in Analysis 2 | 22 | 22 | bar: yes
Kacper | TGC | To check warning of one gas loss | 13 | TS | bar: no
Kacper | RPC | Re-present cost estimate for new distribution racks to RPC Monday meeting | 33 | 34 | bar: no to late
Kacper | RPC | how often the water MFC in humidifier has problem? Had problem in past? | 40 | summary?
Kacper | RPC | Purif lifetime summary | 34
Gianluca/Pieter | Software | Fast reading of flowcell to implement as it should be | bar: no to late
MCA | TGC | to check how to measure PH of CO2 | ?
Kacper | TGC | Change regulation valve to increase flow | 5 | 6 | 3 W +3 M
Kacper | TGC | Purifier festo module replacement and tests | 4 | 5 | ?
Kacper | TGC | Regeneration of code for gas loss alarm | 5 | 5
Kacper | TGC | Isolation mixer and control rack | 4-5 | 11 | ext company
Kacper | TGC | To regulate flow in distribution rack | 6-7 | 7
Kacper | TGC | Rack 61: to check flow fluctuation | 7 | 25
Kacper | MDT | Problematic sensors to replace? | 6-7 | 12
Kacper | MDT | Rack 69 ch 11 oscillations: to replace flowcell or motherboard | 4-5 | 3
Kacper | TGC | summary of checks done for TGC rack61 | 24 | 25
Kacper | TGC | To force regulation valve of rack 61 for few hours | 22 | 22
Kacper | TRT | To check gas system after re-start from TRT team | 3-4 | 4
Kacper/Gianluca | RPC | To define and configure gas loss alarms | 15 | on-going | bar: late to -
LPh | TRT | To check repair IR CO2 analyser. What is wrong with shipment? | 13 | almost back from company
Michal | Software | Fast reading of flowcell to fix | 7 | 7 | bar: no to late
CMS
AUG tests | 10 January 2024
Andrea | ELOG | [5 empty] | yes | yes | yes | yes | late | no | no | late | late | yes | yes | no | yes (M) | - | - | - | yes (M) | late | yes (M) | late (M) | yes | yes | yes | yes | yes | yes | yes |  | yes | yes | yes
Andrea | Check-list | [5 empty] | no | yes | no | yes | yes | no | yes | yes | no | no | no | no | yes | - | - | - | yes | no | no | - | yes
Andrea | Warning check | [5 empty] | - | yes | no | yes | no | no | no | yes | late | no | no | no | yes (M) | - | - | - | yes (M) | no | no | late (M) | no
Andrea/Patrick | CSC | To implement standard analysis module for CF4 IR | 22 | missing pump and other?
Andrea | CSC | To check flow of different racks (tried reset ELMB) | 20 | Michal | bar: yes to yes
Andrea/Mattia | CSC | To test new regulation valve | 6-7 | done
Andrea | CSC | Move gas to recovery after purif | to think | 8
Andrea | CSC | Add new line CF4 recovery HF | 4-5 | 4 | 0.5 E
Andrea | CSC | New high flow MFC CF4 to mount | 3 | 4
Michal | CSC | To check for profibus alarm in mixer | 4 | 4
Andrea | CSC | Change O2 analyser in Analysis Chain | 3 | 4
Andrea | CSC | To buy new analyser for O2 | 4 | 4
Andrea | CSC | Swap of channels in distribution with Xiaofeng | January | 5
Andrea | RPC | Replace leaking valve in purifier 2 | 3 | 3
Andrea | CSC | Increase flow of regeneration gas due to saturation of O2 | 5 | 6
Andrea | CSC | Probem in saturation of column A to understand | 9 | Mattia
Andrea | CSC | Increase flow of column A | 10 | 10
Andrea | CSC | Rack 69 and 70 to change spring of zimmerli | 7 | 9
Andrea | CSC | To adjust flow of rack following Xiaefong email | 6 | 6
Andrea | CSC | To add labels for swapped channels | 6 | 8
Andrea | CSC | Column A saturates: check Ar/H2 in rotamter and PGS pressure | 10 | 10
Andrea | RPC | Mixer HF MFC to test | 6 | 19
Andrea | RPC | To check dummy chamber pressure in all racks | 7 | Mattia
Andrea | RPC | To clean 2 racks (+2 and +1), only input | 8 | 8
Andrea | RPC | iC4H10 MFC to check | 9 | 9
Andrea | RPC | Krohne to check | 10 | 12 Patrick
Andrea | RPC | Purifier 2 column B to open and change material | 13 | 13 | bar: no
Andrea | RPC | Purifer 2 Ar/H2 to set at 300 l/h | 14 | 14 | bar: late
Andrea | RPC | To modify mixer for new HF R134a MFC and R134a recup | 16 | 16 | bar: -
Mattia | RPC | To increase lifetime of purifier 2: next week 800 m3 | 14 | 18 | bar: late
Andrea | RPC | Modify level of oil in bubblers of racks 61, 64, 86, 79, 82, 78, 73 | 13 | 13 | bar: no
Mattia | CSC | Test of fixed flow for the exhaust | 25 | bar: no
Mattia | CSC | To check delta P in the loop | 22 | 22 | bar: no
Andrea/Mattia | CSC | O2 warning high level: why? | 22 | 22 | bar: no; yes to yes
Mattia | CSC | To check O2 saturation of purifier in last years | 24 | done | bar: no; yes to yes
MCA/Mattia | CSC | any effect of more stable flow from exhaust to recuperation? | 35
Gianluca/MCA | CSC | problem in recuperation efficiency calculation (when 100% recuperated) | 35
Andrea | ID flushing | to prepare all 2D drawings | 38 |  |  | Beatrice
Michal | DT | led on analysis module to modify | 39 | EYETS |  | Andrea
Andrea | DT | Summary of still problematic channels in DT analysis rack | 45-50 | 2
Andrea | AUX | Follow-up of IR sent to company: to test | 47 | 5
Andrea | AUX | Problem in O2 and H2O calibration | 46 | 2
Andrea | AUX | Upgrade of analysis rack (new electrovalve + O2+H2O) | 3 | 3 | 1 M
Andrea | Pump | To check H limit for temperature (now in piquet) | 44-45 | 3
Andrea | AUX | To check why we don't receive alarms of O2 and H2O concentration | 48 | 3 |  | Michal
Andrea | CSC | To buy 2 MFCs: CF4 fresh and CF4 recuperated | 44-45 | 2 |  | Beatrice
Andrea | DT | Analysis leak on chain 5 | 7 | 7
Andrea | DT | Replace of flowcell rack 65 ch 44 | 5 | 5
Andrea | CSC | Installation of new PT5011 after new regulation valve | 4 | 4 | 1 W + 1E
Andrea/Mattia | DT | To check the stop of gas every 2 days and 2 hours | 6 | 10
Andrea | DT | Valve at 6 positions to calibrate + chain 1 and chain 2 | TS
Andrea/Mattia | DT | To replace multiway valve chain 4 | 7 | done
Andrea | DT | Disable detection head | 10 | 13
Mattia | CSC | To check O2 absorption | 14 | bar: late
Andrea | CSC | To decrease Ar/H2 regeneration flow | 14 | 14 | bar: late
Andrea | ID flushing | prepare summary of budget used (85% of material already received) | 33 | bar: late
Patrick/Andrea | ID flushing | prepare summary for electrical part (orders, received, budget, ...) | 34 | on-going | bar: late
MCA/LPh | CSC | Calibration IR CF4 or send to company | 24 | 33- MCA | bar: -
Andrea | CSC | To replace one electrovalve in IR CF4 | 15 | 15 | bar: -
Mattia | ID flushing | 3D drawings | 34
Andrea | ID flushing | Construction from October? | 34
Gianluca | ID flushing | functional analysis | 46 | done
Andrea | R134a | Exhaust pressure regulation in recuperation. To add pressure sensor or dupplicate signal | 34 | done
Gianluca | R134a | DIP to be published | 45
Andrea | R134a | test with high flow (400 l/h) to recuperation | 45 | on-going
Gianluca | R134a | working time pump, tot volume injected, tot volume recuperated | 36
Andrea | RPC | Prepare status of flowcells that were changed | 10 | Aleksander
Andrea | RPC | New MFC Freon 600 l/h | 15 | 15
Mattia | RPC | Summary of problematic racks during fast extraction | 13 | 13
MCA | RPC | GC analysis to check SF6 concentration | 10 | 10
Andrea | RPC | To check and regulate ECONEX valve with manual valve | 11
Mattia | RPC | To force valve of mixer HF R134a and add comments | 19 | 19 | bar: late
Patrick | RPC | New chassis for 4 gases | May | May
Patrick | RPC | install New chassis for 4 gases | May | postponed to TS
Andrea | GEM | To change mixture | 6 | 6
Andrea | GEM | O2 and H2O analyses for GEM | 10 | 14 | bar: no to -
Andrea | ID flushing | MFM to change (waiting feedback from tracker team) | 9 | 9
Andrea | R134a Recup | Dismounting existing system | 5-7 | 7 | 10 E (J) + 5 M |  |  |  |  | E | E+M
Patrick | R134a Recup | Electrical cabling of new system | 8 | 11 | 10 E (L) + x M
Andrea | R134a Recup | Installation of new recuperation system | 9-11 | on-going | 5 W + 5 M + 10 E
Andrea | PGS | Intervention on CO2 supply line to check with David | 4-5 | 5
Patrick | PGS | Ar dewar cables to connect |  | 14
Beatrice | RPC | to check with Nicolas Broca for power-cut | 7 | 7
Andrea | ALL | Safety valve and filters: list | 7 | not done
Beatrice | ALL | A/H2 to check stop of systems | 10 | 10
Andrea | R134a Recup | To add GC analysis points for recuperation system | 19 | 20 | bar: late
Andrea | General | to order safety valve 5mbar | 11 | 20 | bar: no to late
Andrea | General | Ar/H2 consumption too high: to regulate the flow | 13 | 14 | bar: no
Andrea | PGS | Check alarm/warning Air | 16 | not done | bar: -
Gianluca | RPC | Purifier 1: to check for adding wanring in case of pump not working | 24 | bar: -; yes
Gianluca | RPC | Purifier logic Regeneration vs Phase 1 to check (flusso di fase1?) | 26 | bar: -
Andrea | GEM | To check of cable with Nicolas/CMS and to check with J. Gulley/R. Perruza for matrix | 23 | bar: -
Andrea | Tracker | Modification of the GC set-up | 19 | 22 | bar: late
Andrea | RPC | Investigate igh humidity after Purif 1 and 2 | 22 | 22 (Mattia) | bar: yes
Andrea/Patrick | R134a Recup | connect heating tape exhaust | June
Andrea | RPC | how often the water MFC in humidifier has problem? Had problem in past? | 40
Andrea | RPC | IR reading 4.3 instead of 4.5% - something done but reading still not ok | 34 | Andrea/MCA?Mattia
Andrea | R134a | order fluid for -90 | 33
Andrea | R134a | order flui for -65 | 33
Andrea | R134a | Install water cooling pipe for Huber | 33 | Michele/MCA
LHCb
AUG tests
Patrick | ELOG | [5 empty] | no | no | yes | yes | no | no | late | no | no | no | no | no | no | - | - | - | - | late | no | late | late | yes | yes | yes | yes | yes | yes | yes | no | no | no | yes | yes
Patrick | Check-list | [5 empty] | no: no; no: no; yes: yes; yes: yes; no: no; no: no; late: no; no: no; no: no; no: no; no: no; no: no; no: no; -: -; -: -; -: -; -: -; late: no; no: no
Patrick | Warning check | bar: no to late
Patrick | RICH1 | Leak search (why? There were leaks?) | January | no report | - | bar: no to -; late
Patrick | SciFi | To check for 3-way valve to check humidity of dry air | 24 | bar: yes
Patrick | MWPC | To fix oscillation of exhaust | 13 | on-going
Patrick | RICH1 | Studies for moving pump in underground | 5 |  | - | bar: no to -; late
Patrick | RICH1 | To do maintenance of safety valves | 5 | 6 | bar: no to yes
Patrick | RICH1 | Filling with CO2 | 8 | 8 | bar: no to yes; late
Patrick | RICH1 | Leak search for CO2 | 9 | 9 | bar: no to yes; no to no
Patrick | RICH1 | Cleaning with C4F10 | 12 | 13 | bar: no to yes; late to no
Patrick | RICH2 | test emptying purifier | 3-4 | MCA | - | MCA | bar: no to yes
Patrick | RICH1 | Put in place small bottle for final cleaning | 13 | done | bar: no to yes
Patrick | RICH2 | test recuperation system - Patrick "test done all working fine" | 35 (2022) |  | - | bar: yes to no
Patrick | RICH2 | Install new pump and change membrane of old one | 3 | 4 | 1 | bar: no to yes
Patrick | RICH2 | IR to put in run 1 time per week: leak found on w36 | 32 | 7 (2023) | - | bar: no
Patrick | RICH2 | To change analysis time for IR | 10 | 12 | bar: no
Patrick | RICH2 | Problem in gas intake in purifier: to repair leak in valve | 2 | 4 | 0.5 | bar: no to yes
Patrick | RICH2 | To add anti-retour for pump | 48 | 5 | 0.5 | bar: no to yes
MCA | RICH2 | GC analysis of CF4 battery | 4 | 5 | - | bar: yes to yes
Kacper | RICH1 | buy material for new pump "module" | 36 |  | - | bar: no to -; late
Kacper | RICH1 | pump back from maintenance is less effective. What should we do? | 36 |  | - | bar: no to -; late
Patrick | RICH1 | ask if and when we should do a cleaning | 33 |  | - | bar: no to -; late
Patrick/Pieter | RICH1 | cleaning? | 35 | bar: no to -; late
MCA | RICH1 | air concentration for detector and big bottle | 36 | bar: no to -; late
Patrick/Pieter | RICH1 | pressure spikes | 36 | bar: no to -; late
Patrick/Pieter | RICH2 | pressure spikes | 36 | bar: no to -; late
Patrick | RICH2 | To test 3rd line of mixer | 4 |  | - | bar: yes to -; late
Patrick | RICH2 | Cleaning filter exhaust and pump | 6-7 | 6 | bar: no to no
Patrick | RICH2 | Ticket open for chanign software for a valve? | 5 | 5 | bar: yes
Patrick | UT | Prepare few slides to show to the team | 49 | 6 | - | bar: no to no
Patrick | RICH2 | CO2 calibration - done w20 all fine | 10 | 20 | bar: no to -; late
Patrick | RICH2 | Pump problem in IR to fix | 10
Patrick | RICH2 | To prepare a volume of 20 liter for GC analysis for MCA | 11 | 14 | bar: no to no
Michal | RICH2 | Fix software problem for purifier gas recuperation | 11 | bar: no to no
MCA | RICH2 | Analysis of purifier column | 19 | 20 | bar: no to no
Patrick | RICH2 | Installation of reservoir de récuperation CF4/CO2 pour le module compresseur | 23 | 23 | bar: no to no; yes
Patrick | UT | DSS test | 6-7 | 12 | - | bar: no to no
Patrick | MWPC | Maintenance pump and filter | 3 | 5 | 0.5 | bar: no to yes
Patrick/MCA | MWPC | Air intake in one pump - analysi to be re-done | 20 | 20 | bar: no to yes; no
Patrick | AUX | To check teledyne with 500 ppm O2 bottle | 10 | 22 | bar: no to -; late to late
Patrick | ALL | Safety valve and filters: list | 7 | 12 | bar: no to no
Patrick | ALL | N2 off on 20 February | 7 | 7 | bar: no
Patrick | UT | To check status of alarms | 23 | bar: yes
Patrick | Analysis | To calibrate with 500 ppm | 25 | bar: yes
Patrick/Pieter | MWPC | Investigation of new leaks in distribution | 48-49
CLOUD
LPh | CLOUD | Safety pressure regulators (one +, one -) for exhaust +- 20mbar (very low flow) | 3 | 3 | bar: no to no
LPh | CLOUD | Exhaust from bubbler/pressure regulator: 1 or more volumes of about 20L before exhaust | 3 | 3 | bar: no to no
Mattia | CLOUD | 200 C heating SI40 pipe --> Mattia checked with Loris | 3 | 3 | bar: no
LPh/Mattia | CLOUD | Buy 2 more humidifiers | 3 | 3 | bar: no to no
LPh | CLOUD | Get quotation for spare temperature control for humidifier (Julabo) (5-30°C) | 3 | 5 | bar: no to yes
LPh | CLOUD | Order Julabo/Huber | 5 | 5 | bar: no to yes
LPh | CLOUD | MFC High or low flow wet air for CLOUD??? Or dry air?? Is it working??? Raised by Eva | 4 | bar: yes
LPh/Mattia | CLOUD | MFCs--> check what missing LPh, Mattia wNOW | 4 | 5 | bar: yes
LPh | CLOUD | Check labels and give to Michal for all MFCs | 6 | bar: no
LPh | CLOUD | Chamber safety valves (over and under pressure)? check for rupture disk | 7 | bar: no
LPh | CLOUD | Replace DPT6486 or add two pressure sensor | 7 | bar: no
Mattia/Patrick | CLOUD | YV6441 (DN40) should close if backup active | 7 | bar: no
LPh | CLOUD | check if line used for TMB was used for Toluene or similar mess | 5-6 | bar: yes to no
LPh | CLOUD | Add MSA to FLOTUS | 20
LPh | CLOUD | SOF measurements (analysis rack) | 5 | bar: yes
LPh/Michal | CLOUD | WinCCOA modifications | 4 | bar: yes
Loris | CLOUD | Update P&ID | 6 | bar: no
Loris | CLOUD | Update electrical drawings | 15 | bar: -
LPh | CLOUD | Change spring in zimmerli backup to have 5-10 mbarg | 6 | bar: no
Gianluca/Roberto | CLOUD | 2nd software meeting | 32 | bar: no
Mattia/LPh | CLOUD | test of new software starting from w34 | 35 | bar: no
LINAC
Kacper | B152 | Dismount and check status of seat and PID for B152 pressure regulators | 3 | Fabio | 0.5 | Fabio | bar: no
Fabio | B152 | to change safety valve H2 line | 10
Fabio | B152 | install new MFM and PCV when will arrive | 40
Fabio/Jo | B400 | replace faulty pressure sensors | 40
NA61
Kacper | NA61 | Show to Fabio whare/how to buy membrane for NA61 pump | 33 | 33
Fabio | NA61 | buy membrane for pump2 | 34
Fabio | NA61 | Replace membrane pump2 (5000 h) | 36
NA62
Fabio |  | Safety valves?
Other projects
Patrick | NA62 | To change PLC | 4-7 | on-going | 15 E (L) + x M |  | no: software 16/02
Roberto | NA62 | Installation in NA62 experiment
Fred | ND280 | Dismounting | 3-4 |  | 5 E + xx M | bar: no to yes
LPh/Mattia | CLOUD | Consolidation and upgrade | 5-12 |  | 27.5 W + 20 M |  | yes: 2.5 W + 1.5 M; no: 3 W + 2 M; no: 5 W + 3.5 M; late: 3 W + 2 M; no: 5 W + 4 M; no: 5 W + 4 M; no: 3 W + 2 M; no: 1 W + 1 M
Patrick | CLOUD | Electrical | 9-13 |  | 15 E (J+L) | bar: no to no
Beatrice | AIDA | Electrical and installation at GIF++ | 4 | 10 | 5 E (J) + 1 M (F) | bar: yes to no
Beatrice | 256 | New He line at 256 | ?
Andrea | COMPASS | Two analysis modules (O2+H2O) | 17
Roberto | CEDAR H | Pipe connections | 5-6 | 11 | 5 W + 1 M | bar: yes to no
PIQUET
Andrea | CMS CSC | Stop of the mixer: why? (elog 1995 and 2024) | 43 | not really undrstood
Kacper | ATLAS | To check for ATLAS DSS ODH alarm | 14 | on-going | bar: no
Andrea | CMS | CF4 recovery to change pressure alarm of CF4 recuperated from 6 to 4 bar | 14 | done y Patrick | bar: no
Michal/Gianluca | ATLAS | TGC: profibus module broke but not alarm: to understand why | 16 | bar: -
Andrea | CMS | To change LL alarm of N2 dewar from 15% to 10% | 16 | 16 | bar: -
Mattia | CMS | CF4 recovery to add warning at 7 bar | 22 | done | bar: -
GENERAL
All | Analysis | To put long cycle in maximum 5 days: ALICE done | 5 | bar: yes
Patrick | Electrical | To buy new coupler for profibus | 16
Michal | WebMass | to verify how to receive an email in case of prolem and to buy new spares
Andrea | Material | To ask to build 8-10 purifier cartridge | 35 |  |  | done
LPh | Pump | To test new analysis pump | 2022-10-01 | Jo/Loris
? | Piquet | To think for a new stock for all pieces needed for the piquet
LPh | Pump | To modif oring for new analysis pump | 31
LPh/Patrick | Pump | Analysis pump speed variator now difficult to implement. Prepare summary | 36
All | Pumps | To check H limit of temperature | 45 | LPh and Andrea not done
Kacper | Pump | Set-up for pump construction | 13
Andrea | Purifier | Cu/Ni material: how to take out dust or ask to company | Sep/Oct 2022
Michal | Software | To check what happen when saturation of alarms for one system | 5 | bar: yes
Michal/Beatrice/Gianluca | Software | To check for implementation of LL threshold for gas loss or mixer to spot problems like elog #4770 | 7 | bar: no
Michal/Gianluca | Software | To check for a table in winccoa for status of detection head | 12 | on-going
Gianluca | Software | To check for implementation of warning/alarm on gas loss with relative value | 22
Gianluca/Peter | Software | To implement gas loss check in Grafana | no date
Gianluca/Patrick | Software/elec | Addition of T sensor for heating of mixer | 26
Gianluca | Software | To check the logic when purifier restart after a stop: Run->Preparation; Preparation->??? | 40

## MD TS1 2023
Assigned to | System | Activity | Need help/info from | Stop of system |  | MD1 | TS1
[5 empty] | 23 | 24 | 25 | 26
LPh | ALICE TOF | Replacement of leaking valve of purifier | Abdel/Herve | no |  | x
LPh | ALICE PGS | Stop of SF6 for 0.5 + 0.5 days | - | no |  | x
LPh | ALICE TPC | Zimmerli back-up to install | Herve | yes |  |  | x
LPh | ALICE | To fill humidifier (missing MCH) | - | yes
Michal | ALICE PGS | Regeneration of code | - |  |  |  | Postponed
LPh | ALICE TRD | Swap of pump | Herve | no |  |  | x
Kacper | ATLAS TGC | To check warning of one gas loss | - | one distribution rack |  |  | x
Kacper | ATLAS TGC | Rack 61: to change motherboard/ELMB | - | no |  |  | x
Patrick/Kacper | ATLAS MM | Electrical connection for O2 analysis | Jonathan | no? |  |  | x (20 June)
Andrea/Patrick | CMS RPC | Modification Mixer for 4th line:hard and elec | Abdel/Herve/Jonathan | yes |  |  | x
Patrick | CMS RPC | New chassis for 4th line mixer | Jonathan | no |  |  | Postponed
Michal | CMS RPC | Upgrade of software | - | yes |  |  | Postponed
Michal | CMS RPC | Replacemeent motherboard rack 62 and 66 |  | no |  |  | x
Patrick | CMS CSC | Installation of new chassis of analysis | Jonathan | no |  | x | 2023-06-19
Michal | CMS CSC | Software upgrade for new IR analysis | - | yes |  |  | 2023-06-19
Michal | CMS CSC | Replacement of motherboard of rack ?? -> Andrea to say |  | no |  |  | x
Andrea | CMS CSC | To install new HF MFC CF4 recup |  |  |  |  | 2023-06-19
Mattia/Andrea | CMS CSC | Test of fixed flow for the exhaust |  | no |  | x
Andrea/Patrick | CMS GEM | To move GEM in Nicolas's matrix | - | yes
Andrea/Mattia | CMS DT | 2 multiway valve analysis | Herve | no |  |  | x

## EYETS 23-24
Experiment | Detector | Assigned to | Action | Stop of System | FSU | days |  | 48 | 49 | 50 | 51 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ALICE | MCH | LPh | Humidifier to build | no | yes | ? | bar: 48; 50
ALICE | MCH | LPh | Humidifier to install | yes | yes | ? |  | 51: x (if system off); 2: x; 3: x; 4: x
ALICE | MCH | Gianluca | Regeneration of code | yes | no | done, waiting humidifier for testing |  | 50: x (5 Dec)
ALICE | TPC | LPh | back-up in error to fix: to test | yes | no | - | bar: 5 to 6
ALICE | TPC | Patrick/Gianluca | Purifier filter pressure sensor to be connected -> AUX | yes | yes | ?
ALICE | TPC | LPh | Fix fluctuation in pump pressure sensor | no | no
ALICE | TPC | LPh | Find leak on pump and in case send to manufacturer | no | no | bar: 48; 51
ALICE | TRD | Patrick | pump temperature sensor to fix | no | yes | 2 E | bar: 3 to 6
ALICE | TRD | LPh | Install pressure sensor on pump filter (Check with Chilo) | yes | ? | ?
ALICE | TOF | LPh/Mattia | Investigation of air intake: pump leak test | yes | no | - | bar: 3 to 6
ALICE | TOF | LPh | To check for installation of flowmeter in back-up line | yes | no | -
ALICE | TOF | LPh | Change purif material for O2 trapping | no | yes | 2 M | on-going | bar: 2
ALICE | TOF | LPh | Change purif regeneration (Ar/H2) | no | yes | 2 W | bar: 2
ALICE | TOF | Mattia | Detection head to be installed (Ar/H2) for Purif | no | no | bar: 49 to 50
ALICE | TOF | LPh | Khrone flow sensors to be replaced | no | yes | ? | bar: 6
ALICE | MID | Mattia | Pump to repair to send to manufacturer | no | no | bar: 48
ALICE | MID | LPh | Leak search in the exhaust | yes | no
ALICE | MID | LPh | Replace faulty sensor | yes | no | Mattia replaced, leak test? | bar: 50 to 51; 3 to 4
ALICE | PGS | LPh/Patrick | Ar/H2 and CH4 swap in transmission, cabling or pneumatic lines to change to check with David Jaillet | no | no | march
ALICE | MCH | LPh | leak on the valve YV6171 | no | no | bar: 5 to 6
ALICE | MCH | Pieter/Mattia | Flowcell calibration | no | no | bar: 5
ALICE | TOF | MCA/LPh | GC analysis for N2 concentration? | no | no
ALICE | TOF,TRD | LPh | Festo pneumatic valve leaking replacement | no | no
ALICE | TOF | LPh | High O2 level (alarm piquet) and high pressure in exhaust filter | no | no
ATLAS | RPC | Kacper | Test of double flow with the 2 pipes going to USA | no | no | - | bar: 48 to 7
ATLAS | RPC | Kacper/Patrick | Purifier 3 column B heating problem: circuit breaker? | no | maybe
ATLAS | RPC | Kacper | Swap of flowmeters between purif 1 and 3 | no | no | bar: 3
ATLAS | MDT | Kacper | Problematic sensors to replace: at least 2 to replace | no | no | -
ATLAS | MMG | Gianluca | Software for O2 analysers | yes | no | - | done
ATLAS | MMG | Kacper/Pieter | High flow tests: flowcell replacement | yes | no | results? | on-going | bar: 48; 4 to 5
ATLAS | MMG | Kacper | Addition of safety valves at ~200 mbar | yes | yes | 0.5 W | bar: 4
ATLAS | TRT | Kacper | Installation of IR | no | no | bar: 48 to 7
ATLAS | TRT | Kacper | Replacement of 3 Krohne | yes | yes | 1 W | bar: 3 to 4; 7
ATLAS | TRT | Gianluca | Software testing for TRT and TRO | yes | no | bar: 49 to 50
ATLAS | TGC | Kacper | Rack 65 Ch1 output flow verification | no | no | done,w4
ATLAS | TFC | Kacper | Confirmation of reparation and new offer for pump | no | no | urgent | bar: 3 to 4
ATLAS | RPC | Kacper/Pieter | Fine tuning PID of humidifer | no | no
CMS | DT | Andrea | DT analysis chain 1: multi-way 4 to change | no | yes | 1 M | w48 | bar: 48
CMS | RPC | Andrea | Mixer HF MFC to test | yes | no | - | bar: 48 to 7
CMS | RPC | Pieter/Andrea | Problem on ELMB or flowcell to investigate | no | no | bar: 5
CMS | FGR | Andrea | Install second compressor | no | yes | 2 M 2 W 2E | bar: 4 to 5
CMS | CSC | Andrea/Mattia | system OFF, backup Ar/CO2 ON + regulate back-up | yes | no |  | on-going | 48: x (30 Nov)
CMS | CSC | MCA | Calibration MFC? | yes | yes | Fabio | NO
CMS | CSC | Andrea | clean filters exhaust, pump and purif | yes | no | 1 M | bar: 49 to 50
CMS | CSC | Andrea | test non-return valves purifiers | yes | no | 1 M | bar: 50
CMS | CSC | Andrea | check zimmerli when system back on | no | no
CMS | GEM | Andrea | change filter GE1/1 and GE2/1 + move? If yes, leak test! | yes | yes | 1 M
CMS | GEM | Andrea/Patrick | To move GEM in N. Broca matrix | yes | no |  | ? | 2: x (10 Jan)
CMS | RPC | Mattia | Purifier 1 MFC to check | no | no | bar: 4
CMS | RPC | Andrea | 100% R134a and purif OFF when test high flow finished | no | no
CMS | RPC | MCA | calibration MFC LF SF6 | no | yes | 1 Fabio | w48 | bar: 48; 51
CMS | RPC | Patrick | cabling new MFC and electrovalve for 4th line | yes | yes | 2 E |  | 2: x (10 Jan)
CMS | RPC | Patrick | Addition of temperature sensor for mixer | yes | yes | 0.5 E |  | 2: x (10 Jan)
CMS | RPC | Andrea | mixer piping to connect to recuperation | yes | yes | 1 W |  | 2: x (10 Jan)
CMS | RPC | Andrea | filter to be cleaned in exhaust, pump | yes | yes | 2 M |  | 2: x (10 Jan)
CMS | RPC | Andrea | change material purif2 column1 | no | yes | 2 M | bar: 49
CMS | RPC | Andrea | test non-return valves purifiers | no | yes | 1 M | bar: 49
CMS | RPC | Andrea | calibration MFC mixer HF R134a | yes | yes | Fabio | w48 | bar: 49
CMS | FGR | Patrick | SF6 recuperation elec | no | yes | E + M | bar: 3 to 5
CMS | FGR | Andrea | SF6 recuperation | yes | yes | 2 M | bar: 49 to 50
CMS | Flushing | Andrea | Add VEBEO connectors | no | yes | 1 M | bar: 3 to 5
CMS | Flushing | Andrea | Leak test racks and labels to add | no | no | bar: 4 to 5
CMS | Flushing | Patrick | Electrical work rack flushing | no | yes | bar: 5 to 7
CMS | Flushing | Andrea | Installation of distribution and SXA5 flushing | no | yes | 1 W | bar: 48 to 8
CMS | Flushing | Andrea | Other racks | no | yes | after EYETS | bar: 48 to 7
CMS | DT | Andrea/Mattia | Regulation valve rack 62 to check | no | no | bar: 5
CMS | RPC | Mattia | IR problem investigation | no | no | bar: 4 to 5
CMS | RPC | Patrick | PT100 for mixer to install | no | yes | 1 E | bar: 48 to 7
LHCb | RICH2 | Patrick | Injection from 3rd line mixer | no | no | - | MCA analysis | bar: 48
LHCb | RICH2 | Pieter | Check IR threshold for CO2 | no | no | bar: 48
LHCb | RICH2 | Pieter/Gianluca | Bug in code for mixer CF4 recup | no | no | bar: 2
LHCb | RICH2 | Patrick | Error in analysis IR: profibus | no | no | bar: 2
LHCb | RICH2 | MCA/Pieter | Check IR CO2 calibration | no | no |  | w48 | bar: 4
LHCb | MWPC | Patrick/Pieter | Search for leak in distribution | yes | no |  | on-going | bar: 48 to 51
LHCb | SciFi | Patrick | To add line for humidity measurement of dry Air | no | yes | 1 E | bar: 48 to 49; 4 to 6
LHCb | RICH1 | Patrick | Several modifications to discuss + software | yes | yes | ? | discussion w4
LHCb | RICH1 | Patrick | Isolation pipes test | no | yes | 10 E | bar: 3 to 4
LHCb | RICH1 | Kacper | Pump to send to company | no | no | bar: 48 to 49
LHCb | RICH1 | Patrick | Piping for new recuperation system | yes | yes | 10 W + 10 E | new recup system | bar: 50 to 51; 8 to 9
LHCb | RICH1 | Patrick/Pieter | To check pipes for pump in balcony | no | no | bar: 48 to 7
LHCb | RICH2 | Pieter/MCA | Test of purifier 2 CO2 intake | no | no |  | on-going | bar: 48 to 7
LHCb | MWPC | Patrick | Monitoring of O2 intake | no | no
NA62 | Straw | Fred | Festo block (electrovalves) to replace | yes | yes | 1 E + 2 M | bar: 3
NA62 | CEDAR | Patrick | Profibus | yes | yes | 1 E | bar: 3; 5
General | ALL | ALL | Check for safety valves to calibrate
General | ALL | ALL | Check leak in analysis rack
General | ALL | ALL | Clean filters purifiers, exhaust and pump
General | ALL | ALL | Check bubbler oil level
General | ALL | Patrick | Check leak current in purifier