## Slide 1: Sparks! Coordination Meeting 5 May 2025

## Slide 2: Agenda
Overview of the Master Event Brief
Logistics and technical requirements
Audio-Visual
Design & Identity
Communication (incl Social Media)
Donors

## Slide 3: Logistics and Technical requirements
ACTIONS: - SG to go forward with ordering backdrop - SG to share dimensions of the backdrop for the Design team to produce a generic CERN theme - SG to order projection lights and share dimensions of projection with Design team (buy vs rent? / Projection vs Mapping?) - SG to get quotes and order carpet for the stage
- SG to confirm cocktail
DANTE to provide - Updated indico description - Provide overall schedule of the day - Confirm meal for technicians
OTHER
Make-up
Confirm rehearsal times and availability

## Slide 4: Audio-Visual
ACTION: - AUDIO VISUAL to start producing trailer and TPG video - AUDIO VISUAL to confirm live stream platforms and vertical live formats
DANTE to provide - Clarity on the video capsules and key messages for production - First version of Script
OTHER
Confirm photography
Confirm freelancers

## Slide 5: Design & Identity
ACTION - DESIGN to produce a generic CERN backdrop, once the dimensions are sent by SG team - DESIGN is to produce a graphical chart of the event
DANTE to provide - All types of formats for the event - Script for animation to Daniel - More information on the “Cahier des charges” for the slides of the speakers
OTHER
DANTE to confirm all titles
Confirm feasibility for map
Material for the website?

## Slide 6: Communication
ACTION - SoMe to provide communication plan and more details on what is expected for the weekly content - Daniela to check regarding content creators
DANTE to provide - Liaison with Press office - Investigate possibility of chat moderation - More information on the use of the website
OTHER points:
Contacts of communication teams for partner organisations
Communication campaign with Le Temps

## Slide 7: Donors
ACTION - Provide a first list of guests the Foundation wishes to invite (if names are not available, at least a number of people) - Check logo requirements
DANTE to provide - More detailed agenda of the day - Draft posters with logos