## Slide 1: SM18 vertical test bench planning
2025.05.13

## Slide 2
As I was preparing these slides yesterday (Monday) I found that today is not an unlucky day here, only in Greece, Spain and Latin America
Other similar unlucky days:
Friday 13 – popular thanks to the movie
Friday 17 in Italy – I didn’t know about this one either
https://simple.wikipedia.org/wiki/Tuesday_the_13th
https://en.wikipedia.org/wiki/Friday_the_13th#Tuesday_the_13th_in_Hispanic_and_Greek_culture

## Slide 3: Back to the monthly discussion

## Slide 4: Update since last meeting
Cluster D | HFM | Siegtal | Long | Diode
MCBXFB07 – finished | MQXFS8b – finished | SMC108-eCLIQ – finished | Sushi – finished | DR_FFC01_06 – finished
MCBRD06 – finished | MQXFS4f – ongoing CD2 | SMC109-eCLIQ – finished | MSCB 399, 386 – finished | IT-diode 1 – finished
MCBRD05 – finished |  | HO session 5 – finished | MSCB 396, 385 – finished | IT-diode 2 – finished
MCBXFA02 – finished |  | PSI SubSMCC 2 – prep | MQ #1 – prep | IT-diode 3 – prep CD2
MCBRD07 – ongoing CD2 |  |  |  | 
 | Fusillo | HO session 6 | MQ x2 (3 next year) | IT-diode 4
MCBRD08 | RMM1e | PSI SMACC | LMF Splices x2 | IT-diode 5
MCBXFB08 | RMM2 | CEA R2D2 |  | DR-FFC01-xx ?
MCBRD11 | HD3 | CHIC – probably 2026 |  | HTS three coils (x2?)
MCBRD09 | MBHSP107 with Beam Scr | SMC 106 |  | CEA HTS racetrack
MCBXFB09 | Ciemat ISAAC | SMC 108 |  | HTS common coil
MCBRD10 | MQXFS4g… | SMC 110 |  | 
 | MQXFS9 | FalconD LMK1 |  | 
In red: new since last meeting
In gray: foreseen later this year

## Slide 5: Planning last few weeks before summer Focus on cryogenics
 | Week 20 | Week 21 | Week 22* | Week 23 | Week 24* | Week 25 | Week 26 | Week 27
Long | MQ |  | MQ |  |  |  | LMF splice | LMF splice
HFM | MQXFS4f | Fusillo | Fusillo |  |  |  |  | 
CTV | Diode IT | Diode IT |  | HTS 3 coils |  | HTS 3 coils |  | 
Siegtal | PSI SubSMCC2 |  |  | PSI SubSMCC2 |  | HO ses6 |  | HO ses6
Cluster D | MCBRD07 |  |  |  | MCBXFB08 | MCBXFB08 |  | 
Low cryogenic availability
Works in the
Cluster G structure
Shutdown starts
Fusillo test may be delayed one week depending on cryogenic capacity
All tests could be delayed depending also on HB tests (Q2, D2, D1)
1.9 K capacity will be very limited
*: Short weeks (Pentecost, Ascension)
June 1
July 1
Preparation
Stand-by
Test

## Slide 6: Planning last few weeks before summer Focus on 20 kA PC
 | Week 20 | Week 21 | Week 22* | Week 23 | Week 24* | Week 25 | Week 26 | Week 27
Long | MQ |  | MQ |  |  |  | LMF splice | LMF splice
HFM | MQXFS4f |  |  |  |  |  |  | 
CTV | Diode IT | Diode IT |  | HTS 3 coils |  | HTS 3 coils |  | 
Siegtal | PSI SubSMCC2 |  |  | PSI SubSMCC2 |  |  |  | 
Cluster D |  |  |  |  |  |  |  | 
Low cryogenic availability
Works in the
Cluster G structure
20 kA PC is practically fully booked until summer
Small delays or extra tests in one magnet will impact all the following ones
*: Short weeks (Pentecost, Ascension)
Shutdown starts
June 1
July 1
Preparation
Stand-by
Test

## Slide 7: Magnets from SMT
Fusillo: in SM18, to be installed after MQXFS4f.
  Test plan ready (EDMS 3292867). Note: no 20 kA PC conflict with other tests.
The following magnets might arrive before summer, but I don’t think we can test them until September:
RMM1e with fishbone and prototype flat QA – June
SMC 108 with eCLIQ – End of May
MQXFS4g with different pre-load – June
Magnets for after summer this year:
RMM2 with second version flat QA – October
MQXFS9 with RRP coils + ESC
SMC 106 and 110

## Slide 8: Magnets from HSD
DR_FFC01
  DR_FFC01_08: test cancelled due to problems when integrating into the mechanical structure
  DR_FFC01_xx: test delayed after the three coils in a frame
Three coils in a frame (SeR_FFC01_01? *): next week
  With Carlo’s MM, NbTi leads
Second Three coils in a frame (SeR_FFC01_02? *): after the next DR_FFC01
HTS leads after summer – can be done earlier (TBD with Christian)
Common Coil configuration (3 and 3): around September
  20 mm apertures
CPCL: lower priority, probably after September
*: DR_FFC is Double Racetrack, Faraday Factory Conductor, so
SeR_FFC could be Sextuple Racetrack, Faraday Factory Conductor

## Slide 9: Magnets from LMF / WP3
MCBRD07 (virgin): to be finished this week
MCBXFB08: June 2-6 – top priority
  It should arrive before June 9 to have a good chance of test before summer
Available right after summer:
MCBXFA3, MCBXFB09 (September)
MCBRD08, MCBRD11, MCBRD09 (September)
MCBRD10: November
Two boards with splices: ?
EESD2 (phase 3): end of the year
MgB2 bending test
It would be best for us to test several of the same time in a sequence.
From this planning we could do the 2 MCBXF (+1 before summer) and then 4 MCBRDs

## Slide 10: Magnets from collaborations
PSI – SubSMCC2 (with ESC) – in SM18, test plan ready (EDMS 3295170)
PSI – SMACC: ?
PSI – HTS racetracks: ?
CIEMAT – ISAAC: December
CIEMAT – Poseidon ?
LBNL – HD3: arrival June 2025
  It could be interesting to have a multipole QA for this
CEA – HTS EuCARD2 ?
CEA – R2D2: arrival October 2025
CEA – MI long racetrack HTS: ?
I took the delivery date of magnets without a “?” from the weekly report week 19.

## Slide 11: Other CERN tests
FCC hh HTS beam screen
  Sergio Calatroni does not have news as of 12.05
  Probably in SP107
  Probably September
  Magnetic measurements device arrived and in calibration/assembly
    Rotating coil for dipoles, 18 mm diameter, <1 m length
    Also used for PSI SubSMCC and HSD’s common coil