## Slide 1: Optimizing Magnet Production Plan: Insights from Simulations
Milosz Artur Zielinski 22/05/2025
Many thanks to the members of the Normal Conducting Magnets section, Damien Lafarge (CERN), Benedikt Müller (Fraunhofer IML), and Felix Blum (Simplan)
22/05/2025 FCC Week 2025
Miłosz Artur Zieliński

## Slide 2: Agenda
Equipment to be produced
Details of the production process
Simulation tool used
Production Model in Plant Simulation
Estimating number of processing stations and buffer size
Study outcomes
Next steps and further developments

## Slide 3
Equipment to be produced
Courtesy of Emeric Bernard

## Slide 4
Production process details

## Slide 5
Production process details
Courtesy of Sarah Fleury

## Slide 6
Simulation tool
Notes: Optimizes production processes and logistics
Plans material movement, workforce, and equipment
Identifies bottlenecks and evaluates scenarios
3D visualization for facility layouts and component transport
Integrates real-time data for adjustments

## Slide 7
Production Model in Plant Simulation

## Slide 8
Production duration (baseline scenario): 1441 days

## Slide 9
Determining number of processing stations
Chart: Booster dipole - single production line
| SP010 | SP020 | SP030 | SP040 | SP050 | SP010 | SP020 | SP030 | SP010 | SP020 | SP030 | SP040 | SP050 | SP060 | SP070 | Yoke | Busbar | Dipole Assembly
Processing time | 30 | 1500 | 1000 | 1000 | 1000 | 40 | 180 | 60 | 480 | 30 | 60 | 30 | 30 | 10 | 40
Takt time | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845
Chart: Booster dipole - parallelized stations
| SP010 | SP020 | SP030 | SP040 | SP050 | SP010 | SP020 | SP030 | SP010 | SP020 | SP030 | SP040 | SP050 | SP060 | SP070 | Yoke | Busbar | Dipole Assembly
Processing time | 30 | 300 | 333.3333 | 333.3333 | 333.3333 | 40 | 180 | 60 | 240 | 30 | 60 | 30 | 30 | 10 | 40
Takt time | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845 | 335.9845
Parralel processing stations | 1 | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1

## Slide 10
Utilization of processing stations

## Slide 11
Small series
1st install. phase
Pre-series
Mass production
First Article Inspections
3rd install. phase
2nd install. phase
4th install. phase

## Slide 12
Outcomes
Validated simulation model for magnet production and logistics
Tool at CERN to handle complex operations
First production strategy defined
Storage requirement analysis: estimated cost ~10 million CHF
Demonstrated impact of installation schedule on storage cost

## Slide 13
Further works
Integrate production and installation models
Update transport durations based on contracting strategy
Include contingency parameters and perform risk analysis
Integration of auxiliary magnet equipment in the production process
Model sourcing lead times and supplier availability for raw materials
Add facility usage costs to existing cost model
Identify optimal balance between production throughput and storage costs

## Slide 14: Thank you for your attention
Optimizing Magnet Production Plan: Insights from Simulations Milosz Artur Zielinski 22/05/2025
Many thanks to the members of the Normal Conducting Magnets section, Damien Lafarge (CERN), Benedikt Müller (Fraunhofer IML), and Felix Blum (Simplan)
22/05/2025 FCC Week 2025
Miłosz Artur Zieliński

## Slide 15
Further topics
Requiring Just-in-time delivery
Balancing contracts between countries
Division of contracts to reduce risks and encourage continuous improvement