## Slide 1: MD15146: Rematched IR7 optics for improved cleaning and performance – high intensity part
B. Lindström, L. Bertolozzi, R. Bruce, X. Buffat, R. de Maria, D. Mirarchi, N. Mounet, S. Redaelli
Acknowledgements: OP, LNO, CEI, RF, BI, MPE, STI
28th May 2025 – rMPP meeting on MD block 1

## Slide 2: Introduction
HL-LHC beam intensity and brightness:
  Beam losses in IR7 DS could cause quenches
  Impedance can cause instabilities
Very successful MD last year:
  Up to 61 % reduction of DS losses
  Up to 33 % reduction of impedance
Optics require combined ramp and desqueeze
  Must test with high-intensity beams to ensure no issues with beam lifetime or loss spikes in IR7
contact person: B. Lindström
nominal meas.
HL MD meas.
Ideally MD1 due to contract of participant
New ramp compared to last year compatible with 2025 physics cycle

## Slide 3: 20h for 7 fills
MD block 1:
  1 (4h): 3 pilots, optics measurement throughout ramp and at FT -- coarse collimator settings for optics measurements, stay at FT
  2 (2h): 3 pilots to validate corrections (if needed)
  3 (3h): Collimator alignment check and loss maps -- two nominal (1.3e11, 0.8e11) and ~8 pilots per beam -- impedance measurement -- Betatron (H/V), off-momentum (dp+/dp-) and ASD
  Standard collimator setup interlock masks
Preparations for next MD block:
  Orbit feed-forward correction
  Cross-check BLM thresholds in IR7
MD block 2:
  4 (2h): repetition of fill 3, nominal collimator ramp functions, no collimator alignment
  5 (2h): 12 nominal bunches, nominal collimator ramp functions, dump directly at FT
  6 (2h): 75 nominal bunches, nominal collimator ramp functions, dump directly at FT
  MP checklist before proceeding (next slide)
  7 (2h): 400 nominal bunches, nominal collimator ramp functions, dump directly at FT
  In fills with trains, add a few pilots for lossmaps

## Slide 4: MP checklist
First check after loss maps before proceeding with > 3e11 protons
Second check after 75b, before proceeding with 400b
  Steady state losses
  Losses during ramp
  Collimator ramp functions
  Beam orbit
  Heating of collimators