## Slide 1
Georgi GEORGIEV, Javier PARA EN-EL
23/05/2025
Indico
HL-LHC DE-CABLING PREPARATION
Status and Next Steps

## Slide 2
Timeline
We are here
HL-LHC: 5,3k cables , 594,2 km
Forward Physics: 1043 cables, 188 km
Total: 6343 cables, 782.2 km
Final Cable lists for LS3
Beginning of the de-cabling
Office verification of
Equipment to be locked out
by the Groups
On-site confirmation of
Equipment to be locked out
by the Groups
EDMS approval of
Equipment to be locked out by the Groups
1778 equipment identified
During the survey
Progressive Equipment Lockout by the Groups
Progressive Disconnection and labeling by the Groups
See slide 3, 4 and 5
DECs to be updated on EDMS:
SY-BI P1 EDMS 2806307 and P5 EDMS 2909129
EN-EL EPM P5 EDMS 2806334
Action EN-EL, HL-LHC. To be signed by SY-BI and EN-EL
Completed
Works to be carried out by the Groups ahead
See slide 6 and 7
See slide 3, 4 and 5

## Slide 3
LOCKOUT PROCEDURE FOR HL-LHC DE-CABLING 1/3
"Standard" LHC Machine lockout + additional specific lockouts for de-cabling
Inventory of 1778 equipment for both points by EN-EL
EDMS 3302715

## Slide 4
LOCKOUT PROCEDURE FOR HL-LHC DE-CABLING 2/3
Office verification of Equipment to be locked out
by the Groups to complete before YETS25-26:
Validation of the equipment ownership
Validation of the power supply
Identification of the Equipment which must remain powered during de-cabling
On-site confirmation of Equipment to be locked out
by the Groups to complete during YETS25-26:
Validation of the information from the ‘Office verification’
Clear doubts
Formal EDMS approval of the Equipment list to be locked out by the Groups - April 2026.
EDMS 3302715

## Slide 5
LOCKOUT PROCEDURE FOR HL-LHC DE-CABLING 3/3
Exchange of lockout certificates workflow
Certificates returned to the Lockout responsible
Certificates to be delivered from the Lockout responsible to CTP/ EL Contractor
Certificates to be delivered from the EL Lockout responsible to CTP/ EL Contractor
Higher level than Groups equipment
When possible
Certificates returned to the EL Lockout responsible
As 1778 equipment to be locked out
physically impossible in a single day
To be planned progressively before the start of de-cabling
Synergy with cables disconnection and tagging (See slide 6)
Not required
EDMS 3302714

## Slide 6
Labelling and disconnection procedure HL-LHC 1/2
IMPORTANT!!!
Groups are responsible for their own safety:
  Planning
  Lockout for disconnection and tagging
  Electrical accreditation of the collaborators
  IMPACT
  VIC
  WDP
  False floor
EDMS 3302714

## Slide 7
Labelling and disconnection procedure HL-LHC 2/2
  Cables must be disconnected in the both ends
  Cables must be marked with PURPLE tape in both ends
  Power cables must be secured (MALTCC)
  The cable list must be updated and communicated regularly to EN-EL (Javier PARRA) for final approval before the start of the de-cabling
  To be done progressively by the groups before the start of de-cabling
  The PURPLE tape marking is in addition to the RED and BLUE tagging done during EYETS23-24.
  If you find an error on this tagging, please correct it and communicate the change to EN-EL (Javier PARRA)
!
EDMS 3302714

## Slide 8
take-home message
HL-LHC need the strong commitment of the lock-out responsible of the Groups for:
  Office verification of Equipment to be locked out
  On-site confirmation of Equipment to be locked out
  Planning for Equipment lockout and Disconnection and labeling
  EDMS approval of Equipment to be locked out
  The Lockout, Disconnection and labeling must be completed before the beginning of the de-cabling

## Slide 9
Thank you for your attention!