## Slide 1
New Readout Electronics for Experimental Areas
Mark McLean 25th June 2025

## Slide 2: Introduction
New readout boards are foreseen for almost all the Beam Instrumentation of the North and East Experimental Areas
XSCI, XCED, FISC, CEDAR => 120 x VME, 130 x RTM1
XDWC => 10 x VME, 10 x RTM2
MWPC => ? x VFC-HD, ? x MWPC RTM

## Slide 3: Overview
Testing of the first batch of six prototypes for the VME and RTM1 boards is largely complete and has been positive.
The V1 design has been updated following this testing and is now the layout team in the Electronics Design Office.
Purchasing is in progress for 20 V2 prototypes, and 130 of the volume production, slightly more than planned but within the budget envelope.

## Slide 4: Component purchasing
Currently the purchase of parts for 160 each of the VME and RTM1 board is ongoing
DR11026447, DO-34764/SY. These are the EVM lines:
It looks like there will be savings here, compensating for the HV PSUs and the inclusion in the project of readout for XDWC and MWPC

## Slide 5: High voltage PSUs
Samples have been tested and found to have satisfactory performance
The purchasing of around 66 units with a total cost of around CHF 178k is proceeding under DR11085516.
This is an overcost of CHF 20k versus EVM, but I think the money can be found from within this Workunit

## Slide 6: Questions
Do you need money? – No
Do you save money? – Not much and what I save in one place I need in another
Missing manpower? – No
Lateness, underspend - Catching up on spending
LS3 readiness – All will be ready for LS3 except MWPC readout which will be developed during LS3
Cabling/decabling/racks – None needed