## Slide 1: Beam Instrumentation for PUMA@ISOLDE
M. Martin Nieto , P. Martins, J. Tassan-Viol
W. Andreazza, S. Bart Pedersen
C. Pasquino, F. Roncarolo
Puma@Isolde – 3 July 2025

## Slide 2: Status and Plans of DBs
Mechanical Design, Integration and Procurement

## Slide 3: BI Diagnostic boxes
DB1
  Isolde type:
    Faraday Cup
    Scanner
DB2-4
  HIE-ISO type:
    Faraday Cup
    Scanner
    MagneToF
    Slit/collimator
  Collector plates

## Slide 4: Manufacturing
Parts are being machined, components have been ordered.
  Delivery of machined parts for end of September.
  Procurement launched: only one order on hold due to single tender – closely followed.
  Assembly, calibration… will take ~1.5 months.
Calibration setup will be reused from HIE-ISO DBs.
  Two calibration stands: manual and motorised.
  Have spare parts to build a mock-up of the DBs.
  Tolerances have been discussed.

## Slide 5: Electronics, Acquisition and Software

## Slide 6: Rack and electronics
Rack is already installed: BY06=170.
Cabling will be pulled after the HV cage and cable trays are installed (EN-EL planning).
Electronics for FC, scanners and slits are in production or in stock.
TDC for MagneToFs:
  TDCs received.
  FEC installed.
  FESA class to be adapted from LHC BSRL.
New rack
installed

## Slide 7: Hardware
Development of MagneToF electronics ongoing.
  Prototype for constant-fraction discriminator looks OK.
  Custom-built switch design ongoing.
    fA@DC and GHz are usually exclusive.
Integration with existing PAM infrastructure.
  FPGA in PAM to be modified for this application.
  Extra circuitry.
  PLC/SILECS/FESA code to be adapted.

## Slide 8: Software / FESA
Requirements discussed with users. Feasible.
Experience in using the TDC with the LHC BSRL.
FESA class will be adapted from the BSRL.
Raw data readout foreseen for some cases.

## Slide 9: Outlook

## Slide 10: Outlook
DBs in production queue:
  Delivery of components scheduled for end of September.
  Time needed for assembly, metrology, calibration, cleaning, vacuum acceptance, installation.
  Delivery for mid-November absolute best case. No change of delivery date.
  No change for collector plates.
Calibration:
  Calibration bench being readapted for the DBs.
Electronics and software:
  FESA class to be implemented considering input from users.
  MagneToF adaptation electronics being developed. Prototypes OK.
Budget:
  Mechanical: 350k (estimate) + 75k (collector plates).
    Components: 55k; machining: 107k.
    Some purchases and services to be added.
  Electronics: 65k (MT + electronics) + 20k (PAMs) + 18k (TDCs).