## Slide 1: TS1 + YETS25-26 info from Experiments
Bastien Rae

## Slide 2: TS1 + O ions run
Cooldown start on the 23rd of June (time to be confirm by RP)
  No beam for East and North
24th of June : start of the TS for 30hrs
25th of June : Restart of Machines
  East beam should be back around lunch time
26th of June : DSO test follow by ions beam tuning for North Area
28th of June : Start of Ions physics

## Slide 3: YETS 25-26 works announced by experiments
For Information :
YETS 25-26 draft dates :
End of Physic/ YETS start : 08.12.2025
Start of Physics : 13.03.2026

## Slide 4: Services requirements for 2026
Amber :
  H2, N2, He, Ar, CO2 and CF4 gas supplied (beginning of march)  TBC
  Cooling water available as early as possible (best in February)  Ok
NA62 :
  Cooling water for racks  13.02.26  Ok

## Slide 5
MD and Stop Planning during RUN BE-EA website