## Slide 1: East Area – Master Schedule and preliminary analysis
  Key dates
    24th November 2025 stop T09-T10 beam for AMS beam line preparation ( beam to T10 from 17h30 to 8h30)
    1st December 2025 test AMS configuration with Beam
    8th December 2025 – start of the YETS2025-2026
    19th January 2026 – Start of East Area Hardware Commissioning
    24th January 2026 – Start of AMS T09 Beam Commissioning
    26th January 2026 – AMS Run
    6th February 2026 – T09 beam line reconfiguration
    11th February 2026 – Start of East Area Beam Commissioning + T08 Start
    18th February 2026 – Start of East Area Physics
  Relevant information
    AMS run require a lot of work and shorten the planning a lot (no showstopper for the moment).
    We aims to have all lines ready before AMS run.
    T09 beam commissioning will be shorten by 1 or 2 days due to the work needed to roll back to normal configuration.
Prepared with A. Ebn Rahmoun and B. Rae