## Slide 1
Structural analysis (WP3.1 – WP3.2) follow up meeting
Status and objectives,
MSC-SMT-Arnaud Foussat, CERN
Collaboration Falcon D meeting, 17/06/2025

## Slide 2: CERN mock ups (LMKs) objectives
Rapid prototyping platform to validate main dipole structure design concepts.
  Baseline focus on R&D dipole alu-shell based Bladder and keys
  Not discussed here collared alternative mock up concept with SS welded shell and alu stoppers
  B&K structure concept on dipole validation:
    Operating stress points at RT, 4K, measurable, model benchmark on dummy test, Nb3sn coils test, poles variants
    Manufacture components, assess tolerances, cost effective methods
    Assembly process and tooling design

## Slide 3: Collaboration objectives
  Advancement to similar level the structure model analysis to pre-dimension main components:
    Technical meetings on structural analysis, CAD drawings review, EDMS versioning archive
    Share of design margin, limits, benchmark preloading sequence
  Procurement of parts take up to 8-10 months for critical items
    Proposed objective dates
      Alu shell : design by end Oct 25 – order Nov 25
      Yoke shapes : design by Nov 25 – order from Dec 25
      End plates, tie rod: design by feb 26
      WP3.2 SS collars shape, dimensions to be confirmed, design by Feb 26
      WP3.1 Alu collar shape for both M1, M2 models by Feb’26
  Most of components need be ‘standardised’ based on availability and lead time:
    Proposed Alu shell nominal thickness ( 32 mm), OD 630 mm, to be confirmed
    Armco laminations 5.8 mm thick

## Slide 4: WP3.1 Models structure test items
M1 mechanical model :
Validation of model size structure manufacture and assembly procedure, including tooling
Preloading system validation, instrumentation test
M2 model shall include tuning of M1 B&K loading parts dimensions, yoke optimization and include new features :
    Energy Shift Coupling (ESC) quench protection coils, no QHs
    Alu collar cooling channels for 4K indirect cooling