## Slide 1: CERN RFD Cavity Fabrication & HOM status
Simon Barrière, CERN
on behalf of the HL-WP4 team
15th HL-LHC Collaboration Meeting – CERN – 1st October 2025

## Slide 2: Outline
In the first few slides, I will highlight the good progress we have made in the production of RFD cavities at CERN
Then, a reassuring status update on the fabrication of HL-LHC crab cavities HOM couplers at CERN

## Slide 3: Outline
In the first few slides, I will highlight the good progress we have made in the production of RFD cavities at CERN
Then, a reassuring status update on the fabrication of HL-LHC crab cavities HOM couplers at CERN
Let’s now find out how much my optimism is close to reality

## Slide 4: RFD Cavities @ CERN

## Slide 5: Context
CERN
1x DQW CM
STFC – UK
4x DQW CMs
TRIUMF – Canada
5x RFD CMs
TCM-1
CM-1
CM-3
CM-4
CM-5
TCM-3
TCM-4
TCM-5
TCM-2
CM-1
See Bob Laxdal’s talk
10 crab cavities cryomodules (CMs) including 2 spares are needed for HL-LHC WP4
See Nik Templeton’s talk

## Slide 6: Context
10 crab cavities cryomodules (CMs) including 2 spares are needed for HL-LHC WP4
CERN
1x DQW CM
STFC – UK
4x DQW CMs
TRIUMF – Canada
5x RFD CMs
TCM-1
CM-1
CM-3
CM-4
CM-5
TCM-3
TCM-4
TCM-5
TCM-2
CM-1
TCM-5
Following PSM in May 2025, decision to add 1x RFD CM in CERN scope, with 2x CERN-produced RFD crab cavities
See Nik Templeton’s talk
See Bob Laxdal’s talk
See Teddy Capelli’s talk

## Slide 7: The Challenge
1 additional bare cavity (nickname CERN-RFD#4) to be fully constructed in 1 year…
          …and then, tested, jacketed and dressed, in time for integration in its TCM-5 cryomodule
          including raw materials procurement,
          650+ fabrication steps,
          13 technologies…
1x RFD cavity (CERN-RFD#3) already available at CERN (and successfully cold tested), spare from the prototyping programme in 2018-2020

## Slide 8: Raw Materials Procurement and Tests
          Purchase order placed on 27/02 (Nb & NbTi for 1x RFD cavity)
          Supply of 6 spare sheets from US-AUP’s series stock & DQW spare sheets allowed forming of initial components in April 2025
          All purchased materials tested and qualified at CERN
See Claudia Santos Maldonado’s talk

## Slide 9: Fabrication Strategy
Kick-off meeting took place on 17/03 with all teams
  Same manufacturing philosophy as CERN prototypes back in 2018/2019, same cavity cut-out
  Process rehearsal and tooling geometry validation with OFE copper trials, for all technologies
  A few days spent locating 70+ production tools and making sure they were complete and in good condition
Notes: Another important point for strategy

## Slide 10: CERN-RFD#4 Fabrication Status
done
in progress
March 2025
FPC Waveguide
H-HOM Waveguide
End Cap
Pole
V-HOM Waveguide
Pick Up
Corner
Half Main Body
Beam Axis
Beam Axis
Tuning Band
& Tuning Pin
Thank you Manuele for the nice chart!
End Cap

## Slide 11: CERN-RFD#4 Fabrication Status
FPC Waveguide
H-HOM Waveguide
End Cap
Pole
V-HOM Waveguide
Pick Up
Corner
Half Main Body
Beam Axis
Beam Axis
Sept. 2025
Tuning Band
& Tuning Pin
done
in progress
End Cap
All main forming activities done!
Now entering the phase where we handle high added-value components: extra care at all stages…
Thank you Manuele for the nice chart!

## Slide 12: Some Pictures
All extremities brazed
EB weld Nb to NbTi rings
Nb tubes all formed, and EB welded
Bulk transitions

## Slide 13: Some Pictures
End Cap
Half Main Body
V-HOM Box
H-HOM Box
FPC Box
Pole
Corner
Tuning Band

## Slide 14: QA/QC and Welding Engineering
          All subcomponents traced, compiled in EDMS 3244937, MIP & MTF structure created
          Joining processes fully qualified, all documents in EDMS 2726804
          Full measurement and tracking of thicknesses’ evolution on sub-components
See Myriam Benahmed’s talk

## Slide 15: Something Interesting
…I’ll be back!
Pole formed with Zanon/AUP material in 2022
A. Gallifa Terricabras et al. (SRF 2023)
“Optimizing the Manufacture of High-Purity Niobium SRF Cavities Using the Forming Limit Diagram: A Case Study of the HL-LHC Crab Cavities RFD Pole”

## Slide 16: Something Interesting
CERN pole PO-01
Zanon/AUP material
(March 2025)
Thickness
2,1 mm
Not acceptable
Heavy thickness reduction on poles formed both with AUP niobium sheets and CERN series material, even using the “2-step” process developed by Zanon RI
The folded morphology on the outer part of the sheet blocks it from entering the mold, resulting in tearing of the sheet
Root cause is likely to be the high mechanical properties
(Rp0,2 > 80 MPa) of these niobium sheets
A. Gallifa Terricabras et al. (SRF 2023)
“Optimizing the Manufacture of High-Purity Niobium SRF Cavities Using the Forming Limit Diagram: A Case Study of the HL-LHC Crab Cavities RFD Pole”

## Slide 17: Something (Very) Interesting
Solved using a new initial sheet design!
Notches all around the profile
Thickness
3,5 mm
CERN pole PO-03
Zanon/AUP material
Great teamwork!

## Slide 18: CERN-RFD#3 Jacketing

## Slide 19: CERN-RFD#3 Jacketing
Metrology of RFD #3 helium tank before final machining
Ti-SS brazed transitions done
Cold magnetic shield assembled on CERN-RFD#3
All hardware (magnetic shields, titanium vessels, fasteners, brazed transitions) manufactured and checked in record time!
Also all ready for CERN-RFD#4
Great synergy with MME design office & workshop
RFD#3 helium vessel assembly to start in the next weeks

## Slide 20: Next Steps
  Helium Vessel
  assembly
  TIG welding in glove box
  Pressure test
  Beam screen installation
From bare cavity to final beam screen assembly, more than 13 fabrication and inspection technologies are intertwined, with teams involved in all ATS departments
→ strong coordination and QA/QC follow-up required
Pictures from CERN-RFD#1 and RFD#2 jacketing (2020)

## Slide 21: Planning
CERN-RFD#4 bare cavity manufactured and tested
Production currently on-track, but aggressive schedule requiring many MME workshop resources, current focus on main body components (critical path)
Only RFD cryomodules shown here
CERN-RFD#3 jacketing in the shadow, the goal is to test this jacketed cavity in 2025

## Slide 22: HOM Couplers

## Slide 23: Production Scope: RFD series
CERN is manufacturing copper HOMC and Field Antennas for AUP RFD cavities
  H-HOM Coupler still under US-AUP scope
  Additional batch required for CERN RFD cavities
V-HOM Coupler
14 units
RF Field Antenna
14 units*
H-HOM Feedthrough & Coupler
14 units & 2 units
Fundamental Power Coupler
14 units
See Naeem Huque’s talk

## Slide 24: RFD – HOMC and Antennas for US-AUP
Pieces | Qty requested (series batch) | Qty produced at CERN
H-HOM Feedthrough | 8 | 4 shipped 4 done*
V-HOM Coupler | 8 | 4 shipped 4 done*
Field Antenna | 8 | 4 shipped 4 done*
  * : in final steps of preparation before shipping
RFD
V-HOM Coupler
RFD
Field Antenna
RFD
H-HOM Feedthrough

## Slide 25: RFD – HOMC and Antennas for CERN cavities
Pieces | Qty requested | Qty produced at CERN
H-HOM Coupler | 2 | 2 ongoing
H-HOM Feedthrough | 2 | 2 done
V-HOM Coupler | 2 | 2 done
Field Antenna | 2 | 2 done
RFD
H-HOM Coupler
RFD
V-HOM Coupler
RFD
Field Antenna
RFD
H-HOM Feedthrough

## Slide 26: RFD – HOMC and Antennas for CERN cavities
316LN St. Steel Jackets
Brazed Nb Bodies
Bulk Nb Hooks
RF Field Antenna after SUBU
H-HOM Feedtroughs
Chemistry & post-treatment processes now clear!
V-HOM Coupler

## Slide 27: Production Scope: DQW series
HOM Coupler + Feedthrough
36 units
RF Field Antenna
16 units
HF-HOM Coupler
16 units
Fundamental Power Coupler
14 units
  HOM Couplers, HOM Feedthroughs, HF-HOM Couplers and Field Antennas for LHC-series DQW Crab Cavities are being produced at CERN Main Workshop

## Slide 28: DQW – HOMC and Antennas
Pieces | Qty requested | Qty produced at CERN
HOM Coupler | 36 | 35 done 2 ongoing
HOM Feedthrough | 36 + 12* | 32 done 16* ongoing
HF-HOM Coupler | 12 + 4* | 12 done 4* ongoing
Field Antenna | 12 + 4* | 12 done 4* ongoing
  *: additional quantities to be produced following PSM in Sept 2024
DQW
HOM Coupler
DQW
HOM Feedthrough
DQW
HF-HOM Coupler
DQW
Field Antenna

## Slide 29: DQW – HOMC and Antennas
  Nb Hook Machining
  HF-HOM Final Weld
  Field Antenna Assembly
  HOM Feedthroughs
  HF-HOM Coupler
  Field Antenna RF Clamp

## Slide 30: DQW & RFD – Coaxial RF Internal Lines
Pieces | Qty requested | Qty produced at CERN
LHCACFRL0195 x4 for 1 CM RFD x2 for 1 CM DQW | 36 | 36 ongoing*
LHCACFRL0198 x2 for 1 CM RFD x4 for 1 CM DQW | 36 | 36 ongoing*
LHCACFRL0261 x4 for 1 CM DQW | 24 | 24 ongoing*
  *only missing components are ceramic brazed feedthroughs, expected to be finished by Q1-2026
DQW / RFD
LHCACFRL0195
DQW / RFD
LHCACFRL0261
DQW / RFD
LHCACFRL0198
See Alex Verduyn’s talk

## Slide 31: Conclusions
2x RFD cavities in production at the EN-MME main workshop for an additional RFD cryomodule to be assembled at CERN
CERN-RFD#3 is being jacketed, goal to cold test it this year
CERN-RFD#4 bare cavity in fabrication, challenging planning, so far on track
Technical issues solved on-the-field thanks to teamwork and workshop technical expertise, but can lead to potential delays
Series production of HOM couplers for WP4 near completion
Our next main challenge will be to keep momentum on fabrication in parallel of cryomodule assembly activities, ramping-up in 2026

## Slide 32: Many thanks to all main workshop and WP4 colleagues for their inputs!

## Slide 33: Backup slides

## Slide 34: RFD – HOMC and Antennas (1st set)
Pieces | Qty requested | Qty produced at CERN
H-HOM Coupler | 2* | 2** shipped
H-HOM Feedthrough | 2* + 4 | 2** + 4 shipped
V-HOM Coupler | 2* + 4 | 2** + 4 shipped
Field Antenna | 2* + 4 | 2** + 4 shipped
  * : spares of the prototypes built at CERN for RFD-SPS cryomodule
RFD
V-HOM Coupler
RFD
Field Antenna
RFD
H-HOM Coupler
RFD
H-HOM FT

## Slide 35: DQW & RFD – FPC Air Side
Pieces | Qty requested | Qty produced at CERN
Water Antenna | 28 | 28 done
Water Flanges In/Out | 30 | 30 done
Transmission Line (wevaguide, body) | 30 | 30 done

## Slide 36: DQW & RFD – FPC Antenna
Pieces | Qty requested | Qty produced at CERN
DQW Antenna | 14 | 6 done 8 ongoing
DQW Double Tube | 14 | 8 done 6 ongoing
RFD Antenna | 14 | 8 done 6 ongoing
RFD Double Tube | 14 | 8 done 6 ongoing
Vacuum Body | 28 | 28 done
RFD
FPC Antenna
RFD / DQW
Vacuum Body
DQW
FPC Antenna
DQW
Double Tube
RFD
Double Tube
  All missing assemblies are at very latest steps of production

## Slide 37: Quality & Documentation
TRAVELLER HOM COUPLERS & FEEDTHROUGHS |  |  |  |  |  | N°WB - __
 | CDD Number / Numéro CDD | Bld./ Lieu | Collaborator / Responsable | Signature | Date | Comments / Observations
Ceamic order number |  | 112 |  |  | __/__/20__ | 
Visual inspection of ceramic discs |  | 112 |  |  | __/__/20__ | 
Degreasing |  | 107 |  |  | __/__/20__ | 
Metalization / Mo/Mn 20-45 µm + Ni 5-10 µm |  |  |  |  | __/__/20__ | 
Visual inspection of ceramic discs |  | 112 |  |  | __/__/20__ | 
Metrology |  | AP |  |  | __/__/20__ | 
Machining Titanium flange (rough) |  | AP |  |  | __/__/20__ | 
Machining Copper part (finishing) |  | AP |  |  | __/__/20__ | 
Thermal stress relief treatment |  | 107 |  |  | __/__/20__ | 
Machining final Titanium flange (finishing) |  | AP |  |  | __/__/20__ | 
Etching flange + tube before brazing |  | 107 |  |  | __/__/20__ | 
Visual control before brazing |  | 112 |  |  | __/__/20__ | 
Vacuum brazing |  | 112 |  |  | __/__/20__ | 
Visual control after brazing |  | 112 |  |  | __/__/20__ | 
Ceramic n° engraving |  | 112 |  |  | __/__/20__ | 
Leak test |  | 864 |  |  | __/__/20__ | 
Sandblasting of ceramic |  | 864 |  |  | __/__/20__ | 
Metrology of antenna’s height |  | AP |  |  | __/__/20__ | 
EB Welding of back pieces |  | AP |  |  | __/__/20__ | 
Visual control |  |  |  |  |  | 
Metrology |  | 100 |  |  | __/__/20__ | 
Inspection finale SY-RF |  | 864 |  |  | __/__/20__ | 
Leak test / Contrôle d'étanchéité |  | 864 |  |  | __/__/20__ |