## Slide 1: Run3 observations as input for Run4 commissioning
D. Mirarchi on behalf of BE-OP-LHC team
Acknowledgments: X. Buffat, E. Maclean, L. Mether, S. Redaelli
15th HL-LHC Collaboration Meeting

## Slide 2: Introduction
Restarting after a Long Shutdown
Unexpected limitations, commissioning, and validation
Possible conceptual limitations
Conclusions

## Slide 3: Outline
Restarting after a Long Shutdown
Unexpected limitations, commissioning, and validation
Possible conceptual limitations
Conclusions

## Slide 4: First beam after LS2!
Some delays at end of LS2 (Covid-19, partial/complete warm-up during HW comm.) pushed start of Run3
2020
2021
B1 took short over 1h
B2 took several hours (debug/solve all issues)
Short before 6pm both beams happily circulating!
Quite efficient first hours of beams, but then…
Hardware Commissioning
(Training campaign to 6.8 TeV)
Checkout
Hardware Commissioning
(Training campaign to 6.8 TeV)
Beam TEST
LS2
Threading
Beam 1

## Slide 5: Unexpected surprises
Circuits
Identified old non-conformity on day 2:
Swapped RQTL7.R3B1 ⇄ RQTL7.R3B2
Identified in 2008, cured in 2009, and re-introduced in LS2
Fixed at control system level
Optics corrected on day 4, achieving db/b ~10%, comparable to 2018
Beam 1
Aperture
First hint of issues identified during Loss Maps (LM)
Confirmed by local aperture meas.
x-ray & tomography
showed buckled RF finger
Warm-up of S23
for repair
MQ-MB.C 21L3
Beam 1

## Slide 6: Lessons from 2 weeks beam test after LS2
If similar boundary conditions as after LS2
to be kept in mind to have a similar 2 weeks beam test towards end of LS3
Restarting a machine like the LHC after several years without beam can hide unexpected issues
Even few days with safe beam at injection can have a significant outcome:
  Test and commission key instrumentation
  Test old & new software tools
  Pre-commissioning of key systems (RF, Inj/Dump, Collimation)
  First collisions provided as well for pre-commissioning of detectors
  Unveal unexpected issues in advance with respect to planned start of Run3, reducing impact of delay
  Good initial training for renewed OP crew

## Slide 7: Outline
Restarting after a Long Shutdown
Unexpected limitations, commissioning, and validation
Possible conceptual limitations
Conclusions

## Slide 8: 2022 run
Broken collimation hierarchy identified during LM at injection for -dp/p (comm. after RF disk incident repair)
Mitigation strategy: phase knob implementation (MOPL019 and IPAC23)
TDIS.2
TCP.7
Parametric scan of MQ and Q’ showed significant impact from non linearities
Broken hierarchy
Beam 2
Beam 1
TCP.3

## Slide 9: 2024 run
Broken collimation hierarchy observed during b* levelling (first 1800b fill reaching warning dump losses)
TCSG.D4R7.B2
Mitigation strategy after TS1:
  Increased on_disp = +250 mrad (Xing = 150 mrad)
  Reduced to Q’ = 6 (from Q’ = 20)
  a3 correction for IR5
Investigations performed as End of Fill, revealed:
  linked with two-high intensity-beam effect
  isolated to Beam 2, caused by vertical beam loss
  sensitivity to bunch population, Q’, MO, Xing

## Slide 10: 2025 run
Broken collimation hierarchy observed at start of ramp in Beam 1 (first 1800b reaching warning dump losses)
Breakage successfully reproduced in -dp/p LM at inj.
Parametric studies revealed dependence on:
  MO polarity
  MO strength
  Phase knob
TCSG.6R7.B1
TCP.7
TCP.3
Beam 1
Mitigation strategy:
  Temporary decrease of MO = 1.5 (from MO = 2)
With phase knob = 1.5
  Increased phase knob = 1.5 after TS1 (from 1) (start of ramp losses moved from IR3 to IR7, not yet fully understood)

## Slide 11: What do they have all in common and lessons learnt?
Issues became clear while already running with full machine
Earlier detection must be pursued to avoid potentially dangerous events
All linked to large non linearities and particles with large betatronic and momentum offset (see Frederik Thu.)
Machine working point fine tuned during intensity ramp-up driven by beam stability considerations
Impact historically expected to be low and validation loss maps nominal Q, Q’ = 10, and MO = 1
Do we need to review/update/integrate validation strategy?
Example 2025 at injection:
 | Q1H/Q1V – Q2H/Q2V | Q’ | MO
Expected | .295/.313 – .295/.313 | 20 | 1÷1.5
Physics | .282/.305 – .286/.308 | 20 | 2

## Slide 12: How could we update validation strategy?
Re-validation after TS: same subset but for both sets of non-linearities to check stability?
Initial commissioning
with safe beams
First intensities above safe beams and first Stable Beams with INDIVs
Fine tuning during scrubbing with long trains + full beam-beam pattern
Important to keep present validation strategy of cycle validation via complete loss map matrix
time
Avoid surprises with high intensity beams (not easy to spot them promptly)
Subset of static points to be validated with full non linearities (after 400b step?):
Injection
Flat Top
Before collisions (most critical for aperture)
End of cycle (lowest b*)
Overall commissioning workflow already presented by Georges at Chamonix 2024, which still holds

## Slide 13: Lumi unbalance
The smaller the b*, the larger the impact any error of ℒIP1/IP5 unbalance (beating, waist shift, …)
See Joanna’s talk for more details!
Timescale of ATLAS & CMS calibration much longer than LHC needs (>1 year after vdM program)
~4% change of CMS ℒ calibration
Even if most of ∫ℒ done during levelling,
Any bias on provided ℒ will translate in bias on ∫ℒ:
high management decision outside our control
Inevitably attributed to not optimal LHC setup
Important to review comm. strategy and have OMC + independent ℒ,
to ensure ℒIP1/IP5 < 5% during commissioning/early stages
significant discussions may arise from unbalance when head-on

## Slide 14: Outline
Restarting after a Long Shutdown
Unexpected limitations, commissioning, and validation
Possible conceptual limitations
Conclusions

## Slide 15: Model dispersion
Full compensation of Dy with ad-hoc knob also for IP2 and IP8 in HL?
Broken hierarchy during b* levelling in 2024 normalised DyTCS.7/DyTCP.7
Mitigated in 2025 with updated on_disp knob
Near miss broken hierarchy in 2025:
Alternative solutions must be studied to avoid yet another hierarchy breakage, if not possible to mitigate in design (e.g. followup on possible asymmetric TCSP settings)
Increase Dx in IR6.B1 during b* levelling
Intrinsic optics feature
TCP.7.B1
TCSP.6.B1
T. Persson

## Slide 16: Loss Maps
Required trim DF/F > 160 Hz to get LossesIR3 > LossesIR7 at top energy
Not possible to validate +dp/p LM with operational Q’ and collisions Q, because the 3rd order resonance is inevitably hit!
How much are +dp/p LM with collision Q representative and is still worth doing them? How to take into account beam-beam for all LM in collisions (MD16225)?
Significant FF during operations
to compensate beam-beam Q shift:
Are we really compensating only or changing working point empirically? Theoretically expectations?
FF to be anyhow removed during validation after TS!
In collisions QH = 0.31, QV=0.32
160 Hz ≈ 1.1e-3 dp/p

## Slide 17: Outline
Restarting after a Long Shutdown
Unexpected limitations, commissioning, and validation
Possible conceptual limitations
Conclusions

## Slide 18: Conclusions
Some possible conceptual limitations may be present and must be addressed
LS3 and start of Run4 represents a unique occasion to brainstorm and integrate procedures based on state-of-the-art knowledge and available tools
Unexpected issues in Run 3 linked to large non linearities and large betatronic and momentum offset
Beneficial to extend validation strategy for an early detection and avoid surprises with full machine
Freezing machine configuration earlier would allow extended theoretical checks from various teams
Very valuable test beam at end of LS2, to be considered for end on LS3 if similar boundary conditions
Restarting a machine like the LHC after several years without beam can hide unexpected issues

## Slide 19: Outline
BACKUP

## Slide 20: First beam after LS2!
RF capture
Tune corrections
Collimators at coarse settings, not aligned
First check of ADT
Preliminary check of some instrumentation
First key system checks

## Slide 21: Bump amplitude for ASD
Apparently random dump experienced during Async. Dump validation:
Issue identified with bump amplitude of 1.2 mm ≈ 2.4 s displacement at TCDQ.6/TCSP.6
Collimation hierarchy tightened over the years and now only 2.3 s clearance TCP.7-TCSP.6
Right jaw of TCSP.6 becomes primary stage, leading to dump on losses (MQY.6) depending on tail population
The issue
The history
0.5 mm needed just for pattern systematic on orbit BPM
The tolerance was set to 1.2 mm and the bump amplitude matched to the edge of the SIS tolerance
IR6 BPM for HW interlock were only available for implementation in SIS
>3 s clearance TCP.7-TCSP.6
Temporary: bump amplitude reduced to 1 mm
Long term: detailed review of new tolerance, SIS on BPM of TCSP now available (~0.5 mm tolerance)
Mitigation

## Slide 22: Collimator settings at injection
Collimator settings definition: measured beam sizes used at injection; model beam sizes used at top energy
Optics corrections reached similar performance at injection and top energy nowadays
Less accurate optics corrections at injection and comparative studies done at beginning of LHC
Main drawbacks of using measured beam sizes at injection:
  Prone to errors during alignment
  More complex settings generation
Is it still necessary to use measured beam sizes at injection?
Comparative studies should be planned at start of Run 4