## Slide 1: BWS LHC CONS Status
BWS LHC CONS #29 J. Emery 27.06.2025

## Slide 2: May/June 2025
12.05.2025 - June BWS LHC CONS meeting #28 https://indico.cern.ch/event/1546764/
05.06.2025 – BI-TB: Mechanical update & Wire Scanners magnetic drive oscillation https://indico.cern.ch/event/1546089/
=> Very positive feedbacks on the team’s good work and readiness => Go ahead with the fabrication of the lab and LHC prototypes
Overall mechanics and optical disk patterns ready See today’s update (Harry)
Calibration bench commissioned with the Test rig V3 See today’s presentation (Jonathan)
Magnetic link system simulation See today’s presentation (Marie)

## Slide 3: On-going request for the installation YETS 25-26
Cablings: copper for pick-up antenna RQF3080062 - Cable installation, number of cables: 2, length: ~90m, LHC, YETS 25-26 Fiber optics for the optical encoder RQF3080177 - Fiber Optics installation: LHC - YETS 25-26 => Exact position to be filled in (~2m upstream of Beam 1 tank) => Fibres added to PLAN 12763 contribution from EN-EL / Optical fibers
ECR: - Document started, editing on-going
Budget cost breakdown update - To be updated with the calculation of the prototypes’ costs.