## Slide 1: Injector RF
Present Status, Activities, Plans

## Slide 2: Work package RF
Accelerator
Injector RF
RF Amplifier
Resonant Structures
RF Feedback Loops
Synchrotron RF
RF Amplifier
Resonant Structures
RF Feedback Loops
MACS

## Slide 3: Recap: Main components of an RF System
Resonant structure = cavity
  To store energy (in form of EM-field)
  To apply E-field component in beam direction
RF amplifier
  To build up EM-field, i.e. to power the cavity
RF signal generation = LLRF
  Drives the RF amplifier
 LLRF (Low Level RF; means: low signal level)
Consists of closed loop controls,
to ensure HW performance
and beam stability/reproduceability
1
2
3
cavity
LLRF

## Slide 4: Injector RF – Status
Visit at Thomson (September 23rd, 2011)
Implement Summary Status in PLC (16 error groups)
Implementation of Beam Interlock Interface
  Two redundant inputs: « ¬RF veto »
  Two redundant outputs: « ¬Operational »
Adaption of LLRF
  Waveforms: 16bit, 10’000 samples, 4 channels
  Disabling Stepping Motor Interface when in REMOTE
  Disabling of 1MHz RTB functionality
  RF pulses: LINAC, STAB, and TEST
  Tagging with COUNTER/SUB-COUNTER
  Implementation of history for LINAC, STAB, and TEST snapshots (including counter/sub-counter)
  Extension of error flags, to indicate « RF pulse OK »

## Slide 5: Injector RF – Milestones
Item | Location | Date/Duration
FAT 250kW amplifier at Thomson premises | Turgi | Next month, 2011
Delivery 250kW+10kW amplifier to CERN | CERN | November 30th, 2011
Installation 250kW amplifier at CERN completed, accepted on non-resonant load | CERN | January 11, 2012
Operation at ITS | CERN | until end of ITS

## Slide 6: Injector RF – Actions
Prepare ITS (acceptance tests, terminated/resonant load, RF conditioning, operation with beam)
Thomson implementing final details
Awaiting updated documentation of PLC signal list (including summary field)  XML device description
Awaiting revised version of LLRF emulator, including updated documentation of TINE interface
Solid-State amplifiers (10 kW): Control System-Integration
During the ITS in 2012, the RF system is available in parallel operation for control system integration (10 kW Buncher subsystem).

## Slide 7: THank you!