## Slide 1: UK Updates Global CCCM 18 Jul25
Niklas Templeton on behalf of UK WP4 team

## Slide 2: Technical Updates
Bi phase received!!!
  Some minor NCs (next slide)
Top plate pre-assembly complete
2K MLI received
OVC#2 received
Cleanroom refurb complete – certification booked late-Aug
CM3 string tooling ready
OVC#2
Bi Phase Received
Top Plate Gantry Assembly
2K MLI received
CM3 String Tooling Ready

## Slide 3: Bi Phase Incoming Inspection
Bellows covers left on for final welds – melted plastic residue left behind
Some welds not cleaned (discolouration)
Tooling loosened during transport
Small-shallow bellows dent discovered

## Slide 4: CM2 Schedule (Jul25)
No delays since May update
Challenges
Many survey & alignment activities
  Particularly for CM2
  Much more than RFD
  Complex requirements
  Time to perform, report, review can be weeks not days
Specialist resource co-ordination & availability
  STFC welder, CERN specialist visits, STFC Cryo & Vac Eng’s
  Other projects, leave, conferences…

## Slide 5: CM3-5 Planning (Jul25)
draft for discussion
draft for discussion
Cavity delivery dates: WP4_Master_Planning_June_2025_v1.7
Assuming 5 build technicians – currently 3.5

## Slide 6
Management & Oversight
Graeme Burt
HL-LHC-UK PM
Anna Vikhoreva Project Support
Ian Lazarus
STFC Sponsor
Phil Atkinson Technical Oversight
Paul Hindley Technician Manager
Ed Jordan
DAPT Lead
WP Lead
Nik Templeton
Andy Blackett-May
IQT Lead
Luke Bladen
TE Lead
Ivan
Cryo Engineer
Ollie
Vac Engineer
John
Welder
Abi
Technician
Roy
Engineering Works
Kavi Grad Engineer
David Undergrad Engineer
Carlos Granjeiro
QAWL Lead
Susan Technician
Matty Technician
Stuart
Vac Engineer
Dan
Design Engineer
Luke F Grad Engineer
Design, Assembly Procedures & Tooling
Quality Assurance, Welding & Logistics
Technical Engineering
Instrumentation, Qualification & Testing
*simplified representation – does not reflect pay band & line management structure
Crab Cavity Cryomodules
Shared Specialist Resources
Outside
Manufacture
In-House Manufacture
Vacuum
Processing
Riggers
Metrology
Logistics
Transitioned to 50%
Departed
Moving to DUNE
Abi Backfill
Back to DAPT (50%)

## Slide 7: Thanks! Questions?