## Slide 1: BGI / Telescope: Key Dates & Priorities for Q3/Q4 2025
James Storey, SY-BI-XEI BGI/Telescope Meeting on 17th July 2025

## Slide 2: (Some) Key Dates in Q3/Q4 2025
Date | Event
27th August - 2nd September | Telescope Testbeam #2
23rd September | HL-LHC WP13 Beam Size Review
29th - 2nd October | HL-LHC Collaboration Meeting
19th - 23rd November | Telescope Testbeam #3

## Slide 3: XEI Priorities (for discussion)
TPX3 Telescope: Fix time synchronisation issue → Fundamental to use telescope this year.
  Hampus, Lukas, Juri & Justus.
SPS BGI: Setup detectors, systematic measurements & comparison with wire scanner → Important input for HL-LHC Beam Size Review.
  Lukas, Hampus
PS & SPS BGI Readout v5: Write Engineering Specification.
  Hampus, Juri, Steen, Lukas, Gabriela, Mark
TPX3 Telescope: Support pre-testbeam & testbeam periods.
  Justus, Lukas, Hampus, Juri, Mark, James
PS BGI: Understand what’s wrong with the PS BGI-H.
  Hampus, Mark
Legend
Task leader + contributors

## Slide 4: XEI Priorities (for discussion)
HL-LHC BGI: Basic electronics design (in-vacuum & DAQ) → Input to HL-LHC Beam Size Review.
  Mark (In-vacuum), Hampus (DAQ)
PS & SPS BGI Readout v5: Demonstrate concept.
  Juri, Hampus, Lukas, Steen, Gabriela
TPX4 Telescope: Engineering specification for Timepix4 telescope.
  Justus, Hampus, Lukas, Juri
TPX4 Telescope: Design telescope plane PCB.
  Justus, Hampus, Mark
PS & SPS BGI: Understand data sync. issue(s).
  Hampus, Mark, Gabriela, Lukas, Juri