## Slide 1: 7 October 2011
Hardware for FRESCA2
A. Milanese, J. C. Perez

## Slide 2: Hardware for FRESCA2
In progress:
aluminium alloy shell
components for the “dummy coil assembly”
cryostat
aluminium oxide insulating coating
oven
vacuum tank for impregnation
To be done:
components for the “coil”: central posts, end shoes, wedges
winding / reaction / impregnation tooling
assembly tooling
cable insulation, traces and other instrumentation
components for the external splices

## Slide 3: Procurement of mechanical components
All the components will be used for the real magnet, with the exception of the dummy coils, that are two blocks of Al alloy.
The order for the Al alloy raw cylinder was placed Sept. 15, 2011. We agreed on alloy characteristics and controls (material certificate, ultrasonic inspection, tensile test at room and cryogenic temperatures).
Expected delivery is in mid Jan. 2012.
The procurement of the other components has been split in three lots, as follows:
  cold mass: half yokes, shell, keys and slipshims
  coil pack mock up: horizontal and vertical pads, coil mock-up
  axial compression system: end plate, rods, components for pretension at room temperature

## Slide 4: Procurement of mechanical components
A call for tender has been published and several companies expressed interest.
On the basis of the price enquiries and the technological competences, three firms are being considered at the moment:
  cold mass: Spanish company
  coil pack mock up: Dutch company
  axial compression system: Finnish company
The next step is to discuss the details of the fabrication with the companies and to evaluate their manufacturing capabilities.
In all cases, the lead time from the placement of the order to delivery is around 3 ½ - 4 months (for the cold mass lot the availability of the shell material should be considered).

## Slide 5: FRESCA2 cryostat
[from Arnaud Vande Craen, Pierre Minginette, Vladislav Benda]
The conceptual design of the cryostat is finished.
The engineering design is on-going, as well as the design of the cryogenic lines.
The call for tenders for the components should be published at the beginning of 2012. Also in that case the lot will be probably split in several parts.
By end of 2012 all the components should be delivered at CERN.
The cryostat should be operational at the beginning of 2013.

## Slide 6: Others
The feasibility of the aluminium oxide plasma spray coating for the pieces of FRESCA2 in contact with the coil is on-going.
For the reaction oven we are in the adjudication process. The working volume has been specified as 2500 × 600 × 500 mm. Operation could start in summer 2012 [Friedrich Lackner].
For the impregnation, we are doing a market survey for a new vacuum tank, that can be used to impregnate the FRESCA2 coils in a horizontal (inclined) position. There is a visit to a company planned shortly. The objective is to buy something off the catalogue, or a slight variant thereof [Paolo Fessia].