Injection Region Design Meeting – Summary
Participants:
Vittorio Ferrentino, Patric Muggli, Edda Gschwendtner, Nicolas Chritin, Jim Uncles, Justin Pisani, Daniel Easton, Eleonora Belli, Marlene Turner

Discussion Points
Magnets
- New magnets (e.g. octupoles): delivery time ~1.5–2 years, cost ~50 kCHF.
- Available CERN magnets: delivery time ~1 month.
- Magnets from collaborators (e.g. quadrupoles): delivery time ~2–3 months, cost ~7–10 kCHF.
- Action: Eleonora to check with Vittorio and Philip the functional specs of existing magnets and assess the margin within the current optics.
- Current Sextupole magnet dimensions are uncertain. Action: Nicolas to follow up with the collaborator and update the CAD drawing accordingly.
- Action: Vittorio and Philip to clarify which of the last 5 beamline magnets (dipole, corrector, octupole, sextupole, quadrupole) can be opened and how.
Waist Location
- CAD shows the waist ~8 cm downstream of the dipole pole pieces.
- Fringe fields extend ~10 cm (comparable to the dipole opening).
- Mechanically, shifting the waist 2–3 cm downstream is feasible if needed.
- The optics waist is ~24 cm further downstream than shown in the CAD.
- Action: Eleonora to shift the optics waist upstream by ~21–24 cm, keeping current magnet positions or, if needed, redesigning the line with the same magnets. Conclusions to be shared with GWA (time estimate: by end of the month).
Space Upstream of Expansion Volume
- GWA has updated the expansion volume design, ending in a CF40 flange.
- BPM + corrector will be a single aligned component, requiring a support structure.
- A short bellow (~few cm) inside the BPM + corrector allows ~2 mm transverse alignment.
- A flange is needed between the BPM + corrector and the octupole — it may extend inside the octupole, but must remain outside the B-field.
- Action: Eleonora and Maria-Carmen to choose the type of flange for the connection between the BPM and octupole chamber
- Action: Eleonora and Nicolas check whether it is possible to modify the support so that we can use the proposed longer corrector. If this is not feasible, we will need to adapt the corrector design instead
- A valve is required and can be placed upstream of the quadrupole.
- Action: GWA to upload the new drawing to the EDMS folder.
- Action: Marlene to organise a meeting on assembly strategy.
- Action: Marlene to check with BI on BPM sensitivity to rubidium exposure.
Injection Dipole
- Covers can be modified but must be present.
- No downstream elements needed for now.
- Only 316 LN steel may be used within the magnetic field.
Other Topics
Begin considering the 150 MeV beamline commissioning phase: could a simpler injection region design be used?