## Slide 1: POLAR-2 Weekly Meeting 04-Aug-2025 (week 32)

## Slide 2: WP0 - Management
Pol LOE: clarifications on export control asked to PRODEX
Discussions in progress with Tübingen and IHEP for PLAN-B
Documentation:
  SoW: no update. New update depends on changes/conclusions of thermals analysis
  ICD:
    ICD_v6 document drafted after CSU meeting.​

## Slide 3: WP0 - Management
ICD:
  Mechanical Design of POLAR-2 well documented
  Thermal Analysis being reviewed with CSU
    Updated RAA sent to Franck (it is now thermally isolated)
    Franck is updating simulations (issues with solver fixed!!)
    FEA is done, document has been sent to CSU last week with already some feedbacks (discussions on Wednesday)
    Main modification: SUN is at 65° respect to Zenith axis (less SUN power consequently)
  Communication interface of ICD sent to CSU (no response about it)
  ICD will converge when thermal analysis is complete and validated by all contributors
  Communication interface information is accepted
  Add 'Annex' with qualification requirements

## Slide 4: WP0 - Management
Beidou:
  CSU is ok if POLAR-2 includes hardware for Beidou
    License to be requested in parallel
  No news about Beidou 3 licences
    Jianchao will contact Shaolin to inquire about possibilities
    Possible synergies with HERD, BSD, POLAR-2 ?
    Development board available for ground-to-ground testing (https://e.tb.cn/h.TugrgUteW76QzSu?tk=lNcXekX3A7X)

## Slide 5: WP1 – Detector Module
10 Carbon Fiber sockets are delivered from Composite Design company (CD)
Target insertion looks OK so far... (inner size checked)
  GO/NoGO gauge : received at DPNC for outer dimension check, will be sent to CD for final production
  Quote by CD received...quite cheap for re machining (170 CHF / 10 units, and 1080 for 120 units).
  8 remaining sockets have been re-machined and sent to DPNC (looks good except some tiny issues on the round corners … will be adjusted for the mass production.
  Total cost estimate for 120 sockets fully operational= 24300 CHF (VAT excluded)
160 bars have been wrapped by Coralie (TBC on a bi weekly basis)
147 bars have been wrapped by Johannes in 202
3 targets assembled (in 202)
Sorbothane pads have been cut and received at DPNC (480 pads)
CITIROC will stop production by early 2026 (currently 1000 units in stock)

## Slide 6: WP1 – Detector Module Production
Chart: 
| Pending Delivery | Delivered | Delivered + Wrapped
Scintillator Bars | 3500 | 3698 | 302
Chart: 
| Pending Delivery | Delivered | Delivered + Probed
SiPMs | 13 | 225 | 262
Chart: 
| Pending Delivery | Delivered
CF Sockets | 120 | 0
Chart: 
| Pending Delivery | Delivered
FEE | 120 | 0
Chart: 
| Incomplete Modules | Target Built | Modules Fully Assembled
Modules | 117 | 2 | 1
Chart: Scint. Bar Wrapping Progress
| EQM | FM
Wrapped | 307 | 0
Should already be wrapped by today (updated weekly) | 426.6667 | 853.3333

## Slide 7: WP2 - FEE
Check again the voltage generation circuit and HK circuit. To understand the correctly how is behaving the FEE with the temperature correction  Will use FEE009.
FEE gain pulse calibration tests.
FEE V1 #4 presents HV high current consumption. Probe station tests show that at least 2 SiPM channels are not working.
  Now we see problems with HV distribution, still under investigation.
FW: version 3.3 released by Yannick.
  Need to prepare a test/validation plan.

## Slide 8: Bubbling problem with silicone window SiPMs
Explanation of Hamamatsu is not compatible with the temperature control of the probe station chuck.
NCR updated, v1.3 on SVN.
Tests done by IHEP, no problem seen. Report soon on SVN.

## Slide 9: WP3– BEE
              BEE Review Report – to be finished
              Corrections after BEE review – implemented
              NP: I have not yet seen the report on my question of unconnected pins
              Manufacturing and assembly documentation - ready

## Slide 10: WP4 – PHU – LVPS First Stage
              LVPS First Stage Review Report – to be finished
              Corrections after LVPS First Stage review – implemented
              Manufacturing and assembly documentation - ready

## Slide 11: WP4 – PHU - LVPS Hub
              Designed and manufactured by external company
              Modifications to be done:
                FEE connector change
                Startup delay circuit to be modified
                New requirement is > 3.9V (was 3.8V), require a change of resistor setting

## Slide 12: WP5 – Payload Thermo-Mechanical Structure (PTMS)
Instrument stacked in pieces:
Polarimeter will be assembled and delivered to China. RAA and PIP will be assembled on CSS
Full instrument will weigh <160kg (including RAA and adapter plate)... Weight to be updated (modules are being optimized after thermal studies)
New design under FEA simulations (see next slide)
Cable routing to RAA being discussed (unacceptable to route over CFRP Top Cover)

## Slide 13: WP5 – Payload Thermo-Mechanical Structure (PTMS)
Minimum gain:
- 60gr per module

## Slide 14: WP5 – Payload Thermal-Mechanical Structure (Steady state)
Leading to transient analyses (COLD & HOT conditions, Beta angles..)

## Slide 15: WP5 – Payload Thermal-Mechanical Structure (transient... up to 31 hours)
Latest simulations up to 31 hours...showed 3.8°C at corner and 10.5 °C at center
SiPM temperature close to the center...
SiPM temperature at a POLAR2 corner..
Need some updates according to CSU, βangle up to 65° to be accounted .. FEA ongoing by DPNC (see next slides)

## Slide 16: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 17: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 18: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 19: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°

## Slide 20: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°

## Slide 21: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°
Next steps:
Apply MLI on critical surface? Like P1?... and the opposite surface when negative beta...
Check with other β angles ...see that of ISS (AMS02 example below)
Up to 45°, eclipse is around 32 minutes
ISS beta angle

## Slide 22: WP5 – Payload Thermal-Mechanical Structure

## Slide 23: WP5 – Payload Thermal-Mechanical Structure

## Slide 24: WP5 – Payload Thermal-Mechanical Structure

## Slide 25: WP5 – Payload Thermal-Mechanical Structure
Thermal analysis report to CSU
  Last iterations with various beta angles and report will be released to CSU for review (by mid August)
  To estimate the impact (sensitivity) of β angle on temperatures
  For instance:
  30° angle, giving 35 minutes nighttime
  0° angle, giving 36 minutes nighttime.

## Slide 26: WP6 – Qualification and Verification
Radiation requirements for BEE and LVPS
  Conditions by UniGe: 1kRad
  Conditions by CSU: none. But test must be performed. Performance metrics decided by UniGe
Probe station tests will resume when the cold water circuit upgrade will be completed (beg. August).

## Slide 27: WP7 – Flight Model Acceptance
Need to contact UniBe for space qualification.
  For TV, we should prepare the list of components with their mass and outgassing properties.
  For vibration, we have to get from CSU the vibration levels during launch (considering POLAR-2 will be in a transportation box).
  Preliminary design document of the payload packaging transmitted by Jianchao.

## Slide 28: WP8 – POLAR-2 Onboard Software System
Still framing problem with ZYNQ.
Vishal has installed vivado2025 on his computer
No progress form YJ. One file is missing fin the project
New Firmware version 3.3 solving last small problem (stopping run)
Discussion about communication box: the FPGA that Dominik use in the BEE can be used as a communication box.
Price of a develpoment board is 1500$ Price for testing the firmware is 30K$ (initial cost) + 10K$ per FPGA. If we find 45k Nicolas can do it in China before end of the year
Yannick say that reading several FEE with GPIO is possible but need some work

## Slide 29: Simulations
Working on Analysis software to unify all scripts we have
  Goal: Full module characterization with a single command
Current implementation includes
  Change of positioning on CSS
  Robotic arm adapter
  Tungsten plate
Open tasks
  Impact of shadow cast by RAA
  Updated implementation of response in framework
  More cleanup

## Slide 30: ESRF
Request accepted
  15 shifts
  Beamline ID19
  Week 6 in 2026 proposed (MD day used to setup)
Tasks to complete before ESRF
  Procurement of components for 10 modules (9+1 reserve)
    FEE -> Yannick is reviewing HV issue on FEE Hancheng used
    Mechanical structures (end cap, alu support structure, etc.)
    cables
  Wrapping 640 bars (~300 done)
  Readout (Nicolas, Dominik, Uni. Tuebingen)
We will prepare a Gantt chart to plan the activities until the beam test.

## Slide 31: EQM

## Slide 32: EQM – Gantt Remarks
The DAQ system should still be added to the chart.
The FEE transportation boxes should still be added to the chart.
2 weeks of Christmas Holidays are taken into account (then if heroes are around, this will just make a nicer chart for January 26).
As soon as we have more infos on the CN7 validation, we should start ordering the PCBs (with or without conclusions on the HV problem of FEE v1, as agreed some weeks ago already).

## Slide 33: Conferences/Paper/Misc.
ICRC proceeding deadline 19/Sep (final version)
NDA writing proceeding for SPIE (about POLAR-2 in general)
More??