## Slide 1: STELLAR Debrief IR-SG input
IR-SG
29 September 2025

## Slide 2: Key figures
  A/V production 12’700 CHF
    Light and sound tech 2’250 CHF
    Camera + consulting 4’500 CHF
    Script 1’100 CHF
    Photograph 1’000 CHF
    Moderation 1’335 CHF
    Interpretation 2’500 CHF (10 headsets)
  Printed signage 516 CHF
  3 hours of cleaning / 150 CHF
  44 guides / 272 hours / 8’959 CHF
  Catering 6’700 CHF
  Guides training material (12 pages)
  Shop : 7’400 CHF income
  80.30 overtime hours (IR-SG) for 4 persons
  Full Big Bang Café (500 crêpes!)
  Estimated 1500 participants overall
    3 talks (600 pax / 250 pax / 250 pax)
    4 meet the astronauts ( 2 x 200 pax)
    3 book signings (30 pax by author)
    3 music bands (150 pax average)
    10 hands-on activities (850 pax in total)
  3 preparatory meeting / many emails
  2 indicos with 5 registration forms
  4 guards / 2’700 CHF
  2 technicians (tech support) / 850 CHF
  3 reception staff / 1’325 CHF
  External A/V 11’400 CHF
    Stage 3’380 CHF
    Screen + light 5’749 CHF
    Sound 2’299 CHF

## Slide 3: What worked well
Meet the astronauts
  Very popular
  Accessible to all ages
  Good format
Science village
  Jump in jump out mode
  Diversity of activities
  Lab’s team support
  Big Bang Café
  Adapted offer
  Open to Piazza with music
Piazza content and setup
  Music bands
  Screen and stage setup
Exhibitions
Always new public for this activity
50% claim they visited them
ELISA was a highlight
Book signing
Used as an alternative meet and greet
Not overcrowded

## Slide 4: Room for improvement (1/2)
Moving target mode
  Too many last minute requests
  Not respected deadlines/decisions
  Need for a real and applied retroplanning
Collaboration with a conference
  First talk for specialists
  Different agendas (social vs public event)
  Interface with conference organisers
Internal organisation
  Unclear responsibilities and decision making
  Parallel path on same topics (guides, signage etc.)
Talks programme
  Too dense, systematically overrunning
External participants
  Unmanaged hands on activities (Apollo)
  Unannounced participants (astronomy club)
Registration process
  Conflicting expectations
  Too complex
  Last minute changes in strategy
  Many missing organisers badges

## Slide 5: Room for improvement (2/2)
Staffing
  Lack of A/V tech support (bands, outdoor etc.)
Book signing
  Requires months of delay to order books
Budget planning
  Nobody had a clear picture of spent budget
  Some costs are still pending (guides)
Chosen period
  Many absent colleagues
  Competittion with other summer activities
  Diffictulties to get A/V material and services
  Major impact on fall activities for all teams

## Slide 6: Next edition of a similar event (i.e. Festival)
Align with strategy
Make sure the event has been approved by management
Build on this first experience
Focus on what worked well
Choose a better date
Earlier in Summer (end of June), away from school holidays
Avoid early September (no decisions during Summer, too close to major events)
Avoid other major science festivals (nuit de la science)
External partners?
If organised with external partners, define a proper interface, including all concerned parties (e.g. like for Cité des métiers)
Better internal organisation
  Involve all concerned parties from the beginning
  Have a clear decision process (project owner, project leader etc.)
  Define a clear retroplanning and respect it
  Clear budget management
  Respect decisions