## Sheet1
AMBER EXTRA TIME CONSTRUCTION
Reason | IMPACT | Hours
Construction started for 2 racks with wrong pneumatics valves | New piping | 120
No mecchanical support for O2 analyser | Support built | 24
Additional valves requested on the system | Modification pipes | 32
Additional welding control | Xray + endoscope | 16
Integration detection heads on top of the rack | more holes in 2 racks | 24
Manifolds exhaust chamber | Welding+assembly | 150
Removed old cable tray | Uninstallation | 16
No cable tray installed in external place | Installation | 24
External Exhaust pipe to build | Welding + mechanics | 24
New pipes for N2 and He | Installation | 16
No cable trays installed in beaam zone | Installation | 16
Piping and chamber adjustment | installation | 24
| TOTAL | 486