## Slide 1: LHCb Installation Expert Review
LHCb TC team

## Slide 2: Upgrade I and Upgrade II comparison
Most of Vessels and Detector support structures will be dismounted / replaced / modified
UI
UII
Muon chambers and ECAL modules will be replaced/modified
In addition to UI:
Middle Scenario: 2 new systems (TORCH and Magnet Stations)
Kept
New

## Slide 3
New VELO (pixel)
New rf-foil
New Vessel and Motion System
New UP ( CMOS, pixel)
LHCb Upgrade II TRACKING (Upgrade I)
New Magnet Station
LS4
New Mighty Tracker
Scintillating Fiber
Si Pixel
Modified or new support structure

## Slide 4
Upgrade II : PID
NEW RICH1
Photon detector
Optics Mirror
Gas Enclosure
Shielding
New TORCH
Install Detector( 12 Quartz bar)
Support structure
LS4
NEW RICH2
Photon detector
Optics Mirror
Gas Enclosure / structure

## Slide 5
Upgrade II : CALO & MUON
New PicoCal
Remove Ecal module
Modify Ecal modules
Reinstall 2864 Sashlik
Reinstall SpaCal
REPLACE HCAL by
Iron-concrete shielding (LS3)
Remove all MWPS (4x276)
Reinstall new Muon mrwell in R1 and R2
Reinstall modified MWPC in R3 and R4)
LS4

## Slide 6: Installation: Boundary Conditions & Features
Detectors can be open/closed/accessed independently
Installation/dismantling sequence to be respected
2 Worksites: Upstream and downstream (wrt to dipole). Connected via Beam Pipe
Limited or No access from Cryo (C) side
Service Cavern and Detector are separated by a Shielding wall (4m of concrete blocs).
A
C

## Slide 7: LS4 planning (middle scenario)
Upstream
Downstream
Dismantling phase
THIS IS NOT CONTINGENCY
ECAL Modules Modifications

## Slide 8: Critical Path Upstream (Installation Phase)
1 Velo Tank
2 RICH1 Gas enclosure
3 UP Side C
4 Beam Pipe sect 1 (and 2-4)
5 Beam Pipe Bake out
6 RICH 1 Exit window and optics
7 Velo Pixel Modules
1
2
3
4&5
6
7

## Slide 9: Critical Path Downstream (Dismantling Phase)
2
3
4
1 Remove beam Pipe Sect 2-4
2 Remove SciFi stations A and C side
3 Remove SciFi support structure
4 Remove RICH 2
5 Open ECAL, start dismantling
5

## Slide 10: Dismantling/installation scenario study for LS4
LHCb Design Office

## Slide 11: Phase 1
Activities :
Upstream :
Remove UT A side - 15d
Downstream :
Remove RICH2 columns -15d
Muon C side chambers & Services - 150d
Infrastructure
Remove shielding wall – 15d

## Slide 12: Phase 1
HCAL & ECAL must remain closed
Activities :
Upstream :
Remove UT A side - 15d
Downstream :
Remove RICH2 columns -15d
Muon C side chambers & Services - 150d
Infrastructure
Remove shielding wall – 15d

## Slide 13: Phase 2
Activities :
Upstream :
Remove RICH1 columns (A&C side)- 15d
Downstream :
Remove SciFi C-Frame A side – 15d

## Slide 14: Phase 2
Activities :
Upstream :
Remove RICH1 columns (A&C side)- 15d
Downstream :
Remove SciFi C-Frame A side – 15d

## Slide 15: Phase 2
Removal of SciFi C-Frame A side

## Slide 16: Phase 3
Activities :
Upstream :
Remove RICH1 optics - 15d
Downstream :
Remove Beam Pipe sections 2 to 4 – 15d

## Slide 17: Phase 3
Upstream :
Remove RICH1 optics - 15d
Activities :
Downstream :
Remove Beam Pipe sections 2 to 4 – 15d
Muon Shielding A-side, HCAL, ECAL, Neutron Shielding & SciFi C-side must be open

## Slide 18: Phase 4
Activities :
Upstream :
Remove RICH1 exit window – 10d
Remove BP section 1 – 5d
Downstream :
Remove SciFi C-Frame C side – 15d

## Slide 19: Phase 4
Activities :
Upstream :
Remove RICH1 exit window – 10d
Remove BP section 1 – 5d
Downstream :
Remove SciFi C-Frame C side – 15d

## Slide 20: Phase 5
Activities :
Upstream :
Remove UT C side – 10d
Downstream :
Remove RICH2 tower A side – 10d
Can be the good moment to remove gantry tower

## Slide 21: Phase 5
Activities :
Upstream :
Remove UT C side – 10d
Downstream :
Remove RICH2 tower A side – 10d
Removal piece by piece
Gantry tower to remove

## Slide 22: Phase 6
Activities :
Upstream :
Remove RICH1 shielding -10d
Downstream :
Remove Bridge – 10d

## Slide 23: Phase 6
Activities :
Upstream :
Remove RICH1 shielding -10d
Downstream :
Remove Bridge – 10d

## Slide 24: Phase 6
Bridge removal possible sequence

## Slide 25: Phase 7
Activities :
Upstream :
Remove VELO modules – 15d
Start of remove VELO mechanics – 10d
Downstream :
Remove ECAL modules A side – 20d

## Slide 26: Phase 7
Activities :
Upstream :
Remove VELO modules – 15d
Remove VELO mechanics – 10d
Downstream :
Remove ECAL modules A side – 20d

## Slide 27: Phase 8
Activities :
Upstream :
Start of remove/install services (upstream) – 30d
Downstream :
Remove ECAL modules C side – 20d

## Slide 28: Phase 8
Activities :
Upstream :
Start of remove/install services (upstream) – 30d
Downstream :
Remove ECAL modules C side – 20d

## Slide 29: Phase 9
Activities :
Upstream :
finish of remove/install services (upstream) – 30d
Downstream :
Remove RICH2 vessel – 10d

## Slide 30: Phase 9
Activities :
Upstream :
finish of remove/install services (upstream) – 30d
Downstream :
Remove RICH2 vessel – 10d

## Slide 31: Phase 9
RICH2 vessel removal possible sequence

## Slide 32: Phase 10
Activities :
Upstream :
Start of install new VELO mech. – 25d
Downstream :
Remove RICH2 tower C side – 10d
Start of install Magnet Stations – 25d

## Slide 33: Phase 10
Activities :
Upstream :
Start of install new VELO mech. – 25d
Downstream :
Remove RICH2 tower C side – 10d
Start of install Magnet Stations – 25d

## Slide 34: Phase 11
Activities :
Upstream :
Finish of install new VELO mech. – 25d
Downstream :
Install cryo equip. on platform C side – 15d
Finish of install Magnet Stations – 25d
Start Muon A side chambers & Services - 150d

## Slide 35: Phase 11
Activities :
Upstream :
Finish of install new VELO mech. – 25d
Downstream :
Install cryo equip. on platform C side – 15d
Finish of install Magnet Stations – 25d
Start Muon A side chambers & Services - 150d
Cryo equip. passage

## Slide 36: Phase 12
Activities :
Upstream :
Install new RICH1 shielding – 25d
Downstream :
Install new RICH2 vessel – 25d

## Slide 37: Phase 12
Activities :
Upstream :
Install new RICH1 shielding – 25d
Downstream :
Install new RICH2 vessel – 25d

## Slide 38: Phase 12
New RICH2 vessel installation possible sequence

## Slide 39: Phase 13
Activities :
Upstream :
Install UP C side – 25d
Downstream :
install TORCH – 25d

## Slide 40: Phase 13
Activities :
Upstream :
Install UP C side – 25d
Downstream :
install TORCH – 25d

## Slide 41: Phase 14
Activities :
Upstream :
Reinstall BP section 1 – 10d
Downstream :
install new Bridge – 20d

## Slide 42: Phase 14
Activities :
Upstream :
Reinstall BP section 1 – 10d
Downstream :
install new Bridge – 20d

## Slide 43: Phase 14
New Bridge top frame in 2 parts possible sequence

## Slide 44: Phase 15
Activities :
Upstream :
Reinstall new RICH1 exit window – 15d
Downstream :
reinstall RICH2 tower C side – 10d

## Slide 45: Phase 15
Activities :
Upstream :
Reinstall new RICH1 exit window – 15d
Downstream :
reinstall RICH2 tower C side – 10d

## Slide 46: Phase 15
Activities :
Upstream :
Reinstall new RICH1 exit window – 15d
Downstream :
reinstall RICH2 tower C side – 10d

## Slide 47: Phase 16
Activities :
Upstream :
Start of install UP A side – 20d
Downstream :
reinstall RICH2 tower A side – 10d

## Slide 48: Phase 16
Activities :
Upstream :
Start of install UP A side – 20d
Downstream :
reinstall RICH2 tower A side – 10d

## Slide 49: Phase 17
Activities :
Upstream :
Finish of Install UP A side – 20d
Install new RICH1 columns – 30d
Downstream :
Install mighty tracker C side – 40d

## Slide 50: Phase 17
Activities :
Upstream :
Finish of Install UP A side – 20d
Install new RICH1 columns – 30d
Downstream :
Install mighty tracker C side – 40d

## Slide 51: Phase 17
Activities :
Upstream :
Finish of Install UP A side – 20d
Install new RICH1 columns – 30d
Downstream :
Install mighty tracker C side – 40d

## Slide 52: Phase 18
Activities :
Downstream :
Install new RICH2 columns -15d
Muon C side chambers & Services - 70d

## Slide 53: Phase 18
Activities :
Downstream :
Install new RICH2 columns -15d
Muon C side chambers & Services - 70d

## Slide 54: Phase 18
Activities :
Downstream :
Install new RICH2 columns -15d
Muon C side chambers & Services - 70d
Neutron shielding must be closed

## Slide 55: Phase 19
Activities :
Downstream :
reinstall ECAL modules C side – 30d

## Slide 56: Phase 19
Activities :
Downstream :
reinstall ECAL modules C side – 30d

## Slide 57: Phase 20
Activities :
Downstream :
Reinstall BP section 2-4 – 15d

## Slide 58: Phase 20
Activities :
Downstream :
Reinstall BP section 2-4 – 15d

## Slide 59: Phase 21
Activities :
Upstream :
Install new VELO modules – 30d
Downstream :
Start install Mighty Tracker A side – 40d
Muon A side chambers & Services - 70d

## Slide 60: Phase 21
Activities :
Upstream :
Install new VELO modules – 30d
Downstream :
Start install Mighty Tracker A side – 40d
Muon A side chambers & Services - 70d

## Slide 61: Phase 22
Activities :
Upstream :
Install new RICH1 optics – 20d
Downstream :
Finish install Mighty Tracker A side – 40d
Reinstall ECAL modules A side

## Slide 62: Phase 22
Activities :
Downstream :
reinstall ECAL modules A side – 30d

## Slide 63: Phase 23
Activities :
Downstream :
Finish Muon A side chambers & Services - 70d
Infrastructure
Reinstall shielding wall – 20d

## Slide 64: Phase 23
Activities :
Downstream :
Finish Muon A side chambers & Services - 70d
Infrastructure
Reinstall shielding wall – 20d
Gantry tower
Visitor platform

## Slide 66: Detector Readiness

## Slide 67: Lessons Learnt from UI (1/4)
The detectors readiness was driving the installation planning in LS2, not the installation time itself
Mitigation:
Enhance follow-up and monitoring of progress though U2IG
Include contingency in planning, not to be confused with extra time.
CERN-LHCC-2024-010

## Slide 68: Lessons Learnt from UI (2/4)
Near detector services* design, integration, and installation work was largely underestimated in UI
(*) Services from the detector to the up to nearest connecting point (Patch panel, valve …)
Mitigation:
Raise awareness, enhance coordination between sub-detector and TC team, strengthen design office and installation teams.

## Slide 69: Lessons Learnt from UI (3/4)
Logistics and assembly facilities were a bottleneck in UI. There is only 1 medium-sized assembly hall at P8. UII will be much more demanding, given the additional work on large detectors (PicoCal, Muon, RICH2, TORCH, Mighty Tracker, support structures).
Mitigation:
It is a necessary condition for success to have sufficient and adequate laboratory, test and assembly space available, from the end of LS3.
A detailed task-oriented facility inventory has been made and documented.
A large Assembly Hall, Laboratory space to work on activated material and Clean Room are missing. Support from hostlab is necessary.

## Slide 70: Lessons Learnt from UI (4/4)
Final detector assembly, test (and of course installation) could only be done at CERN.
Attracting key technical manpower to work at CERN is a necessary condition.
Mitigation:
Raise awareness among participating institutes and FA .
Decent working conditions, work area, and offices shall be provided to users.