## Slide 1: POLAR-2 Weekly Meeting 25-Aug-2025 (week 35)

## Slide 2: WP0 - Management
Pol LOE: Polish budget/CN officially approved?
Discussions in progress with Tübingen and IHEP for PLAN-B
Documentation:
  SoW: no update. New update depends on changes/conclusions of thermals analysis
  ICD:
    ICD_v6 document drafted after CSU meeting.​

## Slide 3: WP0 - Management
ICD:
  Mechanical Design of POLAR-2 well documented
  Thermal Analysis being reviewed with CSU
    Updated RAA sent to Franck (it is now thermally isolated)
    Franck is updating simulations (issues with solver fixed!!)
    FEA is done, document has been sent to CSU last week with already some feedbacks (discussions on Wednesday)
    Main modification: SUN is at 65° respect to Zenith axis (less SUN power consequently)
  Communication interface of ICD sent to CSU (no response about it)
  ICD will converge when thermal analysis is complete and validated by all contributors
  Communication interface information is accepted
  Add 'Annex' with qualification requirements

## Slide 4: WP0 - Management
Beidou:
  CSU is ok if POLAR-2 includes hardware for Beidou
    License to be requested in parallel
  No news about Beidou 3 licences
    Jianchao will contact Shaolin to inquire about possibilities
    Possible synergies with HERD, BSD, POLAR-2 ?
    Development board available for ground-to-ground testing (https://e.tb.cn/h.TugrgUteW76QzSu?tk=lNcXekX3A7X)

## Slide 5: WP1 – Detector Module
10 Carbon Fiber sockets are delivered from Composite Design company (CD)
Target insertion looks OK so far... (inner size checked)
  GO/NoGO gauge : received at DPNC for outer dimension check, will be sent to CD for final production
  Quote by CD received...quite cheap for re machining (170 CHF / 10 units, and 1080 for 120 units).
  8 remaining sockets have been re-machined and sent to DPNC (looks good except some tiny issues on the round corners … will be adjusted for the mass production.
  Total cost estimate for 120 sockets fully operational= 24300 CHF (VAT excluded)
~260 bars have been wrapped by Coralie (TBC on a bi weekly basis)
147 bars have been wrapped by Johannes in 202
3 targets assembled (in 202)
Sorbothane pads have been cut and received at DPNC (480 pads)
CITIROC will stop production by early 2026 (currently 1000 units in stock)

## Slide 6: WP1 – Detector Module Production
Chart: 
| Pending Delivery | Delivered | Delivered + Wrapped
Scintillator Bars | 3500 | 3593 | 407
Chart: 
| Pending Delivery | Delivered | Delivered + Probed
SiPMs | 0 | 89 | 411
Chart: 
| Pending Delivery | Delivered
CF Sockets | 110 | 10
Chart: 
| Pending Delivery | Delivered
FEE | 120 | 0
Chart: 
| Incomplete Modules | Target Built | Modules Fully Assembled
Modules | 117 | 2 | 1
Chart: Scint. Bar Wrapping Progress
| EQM | FM
Wrapped | 442 | 0
Should already be wrapped by today (updated weekly) | 571.4286 | 1142.8571

## Slide 7: WP2 - FEE
Check again the voltage generation circuit and HK circuit. To understand the correctly how is behaving the FEE with the temperature correction  Will use FEE009.
FEE gain pulse calibration tests.
FEE V1 #4 presents HV high current consumption. Probe station tests show that at least 2 SiPM channels are not working.
  Now we see problems with HV distribution, still under investigation.
Production of 25 (30?) FEE PCB will be ordered today.
We have to think about conformal coating
FW: version 3.3 released by Yannick.
  Need to prepare a test/validation plan.

## Slide 8: WP3– BEE (PL)
              BEE Review Report – to be finished
              Corrections after BEE review – implemented
              NP: I have not yet seen the report on my question of unconnected pins
              Manufacturing and assembly documentation - ready

## Slide 9: WP3– BEE (Tübingen)
              Alinx modules & Dev-Boards arrived:
                1x AXU9EGB (Zynq UltraScale+)
                2x AXKU042 (Kintex UltraScale)
              Setting up the environment
              Where can we find the Firmware/Software repository for ACU9EG/Managment SoC?

## Slide 10: WP4 – PHU – LVPS First Stage
              LVPS First Stage Review Report – to be finished
              Corrections after LVPS First Stage review – implemented
              Manufacturing and assembly documentation - ready

## Slide 11: WP4 – PHU - LVPS Hub
              Designed and manufactured by external company
              Modifications to be done:
                FEE connector change
                Startup delay circuit to be modified
                New requirement is > 3.9V (was 3.8V), require a change of resistor setting
                Voltage for Peltier is 9V
                One pin changed from Peltier to GND

## Slide 12: WP4 – PHU + LVPS (Tübingen)
              FEE power connectors are replaced:
                Footprint & position optimized → no change in capacitors required
                Paste-In-Hole process: it seems you are using it on the FEE → What is your experience? → Are there any special requirements necessary?
                Pinout changed according to new design → pin #6 is now GND (was Vpeltier)
                A few optimizations still needed → but looks good now

## Slide 13: WP5 – Payload Thermo-Mechanical Structure (PTMS)
Instrument stacked in pieces:
Polarimeter will be assembled and delivered to China. RAA and PIP will be assembled on CSS
Full instrument will weigh <160kg (including RAA and adapter plate)... Weight to be updated (modules are being optimized after thermal studies)
New design under FEA simulations (see next slide)
Cable routing to RAA being discussed (unacceptable to route over CFRP Top Cover)

## Slide 14: WP5 – Payload Thermo-Mechanical Structure (PTMS)
Minimum gain:
- 60gr per module

## Slide 15: WP5 – Payload Thermal-Mechanical Structure (Steady state)
Leading to transient analyses (COLD & HOT conditions, Beta angles..)

## Slide 16: WP5 – Payload Thermal-Mechanical Structure (transient... up to 31 hours)
Latest simulations up to 31 hours...showed 3.8°C at corner and 10.5 °C at center
SiPM temperature close to the center...
SiPM temperature at a POLAR2 corner..
Need some updates according to CSU, βangle up to 65° to be accounted .. FEA ongoing by DPNC (see next slides)

## Slide 17: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 18: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 19: WP5 – Payload Thermal-Mechanical Structure (transient... at cold conditions, from CSS "extraction" )

## Slide 20: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°

## Slide 21: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°

## Slide 22: WP5 – Payload Thermal-Mechanical Structure
βangle issue: simulations at 65°
Next steps:
Apply MLI on critical surface? Like P1?... and the opposite surface when negative beta...
Check with other β angles ...see that of ISS (AMS02 example below)
Up to 45°, eclipse is around 32 minutes
ISS beta angle

## Slide 23: WP5 – Payload Thermal-Mechanical Structure

## Slide 24: WP5 – Payload Thermal-Mechanical Structure

## Slide 25: WP5 – Payload Thermal-Mechanical Structure

## Slide 26: WP5 – Payload Thermal-Mechanical Structure
Thermal analysis report to CSU
  Last iterations with various beta angles and report will be released to CSU for review (by mid August)
  To estimate the impact (sensitivity) of β angle on temperatures
  For instance:
  30° angle, giving 35 minutes nighttime
  0° angle, giving 36 minutes nighttime.

## Slide 27: WP6 – Qualification and Verification
Radiation requirements for BEE and LVPS
  Conditions by UniGe: 1kRad (10 Gray)
  Conditions by CSU: None. But test must be performed. Performance metrics decided by UniGe
2nd Roughness measurements at HEPIA (5 bars) were consistent with previous batches. Johannes will contact Scionix to understand what happened in the production.
Probe station tests will resume when the cold water circuit upgrade will be completed (beg. August).

## Slide 28: WP7 – Flight Model Acceptance
Need to contact UniBe for space qualification.
  For TV, we should prepare the list of components with their mass and outgassing properties.
  For vibration, we have to get from CSU the vibration levels during launch (considering POLAR-2 will be in a transportation box).
  Preliminary design document of the payload packaging transmitted by Jianchao.

## Slide 29: WP8 – POLAR-2 Onboard Software System
Still framing problem with ZYNQ., perhaps Tuebingen can help.
Vishal has installed vivado2025 on his computer
We received ALINX board. It boots. I tested PYNQ can run some jupiternotebooks. Will have to decide which operating system we want. I can share an ethernet connection with Tuebingen if needed.
Price for testing the firmware is 30K$ (initial cost) + 10K$ per FPGA. If we find 45k Nicolas can do it in China before end of the year. We have to find this money now!
Yannick say that reading several FEE with GPIO is possible but need some work but we will not pursue that, Best is to go to alinx board as test system in a near future.

## Slide 30: Simulations
Working on Analysis software to unify all scripts we have
  This week: finger fit routines included
  Goal: Full module characterization with a single command
Current implementation includes
  Change of positioning on CSS
  Robotic arm adapter
  Tungsten plate
Open tasks
  Impact of shadow cast by RAA
  Updated implementation of response in framework
  More cleanup

## Slide 31: ESRF
Request accepted
  15 shifts
  Beamline ID19
  Week 6 in 2026 proposed (MD day used to setup)
Tasks to complete before ESRF
  Procurement of components for 10 modules (9+1 reserve)
    Johannes placed order for PCBs and Assembly. CITIROCs to be ordered this week. CITIROCS + SiPMs to be delivered 1 month in advance.
    Mechanical structures (end cap, alu support structure, etc.)
    cables
  Wrapping 640 bars (~400 done)
  Readout (Nicolas, Dominik, Uni. Tuebingen)

## Slide 32: EQM

## Slide 33: EQM – Gantt Remarks
The DAQ system should still be added to the chart.
The FEE transportation boxes should still be added to the chart.
2 weeks of Christmas Holidays are taken into account (then if heroes are around, this will just make a nicer chart for January 26).
As soon as we have more infos on the CN7 validation, we should start ordering the PCBs (with or without conclusions on the HV problem of FEE v1, as agreed some weeks ago already).

## Slide 34: Conferences/Paper/Misc.
ICRC proceeding deadline 19/Sep (final version)
NDA writing proceeding for SPIE (about POLAR-2 in general)
More??