## Slide 2: WP3: ISCOOL Cage Relocation
Lukas Nies (SY-STI-LP)
26 / 09 / 2025

## Slide 3: ISCOOL: The ISOLDE Ion Beam Cooler-Buncher primary hardware: remains unchanged
Ivan Padora – Thesis (2007) – EDMS 1072182
Receives ion beams from HRS frontend
Accumulation, cooling and bunching through He buffer-gas collisions
Either DC or bunched beam mode

## Slide 4: ISCOOL: The ISOLDE Ion Beam Cooler-Buncher secondary hardware: to be relocated
Green HT cage including the two racks + access rack
Decabling of all machine side cables (between HT cage and primary hardware)
Recabling/Extension of cables from EN/EL and EPC
ACC-CONS request for consolidation of some of the PLCs and RF drivers (more later)

## Slide 5: Secondary hardware relocation
HV Cage
EPC and EP racks
HV Rack will move on top of RILIS cabin
EPC and EP racks (HT power supply, interlock and access, etc.) will remain in original position -> to be discussed

## Slide 6: Secondary hardware relocation
HV Rack will move on top of RILIS cabin
EPC and EP racks (HT power supply, interlock and access, etc.) will remain in original position -> to be discussed
Extra distance to be compensated by new “HT tube” design
HV Cage
HT tube through RILIS cabin
Primary hardware

## Slide 7: Secondary hardware relocation
HV Rack will move on top of RILIS cabin
EPC and EP racks (HT power supply, interlock and access, etc.) will remain in original position -> to be discussed
Extra distance to be compensated by new “HT tube” design
HV Cage
HT tube through RILIS cabin
Primary hardware

## Slide 8: High-voltage cage and tube design
Maximize cage volume and rack space with the given roof constraints
Use lightweight extruded aluminium profiles, reuse PUMA-RC6 design
Simple di-electric tube in metal sleeve (no “Boris tube” needed) -> Specs (dimensions) still to be defined
HT tube through RILIS cabin
Transformer
Insulators
Maximize racks space

## Slide 9: Updated Functional Specifications and CONS
User requirements and new insights into device operation after 15 years motivate update
New functional specs. document to be circulated for engineering check next week
Information from equipment owners required: estimation of rack space and power consumption on-platform
Basis for ACC-CONS request submitted this round

## Slide 10: Updated Functional Specifications and CONS
 | Model (Suggestion) // Comments | Quantity | Estimated Price (kCHF) |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  | 
 |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
HV CAGE RELOCATION AND PRIMARY INFRASTRUCTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cabling work off-platform | EN-EL | 1 | 10 |  |  |  |  |  |  |  |  | 9 | 3 |  |  |  |  |  |  | 
Cabling work on-platform | EN-EL, SY-STI | 1 | 5 |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 
HV Cage | SY-STI | 1 | 10 |  |  |  |  |  |  |  | 4 | 4 | 1 |  |  |  |  |  |  | 
Racks and insulators | SY-STI | 1 | 5 |  |  |  |  |  |  |  |  | 3 | 2 | 1 |  |  |  |  |  | 
Misc |  | 1 | 5 |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  | 2 |  |  | 
Total |  |  | 35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total per year |  |  |  |  |  |  |  |  | 20 |  |  |  | 13 |  |  |  | 2 |  |  | 
RF DRIVER SYSYEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
400W RF Amplifiers | online + offline (spares), commercial | 6 | 110 |  |  |  |  |  |  |  |  |  | 50 | 60 |  |  |  |  |  | 
Transducer box | online + offline (spares), in-house (SY-RF) | 6 | 15 |  |  |  |  |  |  |  | 5 | 5 | 5 |  |  |  |  |  |  | 
RF generators and digital scop | offline (spare) | 1 | 5 |  |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  | 
Misc |  | 1 | 5 |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 2 |  |  | 
Total |  |  | 135 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total per year |  |  |  |  |  |  |  |  | 12 |  |  |  | 121 |  |  |  | 2 |  |  | 
POWERLINE CONVERTERS AND FAST SWITCHES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Transformer and interfaces | online + offline (spare) | 2 | 35 |  |  |  |  |  |  |  | 2.5 | 5 | 12 | 12 | 3.5 |  |  |  |  | 
Switches | online + offline (spare) | 6 | 4 |  |  |  |  |  |  |  |  |  | 2 | 2 |  |  |  |  |  | 
ISEG -20kV module | ISEG EHS-42-200n | 1 | 6 |  |  |  |  |  |  |  |  |  | 3 | 3 |  |  |  |  |  | 
Fast voltage amplifiers | EDA-01892, online + offline (spare) | 6 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 |  | 
Fast voltage amplifiers, crate | online + offline (spare) | 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  | 
DSS Ressources, 4 weeks |  |  | 10 |  |  |  |  |  |  |  |  | 2.5 | 7.5 |  |  |  |  |  |  | 
Misc |  |  | 3 |  |  |  |  |  |  |  |  |  | 1 | 1 |  |  | 1 |  |  | 
Total |  |  | 67 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total per year |  |  |  |  |  |  |  |  | 10 |  |  |  | 47 |  |  |  | 10 |  |  | 
Total per Q |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total per year |  |  |  |  |  |  |  |  | 42 |  |  |  | 181 |  |  |  | 14 |  |  | 
FULL TOTAL |  |  | 237 kCHF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
35 kCHF
If funded would relief some stress on the RILIS budget

## Slide 11: Tentative work schedule WP3
 |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  |  | 2028 |  |  | 
 |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Tasks |  |  |  | Teams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Lockout of mains power, lockout of HT PLC |  |  |  | EN-EL, EPC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Removal of secondary equipment on HT platform |  |  |  | EPC, RF, STI, EP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Removal of off-platform seconday equipment and racks |  |  |  | EPC, STI, EP, EN/HE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Removal of racks and any remaining secondary hardware |  |  |  | STI, EN/HE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Decabling HT platform <-> ISCOOL |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Removal HT cage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design freeze HT cage |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HT cage procurement |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Construction of new platform and lab |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Recabling secondary eqipment |  |  |  | EPC, EN-EL, STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation off-platform equipment |  |  |  | EPC, STI, EP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cage assembly |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation and cabling of transformer, HT platform, HT tube |  |  |  | STI, EPC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HV conditioning 1 |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Installation of on-platform equipment |  |  |  | EPC, RF, STI, EP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Recabling secondary eqipment |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Powerwing seconday equipment |  |  |  | EPC, RF, STI, EP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HV conditioning 2 |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Commissioning with stable beam |  |  |  | STI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |