## Slide 1: Optimizing the Distributed Computing System via Curriculum Reinforcement Learning
Redwood Project October General Meeting
Shengyu Feng (CMU), Yiming Yang (CMU)

## Slide 2: Optimizing the Distributed Computing System via Curriculum Reinforcement Learning (CMU Team)
Summary of progress
2025/08, AlterMILP (non-learning) accepted by FGCS
2025/05-09, learning approach on data management system data
Simulated data
Data (ATLAS, PanDA, Rucio, 2025/04/01-15) provided by Kuan-Chieh
Processing method from David’s AI Surrogate Model paper
Develop our version of simulated environment for model training ✅
Disable the data cloning and cache due to missing data ⬜
Formulation and challenges
Formulation: Partially observable Markov decision problem
Objective: optimize the throughput of the system
Challenge 1: Partial observable (needs prediction)
Challenge 2: Sparse rewards (long horizon & delayed rewards)
Technical Approach: Curriculum Reinforcement Learning (CRL)
First train the model to predict the job workload ✅
Then optimize the one-step makespan as a surrogate objective ✅
Finally train the model to maximize the long-term throughput ⬜
Current results: slightly outperforming the baselines on the above data
Fig3. Comparison between (current) CRL and baselines
Fig2. Overview of the neural classifier used in CRL
Fig1. Stats of the simulated environment

## Slide 3: Future Steps (Next 6 months)
Target venue (one of the following)
ICLR AI4S workshop (early 2026, TBD)
ICML main track (Jan., 2026)
Action items
⬜ Finish the long-time horizon training of CRL on the current data/simulator
⬜ Integrate the CGSim environment (from Sairam) for testing
⬜ Add the data cloning and cache if new data is provided