## Slide 1: PICv2 Status
Powering Meeting
Alain Antoine (TE-MPE-MI)
24 September 2025

## Slide 2: Status Update
BIS Test Mode
  UNICOS software with BIS test mode released by BE/ICS
  Test with Christophe successfully passed
Procurement
  Pre-assembled crates (Shroff): imminent delivery
  Siemens DI/DQ cards: ordered, ~6 weeks delivery
  Patch panels Burndy connectors: ordered, delivery date pending
  Pending:
    CPU: to be ordered early 2026 (after power selection agreement with BE/ICS)
    IM 155-5 Multifieldbus interface: postponed, Siemens update expected early 2027
Design
  Patch panels revised
Documentation
  The Hardware Interfaces Between Powering Interlock System, Power Converters and Quench Protection System 3.1 [EDMS 368927]
    Approval round completed – comments pending integration

## Slide 3: Remaining Hardware Development
Idea to create a C2 Faceplate for the card C.
Reminder:
  CIPMC/:
    Integration design (mechanical)
    Choice of the power of the Main and Red CPUs
  CIPSA & CIPSB:
    Rear panels for the passage of RJ45s (PROFINET), I/O spares and +24 VDC
  CIPST:
    Rear panels for the passage of RJ45s (PROFINET) and +24 VDC
  Patch Panels (Concentrator)
    Specifications completed – under review
    Design to be completed by end of the year

## Slide 4: Bat. 28.1 Storage
The PIC pallet location has been released by moving the Siemens cards to the PIC cupboard.
Issue
  Total PIC pallet locations required fro Schroff: 17; currently available: 16.
  After placing the Siemens order, an additional 3 pallet locations are estimated to be needed.
Possible solution:
  Some cards and connectors will be stored in the PIC cupboard.
  Three unused spaces on the BIS shelf could be allocated to the PIC, which should be sufficient.