## CERN shifts 2025 summer
			MAY					JUN					JUL
	name\date		19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9
	event					PSD					Neutrino					Oxygen
INR	Morozov S.
	Volkov V.
	Karpushkin N.
NCBJ DBP	Maksiak Bartosz
	Balkova Yulia
	Czopowicz Tobiasz
	Pszczel Damian
NCBJ DTJ	Świderski Łukasz					1	1	1	1	1					5
	Bielewicz Marcin			1	1	1	1	1	1	1	1					14
	Szewiński Jarek			1	1	1	1	1	1	1	1					1	1	1	1	1	1	1	1					31
	Rybka Dominik					1	1	1	1	1	1	1	1					1	1	1	1	1	1	1	1					22
	Kowalski Tomasz					1	1	1	1	1	1	1	1					18
	Piotr Mazerewicz					0
	Adrich Przemysław					0
				days	CHF/day		total CHF
		0					90	140		12600

## action plan
Mon	14		new cable test @lab (MB, SM/NK), soldering cables+boards @lab (MB, TK, SM/NK)
Tue	15
Wed	16	PSD calibr.	FPSD position calibration with markers (SM/NK, PM), cable+boards mounting @FPSD: 90channels, 6 boards (MB, TK, SM/NK), FPSD energy calibration with muons and protons (SM/NK, MB)	10pm-8am
	17		FPSD position calibration with proton beam (SM/NK, PM/MB)	10pm-8am
	18
	19		MPSD calibration with muons and protons	10pm-8am
	20		MPSD calibration with muons and protons	10pm-8am
	21	pi+C	data acquisition, no FPSD contribution, no access
	22
	23
	24
	25
	26
	27
	28	PSD calibr.	FPSD+new_cable test with protons (TK, SM/NK)
	29
	30
	31
	1	PbPb run

			SM: Sergey
			NK: Nikolay
			MB: Marcin
			TK: Tomek
			PM: Piotrek

## CERN shifts 2025 autumn
			OCT					NOV					DEC
	name\date		19	20	21	22	23	24	25	26	27	28	29	30	31	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	1	2	3	4	5	6	7	8	9
	event					pp					setup				PbPb
INR	Morozov S.
	Volkov V.
	Karpushkin N.
NCBJ DBP	Maksiak Bartosz					0
	Balkova Yulia					0
	Czopowicz Tobiasz			1	1	1	1	1	1	1	1	1	1	1					11
	Pszczel Damian					0
NCBJ DTJ	Świderski Łukasz					1	1	1	1	1	1	1					7
	Bielewicz Marcin					1	1	1	1	1	1	1					1	1	1	1	1	1	1			14
	Szewiński Jarek					1	1	1	1	1	1	1	1	1	1	1					1	1	1	1	1	1	1	1			30
	Rybka Dominik			1	1	1	1	1	1	1	1					1	1	1	1	1	1	1					17
	Kowalski Tomasz					1	1	1	1	1	1	1	1					13
	Piotr Mazerewicz					0
	Adrich Przemysław					0
				days	CHF/day		total CHF
				92	140		12880