## Slide 1
5 laser beams
1 billion positrons
≈500 million antiprotons
50 collaborators

## Slide 2
AEgIS 2025: Jan-May (+June +July)
Starting up
True transition of technical coordination – overall it went remarkably smooth
Huge success on the heat shield
Thanks to Stef, who designed and finished a new target holder from scratch (still … +1 month)
We missed an important WP: the anti-sun installation +1 month
Delay of 2 month - was well used for cryogenic Ps laser cooling experiments with a new Ps target and OPHANIM + pbar statistics

## Slide 3
AEgIS 2025 – AEgIS Collaboration Meeting
April: Trento Collaboration Meeting

## Slide 4
AEgIS 2025 – August speed run
August
CapbarA experiments
OPHANIM experiments with pbars
Commissioning of the BOREALIS source
Commissioning of PPT-chamber (FANTASIA)
Ps tests in 1T and 0.2T
Laser steering and testing in the 1T
Relocation of the Torun ion source to CERN

## Slide 5
AEgIS 2025 – Partial warm-up
September
We diagnosed insufficient UHV vacuum in both the 1T/5T due to:
limited differential pumping during OPHANIM and CapbarA tests
procedural problem during cooldown with TP3
leaks in the antisun region
We cleaned up to water evaporation!
Installation and naming of the MEDUSA gravity module:
MoirE Deflectometer for Universality and Symmetry of Antimatter
The MoirE Deflectometer for Universality and Symmetry of Antimatter (MEDUSA) Gravity Module
Congratulation to the MEDUSA team!

## Slide 6
AEgIS 2025 – Final leap
Oct-Dec
No functioning Ps-target
Rapidly deteriorating UHV vacuum again (leak?)
First results with BOREALIS
Progress with FANTASIA
Commissioning of MEDUSA with antiprotons
A force measurement with MEDUSA on antiprotons
Development of procedures for an Hbar beam
Positron catching and cooling in 5T and transport to 1T
Three-body recombination