## TAXN_Equipment
Equipment name / MTF link |  | Slot name
| HCTAXN1001-CR000001 | TAXN.4R1
| HCTAXN1002-CR000001 | TAXN.4L1
| HCTAXN5001-CR000001 | TAXN.4R5
| HCTAXN5002-CR000001 | TAXN.4L5

## DIMR-WDP_overview
DIMR 8032176/1
WDPs | IMPACTs | Steps | Tasks | Owning / Contributing Groups | Reference Work Dose estimation | Duration / Time estim. (minutes) | Coll. dose [person.µSv] | Ind. dose max. [µSv] | Total coll. dose [person.µSv] | Total ind. dose max. [µSv] | Comments
|  | 10 | Phase 1) Pre conditions for the removal of the TAN |  | June/July 2025 - 2 weeks cool-down |  |  |  | (all units) | (all units)
tbd | SY-BI team | 11 | BRAN detectors to be removed (incl. cabling) - lids to be inserted | SY-BI | - reference YETS dose registration | 5 | 6 | 3 |  |  | - decabling only, BRAN removed by ZDC+EN-HE team
HSE-RP expert | ATLAS ZDC team | 12 | ZDC detectors to be removed (incl. cabling) - lids to be inserted | ATLAS / ZDC collaboration | EYETS24-25: IMPACT 246601 (10 weeks of cooldown after ion run) |  | 330 | 57 | 330 | 57 | - Confirm: IMPACT concerned 2 TANs, - Apply correction factor YETS 24-25 --> LS3
HSE-RP expert | CMS ZDC team | 13 | ZDC detectors to be removed (incl. cabling) - lids to be inserted | CMS ZDC collaboration | EYETS24-25: IMPACT 242812 (8.5 weeks of cooldown after ion run) |  | 375 | 88 | 375 | 88 | - Confirm: IMPACT concerned 2 TANs, - Apply correction factor YETS 24-25 --> LS3
CMS ZDC team | CMS ZDC team | 14 | IP5 TANs only --> mini-cranes have to be removed | CMS ZDC collaboration | [6 empty] | - LS3 procedure available (Dragoslav-Laza Lazic )
ATLAS+CMS ZDC team | Realized by ZDC teams | 15 | Survey equipment have to be removed | BE-GM
DIMR 8031879/1 | TE-VSC - LSS1 & LSS5 | 16 | Insulation jackets have to be removed | TE-VSC
|  | 20 | Phase2) TAN disconnection, removal and transport to UX65 |  | Oct./Nov.2026 - 3 months cool-down
DIMR 8031879/1 | TE-VSC - LSS1 & LSS5 | 21 | TAN disconnection | BE-EA,HSE-RP,TE-VSC |  | 1 day
WDP EN-HE | EN-HE | 22A | IP1 TANs removal, transport to UX65 (via pt.2 + surface to SX6) | EN-HE,HSE-RP | WdP - Maria: Estimation of 1 TAN IP1 | 5 days | 500 | 160 | 1000 | 320 | - Use of procedure TAN installation - EDMS 716474
WDP EN-HE | EN-HE | 22C | IP5 TANs removal, transport to UX65 (tunnel transport) | EN-HE,HSE-RP |  |  | 560 | 150 | 1120 | 300
24
WDP 4542/1 | Activity:252450 | 30 | Phase 3) TAN disassembly, modification and TAXN assembly (TDE bunker - SX6) |  | April - Sept. 2028 - 24 months cool-down
|  | 31 | TAN disassembly (storage of obsolete components in dedicated compartment) | BE-EA, EN-HE; HSE-RP
|  | 32 | Modification of TAN U-shielding (drilling of seats for fiducials) | BE-EA, HSE-RP, BE-GM
|  | 33 | TAXN assembly | BE-EA,HSE-RP,TE-VSC
|  | 34 | TAXN tests | BE-EA, BE-GM, EN-CE, TE-VSC
WDP EN-HE | EN-HE | 35 | TAN from UX65 to SX6-TDE + TAXN back to UX65 | EN-HE,HSE-RP | WdP - Maria: Estimation of 1 TAN IP1 |  | 36 | 10 | 144 | 40
|  | 36 | Waste treatment (obsolete components) | BE-EA, EN-HE; HSE-RP
37
|  | 40 | Phase 4) TAXN logistics and installation in LHC (from UX65 to IP1/IP5) |  | Dec.2028 - April 2029 - 32 months cool-down
HSE-RP expert | In work EN-HE | 41 | IP1 TAN surface transport to shaft (TBD)
|  | 42 | TAN transport to underground and tunnel position (IP1 / IP5 go through LHC tunnel)
DIMR 8031879/1 | TE-VSC - LSS1 & LSS5 | 43 | TAXN connection | BE-EA,EN-CV,EN-EL,HSE-RP,TE-VSC |  | 3 days
tbd | In work BE-GM | 44 | TAXN alignment | BE-EA,BE-GM,EN-CV,EN-EL,HSE-RP,TE-VSC |  | 2 days
tbd | SY-BI team | 45 | BRAN detectors installation and tests | SY-BI
problem funding | ATLAS ZDC team | 46 | ATLAS ZDC detectors installation and tests | ATLAS ZDC collaboration
probably not in LS3 |  | 47 | ZDC detectors removal prior to p-p run | ATLAS ZDC collaboration
problem funding | CMS ZDC team | 48 | ZDC detectors installation and tests | CMS ZDC collaboration
probably not in LS3 |  | 49 | ZDC detectors removal prior to p-p run | CMS ZDC collaboration
From: Safouane El-Idrissi <safouane.el.idrissi@cern.ch> Sent: Tuesday, 7 October 2025 14:29 To: Oliver Boettcher <Oliver.Boettcher@cern.ch> Subject: TAN-to-TAXN - wrap-up situation DIMR + next steps
Salut Oliver,
Comme discuté hier lors de notre entrevue, tu trouveras ci-dessous les doses intégrées lors du retrait des ZDC Atlas et CMS pendant le EYETS24-25 :
ZDC ATLAS :
57 µSv ind. max / 330 pers.µSv collective
10 weeks of cooldown after ion run
IMPACT 246601
ZDC CMS : 88 µSv ind.max / 375 pers.µSv collective
8.5 weeks of cooldown after ion run
IMPACT 242812
Pour le retrait du Mini Crane CMS, la date de retrait est prévue pour janvier 2027, ce qui implique que les dose rates sont négligeables car tous les éléments chauds auront été retirés (TAN, collimateurs, QRL).
Bonne journée,
Safouane.