## Slide 1: LS3 constraints and planning
Bastien Rae on behalf of the BE-EA and NACONS Coordination Team

## Slide 2: LS3 Master Schedule
Lates version of the master schedule
Planning still under construction.
Restart phase (HWC, BC, ..) to be precisely define
The dates in this presentation are still draft and have to be validate (beginning of 2026)

## Slide 3: East Area constraints
CLOUD
  CV dismantling work for new ventilation
    From 05.10.26 to 30.10.26
    Can be 1 month longer if the panels contain asbestos (to be check during YETS25-26)
  EN-EL + RP no constraints

## Slide 4: North Area Constraints
MADMAX and RADES
  EL :
    Work on CRYO from February 2028 to beginning of August 2028
    Work on BA81 false floor (no Power converter)
      Oct 26 – Nov 26
      March 27 – July 27
  CV : not possible during CT2 work currently planned: Sept 26 – Oct 27 Sept 27 – June 28
  CRYO : depending on other services + resources
Neutrino Platform :
  EL : TBC if the CRYO work of 2028 impact the Neutrino Platform
  CV : Ok with local chiller
  CRYO : depending on other services + resources

## Slide 5: North Area Constraints
CMS GEM Test.
  EN-EL : Work on BA81 false floor (no Power converter)
    Oct 26 – Nov 26
    March 27 – July 27
  CV : not possible during CT2 work currently planned : Sept 26 – Oct 27 Sept 27 – June 28
GIF++ :
  EL : no long interruption foreseen
  CV : ok with local chiller

## Slide 6: North Area Constraints
AMBER :
  EN-EL : Work under BA82 false floor (No power converter SM1/SM2)
    Dec 26 – Jan 27
    May 27 – Oct 27
  CV : not possible during CT2 work currently planned : Sept 26 – Oct 27 Sept 27 – June 28
  CRYO : depending on other services and resources