## Slide 1: APT progress and resource discussion
HS; 9th March 2012

## Slide 2
Budgets 2012
Summary: |  | 
 | Requests | allocation 1st January
General | 3718 | 4500
Beam Dynamics | 500 | 300
Experimental Verification | 6620 | 3500
x-band activities | 6071 | 3200
CTC | 8117 | 4500
Project Implementation | 260 | 260
 | 25286 | 16260
Requests by activity from december 2011 (in KCHF):
Preliminary allocation to activities as shown; inside the activities breakdown pro-rata of spending 2011.
Implemented by DG-RPC in February 2012
Will allow us to work until we have finished the planning exercise.

## Slide 3: CLIC planning exercise covers 2012-2017 boundary condition: Constant P and constant M
Bottom-up proposals of work-packages: Done first half of 2011  150% of M needed, 200% of P needed
What can be made through collaborations? : 3+4 November meeting  M: 5 MCHF; P: up to 800 FTE = significant contribution; will need a lot of careful arrangements, contracts....; aim to integrate into our planning for CLIC workshop in May 2012...will not be completed by then, but we should aim to give first formal feedback!
Concentrated on CERN planning for MTP2012 exercise in February 2012: - CLIC requests of all work-packages summarized for all concerned group leaders by members of the CLIC study: Done in Dec/January. Many Thanks for the effort! - evaluation and resource loading by the GLs: mainly done; so far only looked at data from two major groups: EN-MME and BE-RF General impression: Very serious effort to satisfy the needs of CLIC, natural tendency to fully support ongoing activities, new activities “on hold” due to lack of resources. - documentation in APT: Scheduled for mid February 2012, but delayed for “technical” reasons, now scheduled for 26th March
Prioritization and “making the planning fit” exercise on 26th and 28th March by CASC team

## Slide 4: What can be done?
The resources ceiling in M and P is re-inforced everywhere. No point in trying to get more.
There is almost no work-package proposal, which foresees the ramp-down of a given activity; all people want to continue the effort or to do more.
1) Keep discussing, decide nothing, continue the present activities... ????
2) Entrust complete work-packages to collaborators: no obvious candidates
3) Stop present activities and increase/start effort on others: ....within the skills of the “liberated” people
... Some possibilities in order to stimulate the discussion: a) ramp-down of CTF3 (+ no consolidation)  CLIC0 injector
b) Distinguish between technology developments for CLIC physics machine (long term) and CLIC0 (medium term): Cut long term developments, re-invest into medium term: examples: Freeze module BPMs, stop after first results of profile measurements, re-invest into CLIC0 diagnostics
No second generation of TBM, no cost optimizations, no industrialization: re-invest people into x-band structure production and the design/construction of test-stands
Ideas of everybody needed. Please bring your ideas forward to CASC members