## Slide 1: Future Disk-Only Storage Project
Shaun de Witt
GridPP Review 20-June-2012

## Slide 2: Motivation
Always good to be aware of options
But now in particular:
  Castor no longer used for disk only storage at CERN
    There is some ‘risk’ around future support
    Starting to hit operational limits
    Castor as we use it is constraining storage purchases
  Many new options maturing

## Slide 3: Motivation
CASTOR Issues
  Flexibility
    Minimum deployment size = 1 disk server
    Cannot use very large storage servers (> ~40TB)
  Operational Limitations:
    Slow access times
      Lowers job efficiencies, time consuming to drain servers
    Not fault tolerant
    Database is SPF
    No hotfile replication limits performance
  Complex to administer – requires expertise & considerable staff effort
  Licensing costs (Oracle)

## Slide 4: Pitfalls
CONSIDERATIONS
Any replacement:
  must be simple and require less operational manpower than existing solution
  Should be more fault tolerant
  Should have wider user base, long term support (open source?)
  Should perform better
Minimal effort for development
  Can’t write another SRM front end
  But can contribute to development
Watch out for ‘hidden’ licensing costs

## Slide 5: Status and Next Steps
Initial set of requirements gathered
Candidates identified
Undergoing paper review
Select 4 for further testing
  Some tests already available from another project
  Need to spend more effort on testing
  Rank solutions
Deploy small scale preproduction set-up for internal testing
Open to VOs for testing
Deploy into production
  Architecture will be based on final solution

## Slide 6: Timeline
Shortlist candidate technologies
  July 2012
Set up test beds
  Aug. 2012
Complete internal testing and report
  Dec 2012
Deploy preproduction service
  Feb 2013
Open for VO testing
  Mar 2013
Deploy for production
  Oct 2013

## Slide 7: Risks and Limitations
Limitations:
  No plan currently to migrate data in CASTOR disk to new service
    Either let VOs do it or let disk-only files ‘age out’ of CASTOR
  Need an SRM until new version of FTS is available
    Storm/Bestman may be used if we don’t choose a HEP solution
Risks:
  First choice selection may show problems during VO testing
    Rank solutions, use experienced gained in setting up test systems to deploy second choice system
    Some slippage built in to plan, but not much
  Getting glue information to CIP is difficult
    Need to see what others do and how they do it