## Slide 1: EuCard-WP7-HFM 10th Collaboration Meeting
Fresca2 Dipole construction status, assembly and tooling
J.C Perez
on behalf of Fresca2 collaboration team

## Slide 2: Outline
Fresca 2 components delivery status
Assembly procedure and tooling
Traces fabrication
Heat treatment furnace
Vacuum Impregnation system
Next steps
Conclusion

## Slide 3: Components delivery status
Price inquiry for the structure launched in September 2011
The order placed in November 2011 has been split between 3 European companies
  Cold-mass to Aratz (Spain)
  Coil-pack (& dummy coil) to Boessenkool (Netherland)
  Axial compression system to Mectalent (Finland)
All components have been delivered and accepted

## Slide 4: Assembly procedure
Coil layer 1-2
Coil layer 3-4
Fiber glass cloth filler

## Slide 5: Gap impregnation
2 facing surfaces of the coils will be mold released
Gap between coils will be filled with 0.9 mm fiber glass cloth
Impregnation of the fiber glass using the coils as cavity
This will guarantee a perfect contact between the 2 coils
This technique will allow to separate the coils in case of failure of one coil
Tests performed at CERN polymer laboratory confirm the feasibility

## Slide 6: Coils assembly sequence
Coil lifting tool
Coil rotation tooling

## Slide 7: Coil pack assembly
Horizontal pads
Coil-pack assembly lifting tool
Coil-pack assembly
Coil-pack rotating tooling
Conceptual design of all lifting tools is ready and price offers received. The official order will be placed end of September. Delivery scheduled for November 2012.

## Slide 8: Shell and Yoke assembly
Sliding the aluminum shell
The 2 half yokes will be aligned with no gap in between
A CERN standard rotating device will be used to turn the magnet

## Slide 9: Real shell and yoke assembly (1/2)

## Slide 10: Real shell and yoke assembly (2/2)
½ yokes assembly
Instrumented Shell
Sliding the shell
Guiding system
Assembly completed

## Slide 11: Shell pre-loading
Two bladders will be used to push the ½ yokes towards the shell inner radius to allow gap keys insertion
Standard hydraulic jacks can be used instead of bladders to perform this operation
Bladders have been produced @ CERN

## Slide 12: Sliding the coil pack in the structure
The assembled parts will be rotated to horizontal position
The coil-pack will be pushed into the yoke aperture
Pumping bladders & insertion of keys

## Slide 13: Pictures of the coil-pack

## Slide 14: Axial compression system

## Slide 15: Magnet in the cryostat

## Slide 16: Aluminium dummy coil assembly
The first mechanical assembly will be performed using aluminum blocks replacing the real coils
This will qualify the support structure, the assembly and loading procedure and validate the FEM
6 stations will be placed on the shell mid-plane and 4 at 45° (20 gauges). See detailed presentation from J.E. Muñoz Garcia
The aluminum dummy coils will be instrumented with 14 strain gauges stations measuring along azimuthal and longitudinal direction
Axial roads will be instrumented (longitudinal direction)
The way to cool-down the structure to 77 K in LN2 is under investigation

## Slide 17: Mechanical tests @ 77 K
An existing cryostat will be used to cool-down the structure to 77 K
A dedicated structure has been designed to support the instrumented mechanical structure (delivery expected October 2012)
Shell, yokes, aluminium dummy coils and longitudinal rods will be equipped with temperature sensors
During cool-down the temperature gradient on different pieces will not exceed 20 K
A dedicated cooling control will be developed

## Slide 18: Coils instrumentation and protection
Each double pancake will be equipped with 2 traces
New traces have been designed and will be produced at CERN
Each coil layer will be protected by 2 independent quench-heater circuits
Voltages across the coil will be monitored thanks to 9 Vtaps per side

## Slide 19: Heat treatment furnace
The heat treatment furnace ordered to GERO will be commissioned at the contractor premises by end of September 2012
Delivery to CERN is scheduled in October 2012

## Slide 20: Vacuum impregnation system
The acceptance tests for the new vacuum impregnation tank will be held in Spain in October 2012
The system will be installed in 927 laboratory and commissioned in November 2012

## Slide 21: Next steps
Pre-load shell-yoke sub-assembly and check gauges
Coil pack assembly with pressure sensitive paper
Rotation of shell-yoke
Coil pack re-assembly and insertion in the shell-yoke
Bladder operation
Axial loading operation
Cool-down to 77 K

## Slide 22: Conclusions
All structure components have been delivered to CERN
Shell, rods and aluminium dummy coil are being instrumented
The shell has been slid around the yoke
First mechanical assembly using aluminium dummy coils planed in October 2012
The structure to support the magnet in the cryostat for cool-down using Ln will be delivered in November 2012
First cool-down of the structure to 77 K scheduled for end 2012
The heat treatment furnace will be operational in October 2012
The vacuum impregnation tank will be operational November 2012
First set of traces scheduled for December 2012

## Slide 23: Fresca2 Collaboration Team
CEA/Saclay:
  M. Durante, P. Manil, J.F. Millot, J.M. Rifflet, F. Rondeaux,
CERN:
  P. Ferracin, G. de Rijk, E. Fornassiere, J. Humbert, A. Milanese,
  L. Oberli, M. Timmins, G. Villiger , TE/MSC-MDT Section
Thanks for your attention