## Slide 1
AIDA Governing Board meeting
12 April 2012, INFN-LNF
Overview of the use of resources by M18 and the financial situation of the beneficiaries
S. Stavrev, CERN
Administrative Manager

## Slide 2
Content
2
Payments of EC funding to the Consortium
Principles of financial reporting to the EC
Use of resources by M18 per Work Package
Use of resources by M18 by the beneficiaries
Partners that seem to over-use or under-use resources by M18
Special case of STFC

## Slide 3: EU payments for AIDA
Pre-financing = 60 %, of which 5% withheld (for FP7 Guarantee Fund, to be reimbursed at the end).
Effective pre-financing = 55% of the 8 M€ of which 60% was paid (pro-rata to project share) to each participant at the start, and the other 40% were distributed after the 1st Annual GB meeting (or after the M18 reporting).
Second EC payment: at M(18+3+5) = reimbursement of costs for the first Reporting Period ~ 24%
Third EC payment limited by 85% of the 8 M€: at M(36+2+3) ~ 6%
Final EC payment (10% + 5%) – after the Final Report is approved
M1
M18
1st Reporting Period
55%
24%
M36
2nd Reporting Period
M26
M48
3rd Reporting Period
6%
M42
10%
M3
5%
5%
EC funding for AIDA = 8 M€

## Slide 4: EU payments for AIDA
Note: the fact that the Consortium has received ~ 80% of the EC funding already does NOT mean that the corresponding resources have been used and justified.
EC funding to beneficiaries
Chart: % of EC contribution to be paid after P1 report, including the pre-financing
| CERN | OEAW | UCL | ULB | INRNE | IPASCR | CEA | CNRS | DESY | KIT | MPG-MPP | UBONN | Wuppertal | NTUA | MTA KFKI | TAU | Weizmann | INFN | VU | FOM | UiB | AGH-UST | IFJPAN | JSI | CSIC | UB | UU | Ulund | UNIGE | RHUL | STFC | UCAM | UNIGLA | UNILIV | UNIBRIS | UOXF | USFD | UNIMAN
% of EC paid | 84.02 | 85 | 68.1 | 55 | 79.19 | 65.56 | 83.12 | 85 | 74.81 | 85 | 85 | 85 | 84.83 | 85 | 75.29 | 85 | 85 | 85 | 85 | 75.46 | 70.1 | 56.02 | 85 | 85 | 85 | 85 | 57.19 | 85 | 70.01 | 63.33 | 35.48 | 58.46 | 100 | 59.4 | 85 | 55 | 79.7 | 70.1

## Slide 5: EU payments for AIDA
EC funding for AIDA (8 M€) ~ 31% of the full costs (26 M€).
Special agreement with the EC to apply “partial cost reporting”, i.e. to report officially to the EC only a fraction of the full costs, sufficient to justify the EC contribution.
This allows flexibility for the partners to select which costs to report, and at the level of the consortium AIDA has to justify (as minimum) 13-14 M€ to receive the 8 M€ from the EC.
Simplification in the financial reporting and verification for the beneficiaries, for the Coordinator, and for the EC.
This cost reporting model is not mandatory: some partners still select or prefer to report their full costs.
Financial reporting to the EC
At M18 (end of P1):
Full estimated costs of ~ 9 M€
Costs reported to the EC ~ 6 M€, of which 1.9 M€ claimed for reimbursement

## Slide 6
Use of resources by M18 per WP
6
Normalized full costs (including matching funds and overheads)
WP3 (under-spending), where the first year was focused on the definition of the programme of work, and most activities started in Y2 only;
• WP4 (over-spending), where more man-power than foreseen will be used;
• WP7 (over-spending), where more local staff has been necessary.

## Slide 7
7
Normalized full costs (including matching funds and overheads)
Over-spending at M18:
MPP (man-power): using mainly PhD students (low cost)
NTUA (man-power): using much more man-power than foreseen (a few p-ms only)
TAU (man-power and budget): using much more man-power than foreseen (additional matching funds)
Weizmann (man-power): using much more man-power than foreseen (additional matching funds)
IFJ PAN (man-power): using much more man-power than foreseen (additional matching funds)
UNIGLA (man-power and budget): terminated; used much more resources than committed.
MTA KFKI (man-power and budget): terminated (just 1 p-m)
Use of resources by M18 per beneficiary 1/2

## Slide 8
Use of resources by M18 per beneficiary 2/2
8
Normalized full costs (including matching funds and overheads)
Under-spending at M18:
IPASCR: will ramp up activities in P2
FOM: will ramp up activities in P2
UiB: delayed recruitment, issue with matching funds
AGH-UST: will ramp up activities in P2.
UU: will ramp up activities in P2
UNIGE: will ramp up activities in P2
STFC: special case
UNIMAN: partner as of M13 only

## Slide 9
Special case: STFC 1/3
9
Expected commitments of STFC in AIDA (following withdrawal from WP4):
At present, STFC’s technical contribution to WP2 and WP3 appears limited – some activities in WP2; WP3 unclear.
STFC is a task leader of Task 8.4 in WP8. After a slow start, task activities are now progressing.
Work-package | Man-power | Full costs | EC contribution
WP2 | 38 p-m | 457 k€ | 77 k€
WP3 | 15 p-m | 188 k€ | 45 k€
WP8 | 54 p-m | 787 k€ | 250 k€

## Slide 10
10
At M12, STFC did not provide the required Internal Resource Utilisation Summary
At M18 (P1 reporting), STFC did not provide the required Internal Resource Utilisation Summary
At M18 (P1 reporting), STFC reported zero costs and claimed zero costs to the EC (official Financial Statement)
Despite several attempts, the management team has not been able to obtain from STFC any information about the status of the resources used so far in WP2, WP3 and WP8.
Special case: STFC 2/3

## Slide 11
11
Recently, STFC has made the following statements
Their commitments and man-power (53 p-m) to WP2 and WP3 remain as foreseen;
Their commitment to WP8 deliverables remain. However, they will not be able to provide the necessary matching funds for the committed man-power (54 p-m).
A few months ago, the Task leader of 8.4 was considering re-allocating ~ 100 k€ EC funding to other partners in the task (WP).
Recently, STFC have changed their mind and would like to keep and use the EC funding in WP8.4 for performing irradiation tests on epoxies.
Main principle of AIDA funding: each partner has to provide the necessary matching funds (40-60% of the full costs on average) in order to receive and use the EC funding.
Special case: STFC 3/3

## Slide 12
Proposal to the Governing Board (subject to “electronic” voting)
12
The principle of AIDA funding should be applied to STFC without exception.
The management team to inform STFC that in case they will not be able to provide the necessary matching funds in WP8, they should estimate the fraction of EC funding which will remain “available” and should make a proposal for re-allocation of this funding to other partner(s) in the task (WP) a.s.a.p.
At the latest at the time of the P2 reporting (M36), STFC has to provide an estimate of the resources used since the start of the project for WP2, WP3 and WP8.
In case of evidence that the resources in WP2 and WP3 have not and will not be used as planned, part of the EC funding for STFC may be allocated to other partner(s) in those WPs.
AIDA Governing Board meeting, 12 April 2012