## Slide 1: LIU Project Timeline
2012
2015
2016
2017
PSB-PS transfer 1.4 GeV  2 GeV
Linac 4 ready
PSB H- injection could be available
2013
2018
Chamonix 2012
SPS aC coating, 200 MHz power upgrade completed
LS1 for injectors
LS2 for injectors
2019
Injectors commissioned
2014

## Slide 2: LIU Project Timeline
2012
2015
2016
2017
2013
2018
LS1 for injectors
LS2 for injectors
2019
2014
01/2016 Stripping foil and instrumentation test stand during L4 beam reliability run (BCC 18/10/2012)
07/2016 Start complete H- injection region “montage à blanc” assembly .
12/2016 all hardware components of the injection region should be available and “ready for installation” in PSB, should the need arise.
W.W – 11/10/2012 LIU PSB Meeting 87
Baseline start of installation in the PSB is beginning of LS2 (present assumption for this is January 2018).
The production of ancillary equipment, like power converters, control systems, etc., shall also follow this planning.