## Slide 1: BI Outlook for 2013-15 BI Day 2012
Based on latest (last Monday) feedback from EN/EL
XXX
XXX
XXX
As foreseen originally
Partially ‘As foreseen originally‘
Postponed

## Slide 3: LINAC4: We will install and commission L4 beam instrumentation (BPM, BLM, BCT, Grids, scanners…) during LS1 following project progress
L4 Beam Instrumentation

## Slide 4: LEIR [Consolidation]: LEIR ECool collector exchange + replacement of the cathod.
L4 Beam Instrumentation
ECool

## Slide 5: L2/3/PSB/PS [Renov]: SEM electronics will be renovated all over CPS complex.
L4 Beam Instrumentation
IPM
SEM

## Slide 6: L2/4 [LINAC4]: New PUs for LT, LTB and BI lines to PSB, including new electronics and SW.
L4 Beam Instrumentation
IPM
SEM
BPM

## Slide 7: L2/4 [Consolidation]: New cables for BCT around inflector zone will be installed (the BCT on L4 side of the wall will not be cabled during LS1.). PSB [LIU]: New cable for PSB slow BCT for injection watchdog will not be pulled during LS1.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT

## Slide 8: PSB Inj [LIU]: The cables for the observation monitor on H0/H- injection foil will not be pulled during LS1.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV

## Slide 9: PSB [LIU]: New cables for the new PSB orbit and trajectory system will not be pulled BUT this system will be installed and commissioned via existing OASIS channels with slightly reduced performance (S/N). Old system remains as is.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM

## Slide 10: PSB [LIU]: New cables for the new PSB BLM system will be pulled in // to the old ones for the existing monitors in the ring only NOT for the extra 32 ring BLMs, NOT for the existing monitors in the transfer line, NOT for the new fast BLM requested. Old system will remain as is. New system will be commissioned in parallel in the ring
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM

## Slide 11: PSB : General maintenance on BWS. We hope to be able reach 20 m/s in the PSB with present set-up. We also plan to improve our PM dynamic range during LS1
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BWS

## Slide 12: PSB [Consolidation]: New cables and monitors for PSB extraction fast BCTs will be installed
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT

## Slide 13: HIE-ISOLDE: We will produce and deploy the new HIE ISOLDE diagboxes following project planning. Some issues remain to be tackled: i.e. Short FC limitations, manpower for the electronics development
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes

## Slide 14: PS[Conso]: * New cables and monitor for the PS ring fast BCT will be installed * 1000 turn BCT will be made operational * BUT cables for TT2 BCTs may not be pulled. A cable tray (~100 m) is missing and would have to be financed.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT

## Slide 15: PS[LIU]: New cables for the PS BLM renovation (ring, TL and fast) will not be pulled during LS1.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM

## Slide 16: PS[LIU]: New cables for the PS BWS bunch by bunch measurement tests on SD68 will be pulled. We also plan to improve our PM dynamic range during LS1 but we cannot reach 20 m/s in the PS with current PS.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS

## Slide 17: PS[LIU]: 2 new WCM monitors will be installed.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
WCM

## Slide 18: AD[Consol]: * AD IPM will be moved and modified (strip readers instead of camera) * BBQ system will be deployed * Ctrl SW will be upgraded (ACCOR, Men, Linux).
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM

## Slide 19: SPS[Consol]: Due to EN/EL constraints, the SPS BTV renovation will only be partial. BA1 will be done. BA2 feasibility is still under discussion. BA80 will only happen in 2015 during TCC2/TDC2 campaign.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV

## Slide 20: SPS[LIU]: The cables for TT10 BLM installation will not be pulled.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM

## Slide 21: SPS[LIU]: The new orbit and trajectory system fibers and cables will be installed for Pt5, 6 and 1(+). The old system will remain operational. BA 5 will be equipped to commission the new electronics
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS

## Slide 22: SPS[NA61]: The new DCCT for personal protection (NA61) will be installed and commissioned at start-up.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT

## Slide 23: SPS[LIU]: A new BWS prototype will be installed, provided enough space is found on cable trays.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS

## Slide 24: SPS[LIU]: The SPS BGI will be repaired and optimized (see comment LHC BGI).
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI

## Slide 25: SPS[LIU]: A sync light telescope will be designed and deployed if we manage to find a place for our electronics where we can pull the necessary cables. …Under investigation…
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT

## Slide 26: SPS[LIU]: Matching monitor installation will be finalized (for LHC as well)
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching

## Slide 27: EAN: New GEMs will be deployed in the north areas
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
GEM

## Slide 28: EAN: New ‘Scaler’ electronics will be deployed in the north areas with sampling rate > 100MHz
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
GEM
SCALER

## Slide 29: EAN: TBIU/ID instrumentation monitors and local cabling will be entirely renovated (same but new)
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
GEM
SCALER
TBIU/ID

## Slide 30: LHC: * The temperature controlled racks (BPM&BLM) will be installed in all surface buildings. * The collimator BPMs will be installed * Cables for BPM defined by ATLAS for their forward physics project will be installed
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
GEM
SCALER

## Slide 31: LHC: If the corresponding DIC is accepted (under discussion), diode BPM will be available around the experiments
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
Diode BPM
GEM
SCALER

## Slide 32: LHC: * BLM cable upgrade campaign (NGFS18) will be done. * A prototype of cryo BLM will be integrated into a cryo magnet * Arc BLMs will be dismounted/remounted following LHC consolidation
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BLM
Diode BPM
GEM
SCALER

## Slide 33: LHC: BTVSE/T/S repair of RF fingers will be done
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
Diode BPM
GEM
SCALER

## Slide 34: LHC: 2 of our 4 Fast BCTs will be replaced by ICT monitors. dT/dt interlock will be made ready for commissioning
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
Diode BPM
GEM
SCALER
BCT

## Slide 35: LHC: Installation of PUs for gated tune measurements will be done
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
Diode BPM
GEM
SCALER

## Slide 36: LHC: * Installation of PUs for BGI calibration * BGI monitors repair and optimization will be done
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
Diode BPM
GEM
SCALER

## Slide 37: LHC: * Full maintenance of the BWS * Installation of new bellows with extended lifetime will be done
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
BWS
Diode BPM
GEM
SCALER

## Slide 38: LHC: * Redesign of the extraction mirror tanks * Installation of the optical bench shielding will be done
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
BWS
BSRT
Diode BPM
GEM
SCALER

## Slide 39: All: An international workshop on beam profile measurements is being organized (around March April) to review and optimized our developments on our instruments (this includes CPS and SPS monitors)
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
BWS
BSRT
Diode BPM
GEM
SCALER

## Slide 40: CTF3/CLIC: * EO bunch length monitor commissioning * Additional segmented dump installation * test of Cherenkov fiber BLMs * Diffraction radiation studies…
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
BWS
BSRT
Diode BPM
GEM
SCALER
CTF3

## Slide 41: Voila! Sorry for the ones I forgot in this list.
L4 Beam Instrumentation
IPM
SEM
BPM
BCT
BTV
BPM
BLM
BCT
HIE DiagBoxes
BCT
BLM
BWS
IPM
BTV
BTV
BTV
BLM
MOPOS
BCT
BWS
BGI
BSRT
Matching
BPM
BTV
BLM
BBQ
BGI
BWS
BSRT
Diode BPM
GEM
SCALER
Just a word on 2 comments:
on how to go from specs to proof of success?
on things disappearing from the requirements
It will clearly be a busy shutdown for all of us
So let start with a well deserved drink!