CYV, 18/01/2013

Minutes of the 47th PS Upgrade Working Group

Date: 16. January 2013

Present: Roland Garoby, Stephane Bart Pedersen, Serge Pittet, Claudia Parente, Laurette Ponce, Markus Brugger, Rende Steerenberg, Heiko Damerau, Mauro Paoluzzi, Simone Gilardoni, Christina Yin Vallgren, Michael Lazzaroni, Joao Saraiva, Joachim Vollaire

All the presentations can be found in:

https://indico.cern.ch/conferenceDisplay.py?confId=226976

Meeting:

a) EVM/APT exercise (Heiko and Simone)

https://indico.cern.ch/getFile.py/access?contribId=0&resId=0&materialId=slides&confId=226976

- Based on the updated input from the responsible work unit holders, all the data has been entered into EVM. The budget sum for each work unit has been double-checked but not the detailed data yet. Some of the work units could not be uploaded directly from the excel files to the EVM and the data has been entered manually. Therefore, during the meeting, Heiko went through the status of each work unit and asked the responsible work unit holders to confirm the consistence between the downloaded EVM table and the provided excel files.

- To be noticed: optional work units will not be included in the baseline, but they should stay in the work packages. These options will stay in EVM with “Draft 4” status.

See all the updated work packages:

\\cern.ch\dfs\Departments\BE\Projects\PSUpgrade\WorkPackages_2013-01\LIU-PS_WU_ExtractionSummary

Next step: Move from “Draft4” status to baseline in EVM by end of Jan.

- Beam instrumentation:

Stephane will check the consistence with EVM by the end of this week.

- Power converters:

Serge confirmed the consistence at the meeting.

- Vacuum:

Coating as option should be kept as D4 in the EVM.

- Controls:

Confirmed.

- Electrical systems:

No confirmation has been received but the work units were never changed. The work has already started and will be finished by mid-2013.

- Vacuum:

The work unit on coating of the PS vacuum chambers becomes optional. Christina reminds Paolo to update the work packages and to send Simone the revised version of EVM.

- Installation and transport:

The corresponding work related to coatings for electron cloud should also be updated as option and it doesn’t belong to the baseline.

b) Discussion on the shielding for the solid-state amplifiers of the longitudinal damper in the PS (Mauro Paoluzzi)

https://indico.cern.ch/getFile.py/access?contribId=1&resId=0&materialId=slides&confId=226976

- Solid-state transistors MRF151G for the longitudinal damper amplifier were installed in the SS02 in the PS. After about 2-3 months, a dose of 290Gy has been received. On Slide 1, the figure shows the plots of transfer functions measured on the MRF151G after the irradiation. As expected, the transfer function shifts with dose rate received, but the component remains functional.

- To extend the lifetime of the amplifier, the received dose has to be limited. This can be done by moving the amplifiers to the floor and shielding them with 40cm of iron.

- Need to remove 4x60kg iron blocks to access the amplifier for repairing. The estimation time to replace one amplifier is about 30mins (The SS02 is a location with lowest irradiation dose in the PS).

- Because of the shielding, the access to the neighboring magnets will no longer be the same. Feedbacks from the concerned people for the magnets, vacuum and civil engineering are needed to verify the possibility of the shielding installation.

- The shielding cost is not yet included in the budget (but it is expected to be relatively cheap with respect to cost of the longitudinal damper cavity), Mauro will estimate the cost and add it in the EVM.

- Roland: an internal/international review/collaboration of this type of devices in the future is necessary for gaining experience, especially in the view of the application of this technology in the PSB.

c) Safety documentations for the PS-LIU (Claudia Parente)

https://indico.cern.ch/getFile.py/access?contribId=2&resId=0&materialId=slides&confId=226976

- The Manual / Guideline Document 1255075 ver.1 Released "Safety requirements and safety file contents for LIU project" by HSE Unit:

https://edms.cern.ch/document/1255075/1

The guideline is now accessible to all public. Everyone involved in the PS-LIU, please take your time and have a look at the file!

- Roland: The manual of safety requirements and safety file is addressed for the PS machine and doesn’t seem to be made for PS- LIU projects. The requirements there are far beyond the LIU project leaders’ responsibilities and more specific documents need to be made for the PS-LIU project.

- Laurette will meet with the holders of the work packages with installations during LS and discuss the specific requirements for the safety files.

- Safety files for any newly installed equipment must be ready before the start of operation. Who buys the equipment has the responsibility to make sure that the safety certificate is linked in the safety file.

- Procedure of approve a safety file: once a safety file is ready => all participates review => record corresponding experts approve => finally, complex manager informed and approve.

d) A.O.B

1. Budget for 2013 (Heiko)

For the budget 2013, it seems to be a flat budget cut of 26% on each work unit and all machines for the LIU project.

Roland: The budget cut is due to difficulty of payment but adjustments according to needs will be made during the year. This means that we can still consider that all the money we ask for material request is still there. Although the payment of request will not be able to reach the level we ask, the difference can probably be compensated internally during this year.

2. Cabling (Heiko):

Identification of un-used cables in the tunnel has long time been a problem and practicing of marking the un-used cables in a proper way is very important.

Announcement: Please use violet scotch tape to mark un-used cable!

3. PS bunch compression (Heiko)

Following the LHC fills with 25ns beam at the end of the 2012 run, the new batch compression and merging scheme (BCMS) is now considered as baseline scenario for option of the LHC with 25ns bunch spacing between LS1 and LS2.

4. Technical design report (Heiko)

Writing of the technical design report concerning the PS-LIU will start soon.

5. Workshop concerning LIU and HL-LHC (Roland)

Short after IPAC13 this year, a Chamonix-like workshop concerning LIU and HL-LHC projects will be held. The workshop will be divided into five sections. The content of the five sections have been defined and the corresponding chairmen are nominated. Section 1. needs of clients from physics side. Section 2 – 3 will be a mixture of LIU and HL-LHC and start from ‘what exists’ to ‘plan to reach’. (Section 2: What we can do today? What we will do with LINAC4?.. Section 3: Performance improvements.. Section 4: Plan to reach HL-LHC. Section 5: Summary and Outlook).

6. Electron cloud monitor in the PS magnet (Christina)

The vacuum chamber of magnet 57 will be replaced. Now we are going to redesign the new chamber and try to insert an electron cloud detector in the PS magnet. Several different alternatives (button pick-up/strip detector/microwave transmission/photon emission/..) have been considered and the studies are ongoing.

Next meeting: 30/01/2013, 9h00, 864-2-B14 (JBA)

Minutes by Christina Yin Vallgren