## Slide 1: Organization of LS1 Consolidation, upgrade and maintenance
K. Foraz, CERN
AMMW 2013

## Slide 2: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 3: Introduction - LHC
Dec. 2012
23 fb-1
4 July, 2012
Higgs discovery
Oct. 2010
1e32
248 bunches
September 10, 2008
First beams around
September 19, 2008
Disaster Accidental release of 600 MJ stored in one sector of LHC dipole magnets
August 2008
1st injection test
Aug. 2011
2.3e33, 2.6 fb-1
1380 bunches
Nov. 2010
Ions
Jun. 2011
1380 bunches
Nov. 2009
Beam back
18 June, 2012
6.6 fb-1
to ATLAS & CMS
2008
2009
2010
2011
2012

## Slide 4: Introduction
Code name LS1 (Long Shutdown 1)
Priorities:
  Implement the necessary safety mitigation measures
  Perform the necessary consolidation and upgrade activities Perform the full maintenance of equipment
in order to ensure the operation of the LHC above 13TeV collision center mass of Energy, and a reliable operation of the accelerator complex.

## Slide 5: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 6: LS1 – Maintenance
Perform the full maintenance of all equipment
  Cryogenics  N. Bonneti - Thursday
  Cooling and ventilation  G. Peon - Thursday
  Main electrical sub-station J.-M. Foray - Thursday
  Safety systems: fire, ODH detections, alarms…
  Access system
  Magnets
  Quench protection systems
  Power converters
  Cranes lifts
  Collimators
  …..

## Slide 7: Main consolidation & upgrade works in injectors
PS ventilation system
SPS – replacement of irradiated cables
Improvement of the radiation shielding over the PS and Septum 16
Magnets
New access system
Demineralized water prod. Station
SPS valves exchange
Interlocks
PS & PSB Upgrade of the RF systems
18kV transformers

## Slide 8: Main consolidation activities in LHC -1
SMACC-Superconducting Magnets And Circuits Consolidation

## Slide 9: Main consolidation activities in LHC -2
P7
P1
P5
P8
Point 1 – ULs, Ujs, RRs
~3 dumps per fb-1
2012
~12 dumps per fb-1
< 0.5 dump per fb-1
2011
R2E – Radiation to Electronics
Point 5 – UJ56, UL55, RRs
Point 7 – UJ, TZ

## Slide 10: Main consolidation and upgrade activities in LHC -3
But also
  LHC pumping stations
  Replacement of water cooled cable hoses
  Replacement of UPS
  New collimators
  Vacuum
  Current leads
  Helium ring line
  Beam instrumentation

## Slide 11: Schedules -1

## Slide 12: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 13: Preparation is fundamental -1
Define
  Arbitration between requests  plan.cern.ch w.r.t resources & priorities
  Understand and evaluate the # requests  coordination meetings, reviews

## Slide 14: Preparation is fundamental -2
Prepare
  3D integration and plans  design offices & ICL
  Prepare, award & set up contracts, Follow material production
  Find and organize resources
  Document changes  ECRs  T. Birtwistle- Thursday
  Schedule activities  detailed and global schedules
  Mitigate risks  Task forms, VIC, DIMR
  Prepare and prepare  Work Package analysis, reviews

## Slide 15: Risks
Safety systems
Electrical systems
Cryogenics
Incidents
  Anticipate and prepare
Peven
Podd
LSS
Vent.
Vent.
LSS
LSS
LSS
Vent.
Tunnel sector
Chart: Evacuation assesment - sector 81
Courtesy: S. La Mendola
Work Packages Analysis
Evacuation simulation
AMMW - K. Foraz

## Slide 16: Risks
Incidents
  Anticipate and prepare
  Safety is a shared concern
Delays due to
  Material unavailability
  Contracts &/ resources problems
  Unexpected additional activities
Follow-up & communication of drifts
  It’s better to lose one minute in life… than to lose life in a minute.
Special Intervention Teams
Work Packages Analysis
Evacuation simulation
Priorities for work coordination
Safety
Quality
Schedule and Cost
AMMW - K. Foraz

## Slide 17: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 18: LS1 additional persons

## Slide 19: Access
  All activities are declared and accepted via in IMPACT D. Lafarge Friday No Impact approved = No access
Access in the LHC is a crucial point !!
  Up to 250 persons in two adjacent sectors  ~ 200 bikes (logistics)
  Start hours spread over 2h30’
  Lift: sensible equipment
    Reinforced “piquet”
    Maintenance - Frequency doubled
AMMW - K. Foraz

## Slide 20: Follow-up
Bi-monthly plenary meetings to follow the activities in each machine
A lots of had-occ meetings
  On site
  Preparation
  Treat new issues
Bi-monthly report to Long Shutdown Committee
Issues management
  New activities
  Material delays – not that much !!
  Delays – not that much, neither !!
Dashboards
  Curves
  Broken line

## Slide 21: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 22: Injectors status
Very good progress 

## Slide 23: LHC status
R2E
  P1 ~ 2months ahead of schedule
  P5, P7 on schedule
SMACC
  ~3 weeks delay
  But 1st wagons will help the followings
Maintenance on schedule

## Slide 24: Contents
Introduction
LS1
  Main activities and schedules
  Preparation
  Organisation
  Status
Conclusions

## Slide 25: Conclusions
The main drivers
  The Consolidation of the Superconducting Magnets and Circuits (SMACC )
  Radiation to Electronics (R2E)
  Massive maintenance after more than 3 years of operation
An exceptional number of activities & co-activities
An exceptional number of additional personnel from contractors, Project Associates, FSU, etc.
Preparation is essential
Strong commitment of all stakeholders
Few bad surprise so far
So far..so good