TS-LEA

LEMIC 93

16th October 2007

# LHC Experiment Machine Interface Committee

# (LEMIC)

# Minutes of the 93rd meeting held on 16th October 2007

Present:	A. Ball, O. Beltramello, F. Butin, P. Ciriani, L. Evans, S. Evrard, C. Fabjan, K. Foraz, M. Ferro- Luzzi, L. Leistam, D. Macina (Scientific Secretary), M. Nessi, M. Pepe-Altarelli, A.L. Perrot, J.P. Revol, C. Schaefer, D. Swoboda, E. Tsesmelis (Chairperson), R. Veness, W. Witzeling

MINUTES OF THE LAST MEETING

There were no comments to the minutes of the last meeting.

matters arising

E. Tsesmelis said that the TI2 test foreseen for October 14th had been cancelled with only a 24 hours notice. ALICE complained about this lack of earlier warning. L. Evans explained that the test was cancelled at the last moment as the AB DSO decided to cancel the test since no shielding at the bottom of PMI2 was available. The situation was clarified in the ICC meeting held 3 days after LEMIC. Shortly before the beam test, an inconsistency was detected with the obligations CERN had taken in its "lettre d'engagement" sent to the INB authorities, and it was decided not to authorise beam operation of TI2 as long as the PMI2 shielding is not in place. ALICE asked to be informed as soon as possible about the new possible dates for the test.

master schedule and progress

(K. Foraz)

K.  Foraz showed the latest progress on the machine installation and commissioning and the new updated schedule. By the 8th of November all interconnections will be closed. A solution has been found for the PIM problem:  the aperture is being systematically checked with the RF mole before cool-down, and will be after each warm-up. All arc Short Straight Section (SSS) which are not already cold (i.e. all but Sector 45) are being displaced axially by 2 mm to compensate for the asymmetry in the PIM length caused by the systematic over-length of the SSS cold mass. This should reduce the number of PIMs failing in future warm-ups.

In Sector 8-1 a new SSS was being installed at the time of the meeting. In Sector 7-8 the activities related to PIM induced a delay of 5 weeks for the start of the cool-down. In Sector 4-5 the cool-down has re-started to allow the “phase 1” power test (i.e. without inner triplet) to be completed by the end of the year.  The dates for the maintenance of the cooling towers (indicated on the planning with black lightening) and the AUG tests have agreed with the experiments. The maintenance of the 400kV electrical network will limit the total power that can be delivered to the LHC during that period. The new schedule takes into account the helium delivery. L. Evans said that, in the last Finance Schedule Meeting, a new contract has been adjudicated to two helium suppliers and two more are kept as reserve.  Finally, the new planning foresees the global test of the LHC access system in week 3.

L. Evans said that the highest priority for the machine is to commission it as fast as possible. The date for beam injection is kept to 21 May 2008. By that date, at least 4 sectors will be fully commissioned to 7 TeV while the remaining 4 sectors will be cooled-down but only partially power tested. The present idea is to inject beam in the LHC on May 21 and proceed in parallel with the beam commissioning at 450 GeV and the completion of the powering test of the 4 remaining sectors.  Details need to be sorted out. The experiments expressed some concern about the new commissioning planning and have asked to get more detailed information about it as soon as available. In addition, the experiments have stressed that, for what concerns physics, the most important thing is to get the machine commissioned to 7 TeV as soon as possible.

status of the experimental beam pipes installation

(R. Veness)

R. Veness gave a status report on the status of the installation and commissioning of the experimental vacuum systems. The zone between the experimental areas and Q1 is called VAX and, in general, it hosts beamline components, the gas injection system and experimental vacuum system used for pumping and venting sectors. The VAX installation is rather complicated because of the limited access (ATLAS and CMS), the limited installation window between triplets repairs and machine sector cool-down, co-activity with survey, triplets repairs and warm magnets commissioning and integration conflicts. Nevertheless, 4 VAX (IR5R, IR8R, IR2R, IR8L) have been successfully commissioned, 2 are in progress (IR1L, IR5L) and 2 need to be done (IR1R, IR2L).

The ATLAS vacuum chamber is 60% complete: 5/7 chambers have been installed, 3 connected and 1 aligned. The extensive permanent cabling is well advanced. It has been found out that the TAS absorbers have been installed 29 mm (A-side) and 21 mm (C-side) further than nominal from the IP. Since the TAS is a machine element, F. Butin is circulating a Non Conformity Report (NCR) to “use as-is”. F. Butin will also coordinate the later alignment of the TAS. The remaining tasks are: testing of the bakeout circuits in the cavern, integration and testing of LUCID with the VJ chamber in building 927, the installation test of the VJ chamber in the cavern and the full integration test of ATLAS reserve chambers in building 927. For what concerns the installation, the opening and closing of the ECAL around the VA chambers needs to be done together with the installation and alignment of VA fixed supports, the connection and alignment of VT chambers, and the full installation of the VJ chambers. The commissioning of the gas injection system is scheduled for week 46 and the final chamber commissioning will happen in 2008.

The ALICE vacuum chamber is 80% complete. The remaining activities are the installation and commissioning of the VAX sector in IR2L and the installation and commissioning of the RB24 copper chambers and supports that ALICE would like to delay until 2008.

The LHCb vacuum chamber is 95% complete. The main remaining task is the installation of the VELO detectors which will require the opening of the vacuum sector which, at the end of the operation, will need to be pumped, leak checked and re-filled with Ne.

For what concerns CMS, the vacuum chamber is 10% complete. The mechanical and bakeout test of the assembled forward chambers has been prepared in building 927 and it will start on week 43. For what concerns the installation in the cavern, AT/VAC is still waiting for a window to install the 54-side forward chamber and the remote flange while the remaining chambers will be installed in 2008.

Finally, R. Veness commented on the schedule and resources for the remaining operations in 2008. The major installation work in ATLAS and CMS will not be complete until at least March 2008, according to the latest experimental schedule. He stressed that he needs to know the time margin between beam injection and beam vacuum ready for beam. In addition, the ALICE RB24 sector may also be pushed to 2008. Since the schedule is not well defined, R. Veness said it is important to keep flexibility for the FSU support and he will request the 50% contribution from the experimental budgets. Finally, the information from the experiments for possible detector openings in 2008/9 shutdown is now requested.

status of the installation and commissioning of the atlas experiment

(M. Nessi)

M. Nessi gave a status report about the installation and commissioning of the ATLAS detector.  Today’s activities concentrate on:

- The completion of the detector installation and all related services (~6000/7000 tons installed).

- The Hardware Commissioning of all electronics components, controls and safety systems.

- Integration and tuning of all controls.

- Full test of the data taking chain with calibration and cosmics events.

- Test of all the online and offline software and computing infrastructures.

A number of achievements have been reached in the last 6 months:

- Installation of the 2 Endcap Toroids and their services connections. The cooling down has started in week 41 and it will last 4 weeks. Then the Toroids will be tested at full current.

- Installation of all services, cables, pipes, gas, cooling systems and access platforms for the barrel muon spectrometer. 99% of all chambers are in place. 90% of the alignment system is operational. Cosmic rays have been detected with 25% of the barrel precision chambers (Monitored Drift Tubes Chambers, MDT). The level of dead and noisy channels is << 1%. The trigger is provided by the Resistive Plate Chambers (RPC) top sector (trigger rate ~ 200 Hz) and the standalone RPC tracking reproduce the shaft images as expected.

- Installation and hardware connection of all forward muon spectrometer (Big Wheels). It took about 3 years of integration and assembly work on the surface and 13 months to transport and install them in situ.

- All Calorimeters (LAr and Tile) connected, cooled and brought to operation. Retrofitting and re-installation of all (low voltage) power supplies is achieved. A relatively simple modification had to be implemented on the LAr Front End Boards (FEBs) to fix a problem that could lead to early ageing, and to cure a shaper instability on ~0.1% of the channels). However, it has been significant work to remove, repair, and reinsert all FEBs. Some retrofitting of electronics front end boards is still ongoing. A few FE components of the Tile Calorimeter, and in particular connectors and flexible connections, are being systematically checked and improved on all drawers. More than 1/3 of the drawers have been refurbished so far, curing all previously observed instabilities. Data taking with cosmic rays is going on with both calorimeters.

- Installation and connection of all Inner Detector (ID) components (2 endcaps TRT + SCT, full pixel). It is still missing the final in situ connection of the silicon detectors cooling system and of the entire pixel and the final closing of the ID volume. A problem was found in a power connector of the heaters of the evaporative cooling system. After two failures, it has been decided to bring the heaters outside the ID volume, on the calorimeter barrel flange. In addition, a new connector was developed with the producers with good results. Full delivery is expected in November 2007. The SCT/TRT commissioning is going on: ~0.3% dead channels have been found out of 6 106 and the electronic noise is as expected. The Pixel detectors have gone through the electrical quality assurance test just before installation with excellent results. The Endcap A was tested on surface prior installation and 15000 cosmic tracks have been reconstructed with very good noise occupancy.

- Installation and vacuum test of the internal beam pipe system. All other beam pipes waiting on surface.

- Preparation on surface of the first small wheel of the Muon Spectrometer. The second one will just follow. All detector radiation shielding elements have been installed while the very forward ones are waiting on surface.

- Installation of ~35% of the necessary online processing hardware, with all functional components present. LVL1 trigger is mostly in place.

- Full scale activation of the main control room. Integration of all systems readout and controls.

- Periodic global cosmic runs of the entire detector (ATLAS operation mode) to debug readout, controls and safety systems.

M. Nessi finally showed the installation schedule 9.2. The main milestones for 2007 are:

- November 2007: full current test of the endcap toroids (ECT) in parallel with the SCT heaters installation and the debug of the cooling system. The Endcap Outer Chambers are installed on both sides.

- December 2007: installation of the Shileding Disk (JD) and of the Small Wheel (MD). For this operation, both the ECT and the Big Wheels (BW) have to be moved to the garage position.

M. Nessi stated that, at the moment, ATLAS has a detector which corresponds to the design in terms of layout and expected performances. A systematic commissioning program is following the installation of the last single devices. Around March 2008, ATLAS will start a continuous operation mode of the detector, manning slowly the main control room with people and shifts and turning on the run coordination organization and all piquet services. Up to that moment ATLAS will bring up, piece by piece, each component through the full read out chain, will debug the control system and the trigger system and will time in all read-out components as much as possible without beam. Finally, they will run global cosmics runs to tune the system and to build up experience. M. Nessi concluded telling that ATLAS will start closing the detector according to the machine schedule but that they need ~2 months of notice. As of today, ATLAS plans to close the beam pipe end of March/early April 2008.

next lemic meeting

The next meeting of LEMIC will be held at 14:00 on Tuesday 4 December 2007.

Daniela Macina