## Slide 1: PREVESSIN, SPS and North Area (1/2)
Circuits | Stop | Restart | Comment
SPS primary Loop | 14/06/2013 | 13/09/2013 | 
Second. circuits of BA1 | 17/04/2013 | 20/06/2014 | 
Second. circuits of BA2 | 10/04/2013 | 21/03/2014 | 
Second. circuits of BA3 | 03/04/2013 | 04/04/2014 | 
Second. circuits of BB3 | 27/03/2013 | 18/04/2014 | 
Second. circuits of BA4 | 10/04/2013 | 18/04/2014 | 
Second. circuits of BA5 | 10/04/2013 | 18/04/2014 | 
Second. circuits of BA6 | 03/04/2013 | 21/03/2014 | 
Second. circuits of BA7 | 03/04/2013 | 22/04/2014 | 
BEQ2 cooling circuit | 25/04/2013 | 25/04/2014 | + test period from the 18th of September for 4 weeks
BEQ3 cooling circuit | 25/04/2013 | 25/04/2014 | + test period from the 18th of September for 4 weeks

## Slide 2: PREVESSIN, SPS and North Area (2/2)
Circuits | Stop | Restart | Comment
North area primary Loop | 10/05/2013 | 31/05/2013 | 
Second. circuits of BA80 | 24/04/2013 | 09/05/2014 | 
Second. circuits of BA81 | 24/04/2013 | 09/05/2014 | 
Second. circuits of BA82 | 27/03/2013 27/09/2013 | 02/09/2013 16/05/2014 | 
Cooling circuit of bldg 867 | 08/05/2013 tbc | 12/05/2013 tbc | Local demineralised water production
CNGS | 15/04/2013 | No restart foreseen so far | 

## Slide 3: MEYRIN, CPS (1/2)
Circuits | Stop | Restart | Comment
PS – Central building Anneau | 01/06/2013 | 21/11/2013 | 
PS – Main magnet | 11/03/2013 | 21/04/2014 | 
PS – Chilled water | 01/06/2013 | 21/12/2013 | 
Booster / TT2 | 25/02/2013 | 24/02/2014 | 
Booster – chilled water | 15/09/2013 | 21/03/2014 | 
EAST area | 17/12/2012 | 05/05/2014 | + Test of the primary zone in March.
LEIR – LINAC 2 and 3 | 14/06/2013 | 13/01/2014 | It could be stopped before the 14th if the water consumption is too high
LINAC 2 | Running |  | 3 days for the maintenance TBD
LINAC 3 | 01/06/2013 | 13/01/2014 | 
AD | 15/05/2013 | 13/01/2014 | 
AD Target | 21/12/2013 | 02/06/2014 | 
ISOLDE | 21/02/2013 | Cooling plant dismantled | Restart on the new cooling system

## Slide 4: MEYRIN, CPS (2/2)
Circuits | Stop | Restart | Comment
378 - Production of demineralised water | 15/05/2013 | 31/07/2013 | Supplying demineralised water circuits CERN wide except SM18
CTF3 | 15/05/2013 | 01/08/2013 | Following the demineralised water consumption
nTOF | Running |  | A week for the maintenance TBD
ISR circuit ( Hall Test 287, 181 ) | 15/05/2013 14/10/2013 | 31/07/2013 29/11/2013 | 181 back up cooling with tap water
Loop 9 (Hall Test 377) | 15/05/2013 14/10/2013 | 31/07/2013 29/11/2013 | TBC
Primary loop Meyrin (compressed air + cryo lab 163, 165, 253) | 04/03/2013 | 11/03/2013 | 
RF bldg 112 | 15/05/2013 14/10/2013 | 31/07/2013 29/11/2013 | TBC
Chilled water for ISR, 112, 30, TT2 | 02/06/2013 14/10/2013 | 28/06/2013 29/11/2013 | TBC