## Slide 1: LS1 Status @ Injectors
S Baird on behalf of N. Gilbert, S. Mataguez, D. Hay & D. McFarlane
LSC 5th April 2013

## Slide 2: PSB
2013
2014
Dec.
Jan.
Feb.
Mar.
Apr.
May
Jun.
Jul.
Aug.
Sep.
Oct.
Nov.
Dec.
Jan.
Feb.
Mar.
Apr.
May
Jun.
Jul.
Aug.
Sep.
Oct.
Nov.
Dec.
2013
2014
Dec.
Jan.
Feb.
Mar.
Apr.
May
Jun.
Jul.
Aug.
Sep.
Oct.
Nov.
Dec.
Jan.
Feb.
Mar.
Apr.
May
Jun.
Jul.
Aug.
Sep.
Oct.
Nov.
Dec.
PSB Hall
PSB Tunnel
MAGNET TESTS
TESTS MULTIP. CONV.
General maintenance
General maintenance
Survey
Magnets
Cables
  Cables
LIFT REPLACEMENT
MULTIP. CONV.
TE-ABT
Survey
Hardware commissioning and cold check out
CV
              SETUP WITH BEAM
VACUUM
RF
EN-STI
BE-BI & CO
BE-BI & CO
ACCESS
COMMISSIONING NEW ACCESS SYSTEM
Beam back from L2 to PSB 30/05/2014
Beam back from PSB to PS 20/06/2014
Beam Off : 11/02/2013
CV
Survey
Magnets
Cable
Lift & crane
CV
Vacuum
RF
BI & CO
Access
EPC
Powering
Tests
Collimation (STI)
Kickers
Septa
No major changes in last 2 weeks
All lifting and handling HSE inspections completed.
Multipole converter project and rack installations ongoing.
  De-cabling in the surface building completed
  Underground cabling in progress
Cabling: 8 PSB campaigns are in preparation
  SEMgrids, RF Finemet cavity, BI BLMs, Vacuum equipment, Kickers, BE-BI, Interlocks (WIC) and the BIW safety system.
MAD installation is being prepared
  Co-activity issues with the replacement of PSB lift AS-45 to be resolved

## Slide 3: CPS
Opening : 11/03/13
End LS1 : 01/05/14
Magnet
Civil engineering
Access
CV
Ventil
CV water
Septa (SE)
Kickers
Collimation (STI)
Vacuum
Cable
EL (pow.)
Lift & crane
Powering
Tests
RF
Control
EPC
Fire detection
Survey
Beam instrumentation
RF
CE
CE
CE
R.Goward
Lift B269
Maintenance Sealing
Powering tests
EPC
Magnet tests
Magnet tests
MU14
MU55\57
MU75
SS15 Liberate
CE
PS PSS complex new access system commissioning
Sept.16
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
HVAC
CV water
SMH16
SEH23
Dummy
SMH42
SMH57
STP
STP
Vacuum bake-outs
STP
STP
STP
EL
RF
RF
RF
RF
RF
RF
RF
RF
10/07
16/02
11/03
01/05
Physics
PS Setup with Beam
PS Operations Cold Check-out
Control
DSO tests
Ready for extraction 10/07/14
Access
  Doors mechanically locked 19h00 and unlocked 07h30 (Thomas’s talk)
  Blind access 08h00 to 11h00 each morning
  Door 101 is not in use until 1st June due to civil engineering work for the new access system
Route Goward shielding work started
  Access restrictions to the “centre anneau” (Simon’s talk)
Dismantling of the existing ventilation system
  Work in Sectors 6 & 8 and Galleries 1 & 3
  Galleries 1 & 3 are closed until 10th May
In the PS Inflector zone certain auxiliary magnets (Linac3 to LEIR transfer line) are NOT CONDEMNED
  LEIR remains in HW test mode until mid-April

## Slide 4
Magnet test are now complete
SPS was opened for “General” access on Wednesday the 27th March (as planned)
Test AUGs at each point have now started and will continue next week.
16 magnets have been identified during the magnet test as needing to be changed (planning for this is on-going)
16 magnets in BA5- will be removed for new coated vacuum chambers. This will start today and continue until the end of next week (4 magnets per day)
Survey have started their survey and re-alignment of the entire SPS.
All works proceeding as planned.

## Slide 5: AD
Main AD-ring access point:
  shielding blocks reorganized.
  ready for new access system installation in August
Improved protection barriers for visitors
Preparation for the new building 393 (Civil engineering starts on 1st May)
  Removal of DC cables completed on 3/04
  Removal of control cables started on 4/04 until 26/04
Old line 8000 almost totally dismantled
  Completed this summer
BHZ8000 definitely removed from AD machine
SMH53 changed
KFI 55/56 tanks : repair in progress (lab)
Awaiting successful coil test results before dismantling ATRAP and removing BHN06

## Slide 6: RP Buffer zones
PSB zone is created but not operational
  Not equipped
AD zone is created but cannot be locked.
  Not used
LEIR zone
  Shared with Linac2
PS zone is not ready
  Space by door 121 is used temporarily