## Slide 1: Preparation for the installation of the CREAM readout
The LKr readout team

## Slide 2: Cooling and power distribution
Decision taken to go to new heat exchangers
  New exchangers to be bought now
  Installation will follow
  The old circuit has been already emptied
After the exchanger installation
  Complete the installation of power plugs
  2 long plug bars on each rack
    4 crates + 4 switches
    Not overload one single bar
    Many power slots unaccessible because of equipment on the back/ exchangers

## Slide 3: VME crates
All the ordered crates are at CERN
  Connected to power
  Keep them running to spot problems
  Indeed:
    A couple of fan trays had problems (fan failure) in the last delivery
  To be reported to CAEN after their holidays
  All the others on without failures for few months

## Slide 4: Optical fibers
Installation completed
Fiber patch panels (both network and clock) will be on top of the racks EB01 and EB08 on the front face
Already being used by the CREAM setup in the dry run
Already discussed:
  The path of the network fibers from the front panel to the internal back part of the racks 2-7
  It is foreseen to install a complete crate (with all the services) to test the routing of cables and fibers

## Slide 6: Broken regulator card
Reminder: during the control of the channels, a regulator board with a short circuit in input was found
Its removal with the standard procedure was failing, because one of the two screws was turning around
Eventually removed and a spare unit prepared for the substitution
For the removal, all the neighbouring cards where removed as well
Conservative approach to remount everything
  Install the regulators one at the time
  Check some of the corresponding channels to be sure the card is correctly installed
  Go to the next one
  During the tests, another board found faulty and replaced
Mechanical problem:
  The initially faulty board was not fitting exactly in its position, because the hole in the brass box to the flange is too small
  The board had to be grinded on one side to fit in

## Slide 7: Channel checks
We have to complete the channel checks using calibration and scope.
  About 3000 channels
Work started after the board repair
  As of today, 1100 channels done
  8 hours still needed
A refined investigation will be needed
  To understand specific problems

## Slide 8: Calibration driver hw/sw
Planned to upgrade the driver to new hardware
  VME I/O registers instead of CAMAC
  The TALK board to configure the pulse sequence
  A patch panel PCB to match the old cables to the new connectors
New software as well
  C++ code to handle the new hardware, run control and burst timing
  Prototype setup by Christina Hughes (G. Mason Univ.)
  TALK commands to be added
I plan to smoothly shift from the old system to the new one in the next months
In this way we can dismiss the last pieces of the NA48 LKr system