## Slide 1: Straw electronics status

## Slide 2: webs
Problem with bad batch not yet fully understood
  Manual soldering resulted in solder balls under HV capacitors
    Cleaning with tool
    Iterative process, long
  To improve, soldering in oven was proposed
    Assembly workshop proposed to use a tool/jig for better precision solder deposition
    At the end, they used new machine, like a printer
  The result was a batch with a copper deposited on the petals and conductive dirt
  Even after careful cleaning and petal re-metallisation there was a leaking current
New production
  Return back to manual soldering
  Must again check solder balls
  Tested OK!
Test tools, particularly noise scan, proved to be very sensitive to any HV problem

## Slide 3: Covers
The last modifications proved to be beneficial
Shielded ethernet connector + signal conditioning
  20meter cable
  Link stability
  Also mechanical strength and reliability
Bigger FPGA
  No degradation of performance
New rate numbers
  15MHz instead of 10MHz (muon halo + other contributions)
  Mean rate/straw has changed 33kHz->40kHz->60kHz
  Maximum rate/straw 0.5MHz -> 0.8MHz
  Worst cover close to the beam with 10 straws
    Total rate 10*0.8MHz*2(edges) = 16MHz events
    Current extraction rate is 10MHz – use 2nd data link to achieve 20MHz
  Still OK, but margin small

## Slide 4: Covers
Pre-production
  15 boards of each type delivered
  Vito has tested 6 of each type
  2 boards did not pass
    1 (probably) only minor problem with parameters set too tight
      0.65A current instead of 0.64A
    2nd board has problems with DAC programming
  Finish testing next week
  If yield better then 90%, go ahead with production
Full production ~6 weeks from green light
  October 2013

## Slide 5: Covers
Production tests
  Test bench used for pre-production
  Very efficient and complete
    Parameters rd/wr
    Link test
    Power (current and voltages)
    Noise scan
    Signal injection even/odd channels with 3 different amplitudes
      Can discover shorts between neighbouring channels
      Sensitivity estimation

## Slide 6: Covers
Chamber installation
  Check mechanics
  Gas tightness
  Noise scans with module shield installed

## Slide 7: Patch panels
HV
  Fully passive now
    No DCS
    If problem, stop experiment and manual intervention
  Modularity changed
    More channels to better isolate the problem
LV
  Wait for final PS
  Probably minor design change
    4 inputs 8V/10A instead of 8V/40A
Both PP should go to the production as soon as we know PS for sure
  Type of the connectors
  Cable types
  Simple objects – production fast

## Slide 8: Cables
Ethernet/data cables
  We should start procurement soon
  Try to get help from CERN stores
    Existing cables, but longer and shielded
    Halogen free
LV+HV
  Wait for final PS
  Production at CERN

## Slide 9: Power supplies
Wiener
  New offer
  LV module with 8x8V/10A instead of 2x8V/40A
  HV module with
    high precision current measurement 200pA
    More lines to improve modularity
  Try to buy 1 set this year (Dubna?)
  The rest 3 next year
Also offer from CAEN
  Custom HV module
  New LV module
  Price still 10% higher then Wiener
  It seems they are more noisy then wiener (not measured)

## Slide 10: VME
Need 4 VME crates – 1/chamber
  2 VME-9U crates used now
  2 ordered
Need 4 SBCs
  2 in use
  Still need to order 2 pieces

## Slide 11: SRB
SRB prototype tested and verified in different conditions, even with very high rate
Can be extended to final full SRB
SRB
  Serving up to 16 covers, ½ view, 256 straws
  TTC control from fiber, VME, LEMO
  Output – 2 GbE to pc farm with L0 selected data
  Optional output to L0 trigger
  Full 10s data buffer readable VME and pc-farm
  Design started
  Prototypes December
  Details next talk

## Slide 12: DCS
We provided
  User requirement document
  Testbench with patch panels
MPOD
  Still not resolved
  Possibly 2014 only user control