## Slide 1: DCS WG : achievements and challenges

## Slide 2: DCS strategy and plans
Concentration on basic control of whole detector without closing possibility of future upgrade (horizontal base)
  Test and integration of all available middleware
  Integration of all available hardware
  Migration to final network and DB set-up
  Simplified User Interface and functions
Implementation of advanced control in case of availability of extra manpower
Installation of final DCS hardware – beginning of spring of 2014
Commissioning - April / May 2014

## Slide 3
Main DCS hard- and middleware
CAEN HV
KTAG
CHANTI
LAV
STRAW
RICH
CHOD
MUV
IRC/
SAC
LKr
CAEN HV: 12
CAEN HV
CAEN HV
CAEN HV: 1,2
WIENER FE crate
WIENER FE crate
WIENER FE crate
FE control: 12
CAEN HV
WIENER FE crates
LV control
LKr LV control
LAV FE control
Win CC OA 3.11
OPC servers and
other middleware
IT: ORACLE DB
WIENER FE crate
PS (?)
FE control
MPOD: 4
WIENER FE crates: 4
LV control
CAEN HV: 4
WIENER FE crates: 5
CAEN FE crates: 32
CAEN FE crates
KTAG FE control
MPOD
STRAW HV & LV
RICH FE control
FE control
CHANTI PS
FE control
Hardware
Env. monitor
KTAG Env. monitor
GTK
External systems
Ready
In progress
CAEN EASY
WIENER FE crate: 4
WIENER FE crates: 12
RO card control
GTK RO card control
S
T
A
T
E
2
MON
T
H
S
AGO

## Slide 4: Common for all sub-detectors tasks
Last achievements:
  Migration to WinCC OA 3.11 SP1 + JCOP 5.01 + UNICOS 6.1 :
    Operational version for 2014
    Validation of component base approach
    Clean-up
  Integration of second VAISALA Combined Pressure, Humidity and Temperature Transmitter
  Another iteration with CAEN OPC server. A test of a new version is near completed.
Challenges (till run 2014):
  Stable and reliable common middleware
  Adaptation of DCS to final set-up of NA62 network
  Procurement and installation of final DCS hardware
    SYSTEC box(s) for LAV FE control
    New front-end computer(s) in pc-farm area
    New back-end server(s) in CCC
    Cabling and arrangement of DCS rack in pc-farm area
  Integration of information provided by external systems
  Further cleaning and unification of internal DCS structure

## Slide 5: Sub-detectors : KTAG/CEDAR
Last achievements:
  FE control of two fully populated FE boards installed in KTAG d uring July dry run
  Successful test of DIM server for LV power supplies control
Challenges:
  Finalization of control of HV system
  Implementation of FE control for full detector
  Integration of LV power supplies
  Development of control program for CEDAR pressure scan
  Improvement of CEDAR alignment tools
  Final tuning of Temperature & pressure measurement
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 6: Sub-detectors : GTK
Last achievements:
  A preliminary version of User Requirements + first meeting + mails exchange
    4 WIENER VME crates – integration should be straightforward
    Custom control of RO cards
      6 parameters x 30 cards
      A DIM server should be developed by GTK team
    CAEN-EASY 3000 LV system
      3 crates x 12channels = 36 channels in total
      Doubts about reliability of long CAN bus line between branch controller and EASY crate (should be <150m according to CAEN spec)
    CAEN HV system – 3 channels, integration should be straightforward
Challenges:
  Detailed User Requirement document (naming, mapping, UI panels, etc - “a la” KTAG)
  Decision on CAEN-EASY mainframe location (central team recommends to install it in TCC8)
  Development of RO cards control
  Kick-off meeting is scheduled in mid September
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 7: Sub-detectors: LAV
Last achievements:
  Integration of FE control for 3 stations in central DCS
  Stress test of new FE board FW shown that after a few days of correct operation 2 boards from 5 started to drop frames and finally stopped to send them completely.
Challenges
  Reliable and stable FE board FW
  “KTAG like” LAV DCS user requirement document available on EDMS, in particular for LAV12
  Development of FE control for whole detector
  Finalization for HV and WIENER control – pending on hardware availability
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 8: Sub-detectors: Straw Tracker
Last achievements:
  Simulator of monitoring system (LV, temperatures, etc) based on ELMBs for ½ chamber (Straw team).
Challenges:
  Full monitoring system (> 2000 channels !)
  WIENER crates
  Integration of MPOD power supplies (by STRAW team)
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 9: Sub-detectors: RICH
Last achievements:
  Partial test of HV system (2 crates)
Challenges:
  Full test of HV system (waiting for hardware)
  WIENER crates (waiting for hardware)
  Front-end control - “terra incognito” – no progress yet
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 10: Sub-detectors: LKr
Last achievements:
  Full integration of CAEN 8100 crates
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC

## Slide 11: Sub-detectors: LKr
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC
Challenges:
  Final debugging and cleaning

## Slide 12: Sub-detectors: MUV
HV system and WIENER crate are ready
Challenges:
  HV system for MUV1. Waiting for URD and hardware
  Front end control - “Terra incognito” – no progress yet
CEDAR
GTK
CHANTI
LAV
STRAW
RICH
CHOD
LKr
MUV
IRC/SAC
“Terra incognito”: IRC/SAC, CHANTI, HAC
?
?
?

## Slide 13
Main DCS hard- and middleware
CAEN HV
KTAG
CHANTI
LAV
STRAW
RICH
CHOD
MUV
IRC/
SAC
LKr
CAEN HV: 12
CAEN HV
CAEN HV
CAEN HV: 1,2
WIENER FE crate
WIENER FE crate
WIENER FE crate
FE control: 12
CAEN HV
WIENER FE crates
LV control
LKr LV control
LAV FE control
Win CC OA 3.11 SP1
OPC servers and
other middleware
IT: ORACLE DB
WIENER FE crate
PS (?)
FE control
MPOD: 4
WIENER FE crates: 4
LV control
CAEN HV: 4
WIENER FE crates: 5
CAEN FE crates: 32
CAEN FE crates
KTAG FE control
MPOD
STRAW HV & LV
RICH FE control
FE control
CHANTI PS
FE control
Hardware
Env. monitor
KTAG Env. monitor
GTK
External systems
Ready
In progress
CAEN EASY
WIENER FE crate: 4
WIENER FE crates: 12
RO card control
GTK RO card control
Operational version for 2014

## Slide 14: DCS tasks and resources needed (in days)
 | HV | LV | FE control | Crates | Specific tasks | Total
KTAG | 10 | 50 | 10 |  | 60 | 130
 | HV | LV | FE control | Crates | Specific tasks | Total
GTK | 2 | 5 |  | 5 | 15 | 27
LAV | 2 |  | 15 | 1 |  | 18
STRAW |  | 15 |  | 5 |  | 20
RICH | 5 |  | 30 (?) | 5 |  | 40
LKr |  |  |  |  | 5 | 5
MUV | 10 |  | 30 (?) |  |  | 40
Total |  |  |  |  |  | 150
Central DCS – sub-detectors

## Slide 15: DCS tasks and resources needed (in days)
Central DCS – common tasks
Task | Resources needed (in days)
Integration of external information | 10
System management, operation and maintenance | 20
Test of common middleware | 10
Total | 40
Summary
 | Resources needed (in days) | Developer | End of contract
KTAG | 130 | Ryan Page | September 2014
Central DCS | 190 | Roman Fedoseev | May 2014

## Slide 16: DCS tasks and resources
Conclusion
In current situation the Central DCS team doesn’t have resources neither for consideration of new requirements nor for implementation of advanced control