## Slide 1: Electrical Infrastructure and Control Update, Schedule and Future Requirements Steve Griffiths 7th May 2013

## Slide 2: Contents
Decay Solenoid
  Replacement of Power supply and protection circuit
Quench Protection System
  DL system and future requirements
Rack Room 2
  Rack allocation and design considerations
  Alternative location and implications
Cooling Channel
  Main Control system
  AFC Power Supply and Instrumentation
  SS Power Supply and Instrumentation
RF System
  Electrical requirements

## Slide 3: Decay Solenoid Power Supply Replacement
FuG - Superconducting Magnet Power Supply - 10V, 1000A
Existing PSI Power Supply & Control System
SC Magnet, PSU and control system donated by PSI.
Operational for over 30 years.
Existing system is electrically noisy and unreliable.
New FuG Power Supply delivered June 2013.
Guaranteed for 2 years – need to review spares requirement.
System installed and electrically commissioned July 2013.

## Slide 4: Quench Detection System
Existing system contains obsolete components and new QD systems also required for AFC#1&2.
A QD system has been developed at DL.
Combining the reliable PSI philosophy with a modern modular designed.
Additional monitoring included but it has NO Data logging capability.
Commissioned June 2013.

## Slide 5: Quench Detection System for Cooling Channel
The new QD System has been successfully tested on the AFC#1.
Decay Solenoid and AFC#2 QD systems available June 2013.
The Spectrometer tests utilised the FNAL QD system.
  Combines protection and data logging – cost and size considerations
A specification for a QD system capable of protecting and diagnosis is being written.
An independent data logging system is currently being tested at DL.
AFC QD system configuration

## Slide 6: Cooling Channel Rack Location – RR2
Rack positions and cable management reviewed and optimised.
Cable lengths and sizes calculated.
Cost savings by directly installing in RR2.
Cables for cooling channel cannot be installed until rack & associated magnet are ready.
Only 7 racks required for Step IV.
Additional rack spaces available for Steps V & VI.

## Slide 7: Cooling Channel Rack Location – North Wall
7 Cooling Channel controls, instrumentation and power supply racks designed and under construction
An additional rack will be required for Vacuum and Compressor controls

## Slide 8: Cooling Channel Rack Configuration
Portable control and instrumentation racks designed, assembled and operational for AFC and SS.
Modifications and improvements incorporated in the final rack designs.
Cooling Channel Control Rack
Spectrometer #1&2 Control & Instrumentation Rack
AFC Control & Instrumentation Rack
AFC Power Supply Rack
Spectrometer #1 Power Supply Rack
Spectrometer #2 Power Supply Rack
Spectrometer #1&2 discharge circuit Rack

## Slide 9: Cooling Channel Control Rack
Blister
Front
Back
Control system designed and hardware procured.
Rack assembled and wire checked.
Rack houses – VME crates, CANBUS modules, ADC, DAC and serial interfaces.
Testing scheduled for June 2013

## Slide 10: AFC – Portable Control & Power supply rack
Two racks are required for the AFC#1&2.
  One rack containing instrumentation – control & monitoring
  And a separate rack for power supplies and energy absorbers
All instrumentation and control will be re-used in final design once testing complete,
Rack houses – VME crates, helium level monitors, temperature monitor / controllers, pressure indicators, power supply, energy absorbers and plant interfaces.

## Slide 11: AFC #1,2&3 – Control Rack
Controls system designed and hardware procured.
Rack assembled and wire checked.
Full integration testing scheduled for June 2013.
Rack houses – 3 x QD systems, He level gauges, temperature indicators / controllers, pressure indicators and interfacing.
Instrumentation for control and monitoring still needs to be purchased.
Equipment will also be reclaimed from portable control rack in R9.

## Slide 12: AFC #1&2– PSU Rack
Power supplies and energy absorber circuit designed and hardware procured.
Rack assembled and wire checked.
Full integration testing scheduled for June 2013.
Rack houses – power supplies & controllers, energy absorber modules, main contactors and interfacing.
Equipment will be reclaimed from portable control rack in R9.

## Slide 13: Spectrometer Control Rack
Controls system designed and hardware procured.
Rack assembled and wire checked.
Full integration testing scheduled for June 2013.
Rack houses – 2 x QD systems?, He level gauges, temperature indicators / controllers, pressure indicators and interfacing.
Instrumentation for controls and monitoring still needs purchasing.
Rack will be fully populated once testing at WANG completed.

## Slide 14: Spectrometer Energy Discharge Rack
Rack design complete and under construction.
One set of discharge circuits at DL.
Rack assembled complete May 2013.
Full integration testing scheduled for June 2013.
Rack houses – energy absorber circuits and fast discharge circuits.
Rack fully populated once testing at WANG completed.
Some module modifications required.

## Slide 15: Spectrometer Dump Circuit - Testing
Electrical insulation with good thermal conductivity added.
All modules to be thermally tested.
A cooling water failure will damage components and a reservoir tank needs to be assessed.
Max Temp on copper busbar - 85°C
Within minutes excessive temps reached on copper busbars.
Water failure

## Slide 16: Spectrometer PSU Racks
SS#1&2 power supply rack layout design complete.
Assembly started May 2013.
Rack will be fully populated once testing at WANG complete. (DL has 1 complete system)
Control & Instrumentation rack operational at WANG

## Slide 17: Assembly and Testing - RF System
RF System#1 assembled complete and testing well advanced.
Only manual control available and some system developments required.
Crowbar protection is sensitive and has a limited HV operating range.
RF System#2 partially constructed – lower priority
4616 Control & PSU
TH116 Control & PSU
TH116 Amplifier & Load

## Slide 18: Questions?
Thanks for listening